ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN (ESMP)

OF THE PROPOSED

CONSTRUCTION/UPGRADE OF THREE (3) MODEL PRIMARY SCHOOLS AT YELWAN DUGURI, DAGAUDA AND MASHEMA COMMUNITIES, BAUCHI STATE, NIGERIA

BY

THE BAUCHI STATE INCLUSIVE BASIC SERVICE DELIVERY AND LIVELIHOOD EMPOWERMENT INTEGRATION PROGRAM (IBSDLEIP)

SUBMITTED TO

FEDERAL MINISTRY OF ENVIRONMENT, MABUSHI, ABUJA –FCT”

FINAL REPORT

March, 2025

TABLE OF CONTENTS

LIST OF FIGURES	ix

List of Abbreviations and Acronyms	x

EXECUTIVE SUMMARY	xiii

ES 1.2: Project Background	xiii

ES 1.3 Objectives of the ESMP	xiii

ES 1.4 Scope of ESMP and Applicability	xiii

ES 1.5 Study Methodology	xiv

ES 1.6 Policy, Legal, and Regulatory Frameworks	xiv

ES 1.7 African Development Bank Environmental and Social Safeguard Policies	xiv

ES 2.1 Project Justification	xvi

ES 2.2	Project Sustainability	xvi

ES 2.2.1	Technical Sustainability	xvi

ES 2.2.2	 Socio-economic Sustainability	xvi

ES 2.2.3   Environmental Sustainability	xvii

ES 3.0 Project Description	xvii

ES 3.1 Description of the Construction Activities at the 3 Model Primary Schools	xvii

ES 3.2 Sourcing of water & other materials	xvii

ES 3.3 Project Location	xvii

ES 3.5 Typical Activities at the Operational Stage	xviii

ES 3.6 Manpower	xviii

ES 4.0 Description of Baseline Environment	xviii

ES 4.1 Biophysical Environment	xviii

ES 4.8 Socioeconomic Environment Assessment	xix

ES 4.8.1 Socioeconomic and health status of the project communities	xix

ES 5.0 Potential Impacts and Mitigation Measures	xx

ES 7.1 	Institutional Arrangements	xxxv

ES 7.2 Cost of Implementing the ESMMP	xxxv

ES 8.0 STAKEHOLDER CONSULTATION	xxxv

ES 8.1 Process and the methodology of Stakeholder consultation	xxxvi

ES 8.3 The outcome of the Stakeholder Engagement	xxxvi

ES 9.0: GRIEVANCE REDRESS MECHANISM	xxxvii

ES 9.1 Designated staff coordinating Grievance Redress	xxxvii

ES 9.2 Mode of receipt and recording of Complaints	xxxvii

ES 9.3 Structure of Grievance Redress	xxxvii

ES 9.4 Grievance Redress Mechanism Process	xxxvii

ES 10.0 Conclusion	xxxvii

CHAPTER ONE: INTRODUCTION	1

1.1 Introduction	1

1.2 Project Background	1

1.2.1 Programme Description	2

1.3 Objectives of the ESMP	2

1.4 Scope of ESMP and Applicability	3

1.4.1	Scope	3

1.4.2	Applicability	3

1.5 Study Methodology	3

1.6 Administrative, Policy, Legal, and Regulatory Frameworks	4

1.6.1	Nigerian Administrative Framework	4

1.6.2 Policy Framework	5

1.6.3 Specific Policies and Institutions in the Educational Sector	7

1.6.4 International Conventions and Treaties	9

1.7 African Development Banks Environmental and Social Safeguards Policies	10

AfDB Operational Safeguards	10

1.8 Structure of the ESMP	12

CHAPTER TWO: PROJECT JUSTIFICATION	13

2.1	Introduction	13

2.2	Project Justification	13

2.2.1	Need for the Project	13

2.2.2	Benefits of the Project	13

2.3	Project Sustainability	14

2.3.1	Technical Sustainability	14

2.3.2	Socio-economic Sustainability	14

2.3.3	Environmental Sustainability	14

CHAPTER THREE: PROJECT DESCRIPTION	16

3.1 Introduction	16

3.2 Project Location	16

3.2.1 Bauchi State	16

3.2.2 Dambam Local Government Area	17

3.2.3 Itas/Gadau Local Government Area	17

3.2.4 Alkaleri Local Government Area	17

3.3 Description of the Construction Activities of 3 Model Primary Schools	18

3.4 Sourcing of water & other materials	19

3.5 Site Layout	19

3.6 Project Facilities	20

3.7 Typical Model Primary Schools Activities at the Operational Stage	21

3.8 Manpower	21

CHAPTER FOUR: DESCRIPTION OF BASELINE ENVIRONMENT	22

4.1 Introduction	22

4.2 Data Acquisition Methods	22

4.3 Spatial Boundary for the Study	22

4.4 Environmental Components of the Study	22

4.5 Study Approach and Methodology	22

4.5.1 Description of Sampling Locations	22

4.5.2 Literature Review	22

4.5.3 Field Visits	22

4.5.4 Biophysical Components	23

4.6 Quality Assurance/Quality Control	23

4.7 Biophysical Environment	23

4.7.1 Climate/Meteorology	23

4.7.2 Ambient Air Quality and Noise Level	26

4.7.3 Soil Quality Assessment	27

4.7.4 Groundwater Quality	30

4.7.5 Biodiversity Assessment	35

4.7.5.2 Faunal species	37

4.7.7 Hydrogeology	40

4.8 Socioeconomic Environment Assessment	40

4.8.1 Sex, Age and Marital Status of the Respondents	40

4.8.2 Education	41

4.8.3 Number of children per household	42

4.8.4 Languages Spoken	42

4.8.5 Occupation	43

4.8.6 Income Level	43

4.8.7 Housing	44

4.8.8 Sources of water in the household	44

4.8.9 Experience of water shortage in the household	44

4.8.10 System of sewage disposal	45

4.8.11 Toilet types	45

4.8.12	Sanitation	46

4.8.13 Methods of refuse/solid waste disposal	46

4.8.14 Health and Hygiene	46

4.8.15 Factors responsible for good health	47

4.8.16 Factors responsible for household health risk	47

4.8.17 General health status of the respondents in the study area	47

4.8.18 Hygiene Practice of the Respondents	48

4.8.19 Types of Diseases Contracted by Respondents Households in the Past One Year	49

4.8.20 Number of Deaths recorded as Result of Contracting Diseases in the Past One Year	49

4.8.21 Age Group of Respondents Mostly Infected/Affected by Diseases	50

CHAPTER FIVE: POTENTIAL IMPACTS AND MITIGATION MEASURES	51

5.1 Introduction	51

5.2 Impact Assessment Approach and Methods	51

5.2.1 Impact Prediction or Identification:	51

5.2.1 Impact Characterization:	51

5.2.3 Impact Evaluation:	52

5.3 Identification of Environmental and Social (E&S) Impacts	61

5.3.1 Potential Positive Environmental Impacts	61

5.3.2 Potential Negative Environmental Impacts	63

CHAPTER SIX: MITIGATION AND ENHANCEMENT MEASURES	69

6.1	Introduction	69

6.2	Mitigation Approach	69

6.3 Mitigation and Enhancement Measures	69

CHAPTER SEVEN: ENVIRONMENTAL AND SOCIAL MANAGEMENT AND MONITORING PLAN (ESMMP)	79

7.1	Introduction	79

7.2	Environmental and Social Impacts and Mitigation (ESMP)	79

7.3 Institutional Arrangements	94

7.4 	Contractual Measures	97

7.5 	Capacity Building for Implementation of ESMP and Permit Conditions	98

7.6 Implementation Schedule	99

7.7 ESMP Cost & Analysis	101

CHAPTER EIGHT: STAKEHOLDER CONSULTATION	103

8.1 Introduction	103

CHAPTER NINE: GRIEVANCE REDRESS MECHANISM	106

9.1 Introduction	106

9.2 Designated staff coordinating Grievance Redress	106

9.3 Mode of receipt and recording of Complaints	106

9.4 Structure of Grievance Redress	106

Expectation When Grievances Arise	107

Management of Reported Grievances	107

Monitoring Complaints	107

9.5 Grievance Redress Mechanism Process	107

9.6 GRM Jurisdiction	110

9.7 AfDB GRM …………………………………………………………………………………………………………………………………110

CHAPTER TEN: CONCLUSION	111

10.1 Introduction	111

References	112

Annex 1: Attendance Sheet	113

Annex II: Sampling Locations	114

Ground Water sampling locations	114

Annex III: Questionnaire used for the socio-economic survey	115

Annex IV: Pictures of the existing structures at the schools	123

LIST OF TABLES

Table 1 : Policies, Legal and Regulatory Frameworks	5

Table 2 : International Treaties and Conventions on Environment to which Nigeria is a Party	9

Table 3 : AfDB Operational Safeguards Policies Triggered	11

Table 4 :  Bauchi State AfDB-Assisted IBSDLEIP Construction of model Primary schools.	19

Table 5 : Estimate of manpower required at various stages of project	21

Table 6 : The ambient air quality and noise levels	27

Table 7 : Physico-chemical characteristics of soil collected from the project sites	27

Table 8 :  Water quality parameters at 3 Model Primary Schools.	31

Table 9 : Biodiversity of the project sites	35

Table 10 : Common faunal species found in the vicinity of the project sites.	37

Table 11 : Age Distribution of Respondents	40

Table 12 : Sex Distribution of Respondents	41

Table 13 : Number of children per household	42

Table 14 : Primary Occupation	43

Table 15 : Income levels	43

Table 16 : Types of Housing	44

Table 17 : Main Source(s) of Water in the Household	44

Table 18 : Experience of water shortage in the households	44

Table 19 : Frequency of clearing bushes around household surroundings	46

Table 20 : Information on health and hygiene status of the household	46

Table 21 : Factors responsible for good health in the households	47

Table 22 : Factors responsible for household health risk	47

Table 23 : General Health Status of the respondents in the study area	47

Table 24 : List of Hygiene Practice/Protocol Practiced by Respondents	48

Table 25 : Types of Diseases Contracted by the Household in the Past One Year	49

Table 26 : Number of Deceased Persons Recorded after Contracting the Below Listed Diseases in the Past One Year.	49

Table 27 : Age Group of Respondents Mostly Infected/Affected by Diseases	50

Table 28 . Substances Commonly Abused by within the Community	50

Table 29 : Impact categories used in this study	51

Table 30 : Probability of Impact Occurrence	52

Table 31 : Consequence and Severity of Impacts	52

Table 32 : Risk Assessment Matrix	53

Table 33 : Impact Rating	53

Table 34 : Impact Assessment Matrix	54

Table 35 : Identified Positive Impacts of Proposed interventions at selected facilities	615

Table 36 : Identified Negative Impacts of Proposed interventions at selected facilities	637

Table 37 : Proposed Mitigation Measures	59

Table 38 a: Environmental, Social Management and Monitoring Plan Matrix	80

Table 39 : Institutional Arrangement for ESMP Implementation	94

Table 40 : Contractual Measures	97

Table 41 : Capacity building plan for implementation of the ESMP & permit conditions	98

Table 42 : Implementation Schedule	88

Table 43 : Cost of implementing the ESMP	101

Table 44 : Methods, Tools and Techniques for Stakeholder Engagement in School project	103

Table 45 : Record of Engagement carried out at the various school project sites	104

Table 46 : Outcome of stakeholder consultations held for the school construction projects	104

# LIST OF FIGURES

Figure 1    Map of Bauchi State showing the proposed sites for the 3 Model Primary Schools.	18

Figure 2 : Proposed Site Plan, Model Primary Health Care Centre, Dagauda	20

Figure 3 : Proposed Site Plan, Model Primary School, Yelwan Duguri	20

Figure 4 :  Proposed Site Plan, Model Primary School, Mashema	20

Figure 5 : State mean annual temperature in Bauchi State 2007-2021	24

Figure 6 : State mean annual Precipitation in Bauchi State 2007-2021	24

Figure 7 : Wind  direction at Mashema Model Primary School project site	25

Figure 8 : Wind speed at Mashema Model Primary School project site	25

Figure 9 : Wind direction at Dagauda Model Primary School project site	25

Figure 10 : Wind speed at Dagauda Model Primary School project site	26

Figure 11 : Wind direction at Yelwan Duguri Model Primary School project site	26

Figure 12 : Wind speed at Yelwan Duguri project site.	26

Figure 13 : Marital status	41

Figure 14 : Educational qualification	42

Figure 15 : Ethnic composition	43

Figure 16 : System of Sewage Disposal	45

Figure 17 : Toilet types	45

Figure 18 : Methods of solid wastes disposal	46

Figure 19  shows a proposed Grievance Redress Mechanism flow process for the IBSDLEIP.	109

| # List of Abbreviations and Acronyms |  |
| --- | --- |
| AfDB | African Development Bank |
| BASG | Bauchi State Government |
| BASEPA | Bauchi State Environmental Protection Agency |
| BASMEnv | Bauchi State Ministry of Environment |
| CESMP | Contractor Environmental and Social Management Plan |
| CBOs | Community Based Organizations |
| CoC | Code of Conducts |
| CO | Carbon Monoxide |
| CO2 | Carbon Dioxide |
| CSOs | Civil Society Organizations |
| DPs | Development Partners |
| EC | Electrical Conductivity |
| ESAP | Environmental and Social Assessment Procedure |
| ESMP | Environmental and Social Management Plan |
| ESSO | Environmental & Social Safeguard Officer |
| FMEnv | Federal Ministry of Environment |
| GBV | Gender-based Violence |
| GRM | Grievance Redress Mechanism |
| HSE | Health, Safety, and Environment |
| IBSDLEIP | Inclusive Basic Service Delivery and Livelihood Empowerment Integration Program |
| JHA | Job Hazard Analysis |
| LGAs MDAs | Local Government Areas Ministries, Departments, and Agencies |
| NGOs | Non-Governmental Organizations |
| NSDWQ | National Standard for Drinking Water Quality |
| NIMET | Nigeria Meteorological Agency |
| NO2 | Nitrogen Dioxide |
| OM | Organic Matter |
| PAPCs | Project Affected Persons and Communities |
| PAPs | Project Affected Persons |
| PCU | Project Coordinating Unit |
| PHCs | Primary Health Care Centres |
| PIU | Project Implementation Unit |
| PPEs | Personal Protective Equipment |
| RfP | Request for Proposal |
| RTA | Road Traffic Accidents |
| OHS | Occupational Health and Safety |
| SEA | Sexual Exploitation and Abuse |
| SO2 | Sulphur dioxide |
| SPM | Suspended Particulate Matter |
| STDs | Sexually Transmitted Diseases |
| TMP | Traffic Management Plan |
| UBEC | Universal Basic Education Commission |
| VAC | Violence Against Children |
| WHO | World Health Organization |
| WMP | Waste Management Plan |

# EXECUTIVE SUMMARY

Es 1.0 Introduction

The Bauchi State AfDB-Assisted IBSDLEI Programme (hereinafter referred to as ‘the Project Implementation Unit’ or the ‘PIU’), wishes to construct three (3) Model Primary Schools at Yelwan Duguri, Dagauda and Mashema townships in Bauchi State. Considering the importance, the PIU attaches to the protection of the environment as well as the health and safety of the host communities, and in order to comply with the African Development Bank’s (AfDB) safeguards policies, national and Bauchi States environmental policies, it commissions the preparation of an Environmental and Social Management Plan (ESMP) with a view to ascertaining the potential and associated impacts of the project on the environment and people’s health and well-being.

## ES 1.2: Project Background

The Inclusive Basic Service Delivery and Livelihood Empowerment Integration Program (IBSDLEIP) is part of Federal Government efforts toward Northeast States Emergency Transition, Recovery, and Peace building, elaborated by the five-year programmatic “Buhari Plan” of 2016.

The Program is anchored on three (3) major reinforcing components as elaborated below.

Component I: Service Delivery

This component will promote restoration, access, and utilization of basic social services in health, education, water, and sanitation (with targeted interventions in infrastructure provision, skills acquisition, and upgrading, rural water, and sanitation reform) and community-based nutrition support programmes.

Component II: Economic Recovery

This component will promote job creation and entrepreneurship with a focus on youth and women. It will also support the reconstruction of Major markets to recover commerce. Additionally, tailored training to upgrade the skills of artisans and equip them to take better, the economic opportunities arising from public work programmes resulting from reconstruction and rehabilitation of infrastructure in component 1 and other economic integration activities will be undertaken.

Component III: Institutional Strengthening and Project Management

Institutional strengthening interventions include technical assistance to the Women Empowerment Fund to facilitate loan disbursement to women SMMEs, enhanced capacities of the Ministry of Labour and Employment for enforcement and monitoring of the Private Agency Employment Regulation;

## ES 1.3 Objectives of the ESMP

The objectives of the ESMP are to identify the beneficial and negative impacts that could emanate from the proposed project and associated activities, identify measures to prevent and mitigate undue harm to people and the environment because of the project, recommend mitigation/enhancement measures, monitoring, consultations, and institutional strengthening measures to be undertaken during project implementation and operations.

## ES 1.4 Scope of ESMP and Applicability

The scope of this ESMP covers the construction and sustainable operations of three (3) Model Primary Schools at Yelwan Duguri, Mashema, and Dagauda Towns of Bauchi State. The ESMP emphasizes the incorporation of environmental, occupational health & safety, and social aspects associated with the construction and operational activities of the Model Primary Schools.

## ES 1.5 Study Methodology

The methodology comprised a desk review of documents such as engineering designs to obtain secondary data on the project area. Field visits, stakeholder engagement, and consultations were also carried out from 5th to 10th September 2022 in the three communities.

This methodology has enabled the identification of environmental and social sensitivities associated with the project and have facilitated the preparation of mitigation measures aimed at eliminating or minimizing adverse environmental and social impacts of specific actions, projects, or programs while also enhancing positive effects.

## ES 1.6 Policy, Legal, and Regulatory Frameworks

The ESMP is governed by relevant legal, Institutional, and regulatory frameworks at the Federal and State levels. The most relevant federal legislation is the Environmental Impact Assessment (EIA) Act No. 86 now LFN EIA Act Cap LFN 2004.

## ES 1.7 African Development Bank Environmental and Social Safeguard Policies

To ensure environmental sustainability by protecting the people and environment from potential adverse impacts of projects, the African Development Bank Group developed an Integrated Safeguards System (ISS) in December 2013.

The Bank’s Integrated Safeguards Policy Statement sets out the Bank’s own commitments to and responsibilities for delivering the ISS to

- ensure the systematic assessment of E&S impacts and risks;

- apply the Operational Safeguards OSs to the entire portfolio of Bank operations;

- support clients and countries with technical guidance and practical support in meeting the requirements;

The ISS consists of four parts: (i) an overall Policy Statement; (ii) five Operational Safeguards (OSs); (iii) technical guidance in the form of Environmental and Social Assessment Procedures (ESAP); and (iv) a set of Integrated E&S Impact Assessment (IESIA) guidance notes.

AfDB Operational Safeguards:

The AfDB have five operational safeguards that are used to ensure adequate protection of the environment and people from negative impacts of projects. Over time the Bank may adopt additional safeguard requirements or update existing requirements to enhance effectiveness, respond to changing needs, and reflect evolving best practices. The objectives of the five OSs include:

- To integrate considerations of E&S impacts into Bank operations to promote sustainable development in Africa;

- Ensure projects are prevented from adversely affecting the environment and local communities or, where prevention is not possible, minimise, mitigate and/or compensate for adverse effects and maximize development benefits;

- Avoid the impact of climate change on the sustainability of investment projects and the contribution of projects to global greenhouse gas emissions;

Out of these five, four are triggered while one is not triggered in this project as outlined in Table ES1 below:

Table ES 1: Operational Safeguards Policies Triggered by the Project

| AfDB Operational Safeguard | Description | Triggered (Yes/No) |
| --- | --- | --- |
| OS 1: Environmental and Social Assessment | This overarching safeguard governs the process of determining a project’s environmental and social category and the resulting environmental and social assessment requirements | This OS is triggered because the construction and upgrade activities will have environmental interactions with potential negative impacts to the environment and humankind |
| OS 2: Involuntary Resettlement: Land Acquisition, Population displacement and Compensation | This OS consolidates the policy commitment and requirements set out in the Bank’s policy on involuntary resettlement and incorporates a few refinements designed to improve the operational effectiveness of those requirements | This OS is not triggered. All activities are within existing footprint. |
| OS 3: Biodiversity and Ecosystem Services | This OS aims to conserve biological diversity and promote the sustainable use of natural resources. | This OS is triggered. Triggered due to land clearing operations and potential disturbance of vegetation |
| OS 4: Pollution Prevention and Control, Greenhouse Gases, Hazardous Materials and Resource Efficiency | This safeguard covers the range of key impacts of pollution, waste and hazardous materials for which there are agreed international conventions, as well as comprehensive industry-specific and regional standards, including greenhouse gas accounting, that other multilateral development banks follow. | This OS is triggered Triggered because construction and medical wastes will be generated during construction and operational phases respectively |
| OS 5: Labour Conditions, Health and Safety | This safeguard establishes the Bank’s requirements for its borrowers or clients concerning workers’ conditions, rights and protection from abuse or exploitation. It also ensures greater harmonization with most other multilateral development bans | This OS is triggered. Triggered because local and migrant workers as well as skilled and unskilled workers will be engaged in the project. There is therefore potential for risks to health and safety of workers during project implementation |

ES 1.8 Structure of the ESMP

The structure of this ESMP report is presented below.

Chapter1. Introduction: Provides a background to the proposed Project, its key stakeholders and the ESMP. The Administrative, Policy and Regulatory Frameworks within which the ESMP was undertaken were also covered in the chapter.

Chapter2. Project Justifications: It justifies the project.

Chapter3. Project Description: The chapter provides a description of the Project

## ES 2.1 Project Justification

Various international conventions and national laws at the state and federal levels agree that education is essential to the development of every nation and state and that basic education should be compulsory and free. The most popular of these acts is the Universal Basic Education Act 2004 which not only outlines the role of government and divides responsibility between the three levels, but also emphasizes the role of parents/guardians and the funding of this basic education.

Educational infrastructure is an important factor in the quality of learning and the number of graduates, but most public schools lack basic infrastructure such as a laboratory, library, electricity, and a quality learning environment. While the existing infrastructure in some public schools is in a deplorable state, others are below acceptable standards and, in some cases, non-existent.

Benefits of the Project

Primary school is globally recognized as the foundation of all levels of education. It provides the mini-structural framework on which the quality of other levels of education is anchored. The following are the major benefits of the Model Primary Schools project

- The better learning environment and Improvement in students’ performance

- Provision of a good school environment reduces absenteeism among teachers and students

- Increase in enrolment and reduction in the number of dropouts and out-of-school children

- Complementing the efforts of achieving Sustainable Development Goal 4.

## ES 2.2	Project Sustainability

### ES 2.2.1	Technical Sustainability

The Project Implementation Unit (PIU) should ensure that competent contractors with proven track records are engaged for the construction work. The contractor should ensure all the structures are built to international standards and ESMP consultants ensure that the project is constructed using high-quality materials.

### ES 2.2.2	 Socio-economic Sustainability

The following measures should be considered to guarantee the social sustainability of the project:

- The project’s social sustainability is guaranteed because of deep engagement and consultation with local stakeholders at all stages of the project’s planning, construction, and operations.

- Prompt payment of adequate compensation package to displaced project-affected persons and communities (PAPCs)

The employment opportunity created would reduce joblessness, increase the economic status of the community, and reduce youth restiveness.

### ES 2.2.3   Environmental Sustainability

To ensure environmental sustainability, the following measures would be considered

- Commissioning of a comprehensive Environmental Impact Assessment

- Implementation of the Environmental Management Plan

- Proper monitoring of the environmental management plan developed in the ESMP study at the construction and operational stages of the project

- Consultation and participation of the project-affected persons and communities

- Standard site layout to ensure proper alignment of the facilities to minimise the risks of water erosion, flooding etc.

## ES 3.0 Project Description

The Construction activities of the Model primary schools at Yelwan Duguri, Dagauda, and Mashema will involve the construction of a perimeter fence around the clinic, the construction of the main building renovation of some existing structures, the provision of teaching aids and the construction of staff quarters with furnishings

## ES 3.1 Description of the Construction Activities at the 3 Model Primary Schools

The construction/upgrade activities of the 3 model primary schools at Yelwan Duguri, Dagauda, and Mashema will involve the construction of a perimeter fence around the clinic, constructing the main building renovation of some existing structures, and providing the provision of school working Equipment, and the construction of staff quarters with furnishings.

## ES 3.2 Sourcing of water & other materials

Naturally occurring construction materials such as water, fine sand, and aggregates are available in the project area. Where applicable, approvals would be obtained for the extraction of raw materials. Materials that will be used are:

- Water: Water for the proposed primary healthcare center work can be sourced from existing boreholes within the vicinity of the project area and this would be delivered by water truck to the site.

- Fine Sand: There are no rivers close to the project sites for the construction of the three model primary schools. Therefore, fine sands need to be sourced from other places. In doing so, all the necessary measures to ensure material transport and handling are carried out according to Health, Safety, and Environment (HSE) standards in this ESMP will be in place.

## ES 3.3 Project Location

The proposed projects will be located in Yelwan Duguri, Mashema and Dagauda towns located at Alkaleri, Itas/Gadau and Dambam Local Governments of Bauchi State.

ES 3.4 Project Facilities

The 3 Model Primary Schools were designed according to the prescribed national standard and in conformity with the international based practices. The Construction/upgrade activities of 3 Model Primary Schools at Yelwan Duguri, Dagauda and Mashema involves; provision of school perimeter fencing, renovation of some existing structures, demolition and alteration and Construction of class room blocks, offices, stores, libraries, laboratories, school garden, recreational facilities, and construction of staff quarters including furnishings.

## ES 3.5 Typical Activities at the Operational Stage

The activities in the model schools during the operational stage teaching and learning, practical demonstrations in the laboratories, gardening, arts and crafts instructions, debates, quizzes and different sporting activities.

## ES 3.6 Manpower

The project will require both skilled and unskilled manpower at the pre-construction, construction, operational and Demobilization phases. It is envisaged that about 96 unskilled and 72 skilled workers will be needed in the 3 facilities during the various phases of the project.

## ES 4.0 Description of Baseline Environment

The baseline conditions of the project site were assessed to establish a reference against which environmental changes and impacts during the construction and operational phases of the project could be evaluated and monitored. The data acquired would also be used in impact analysis.

The baseline data were generated using several methods such as literature reviews, collection of soil, water, and air samples, laboratory analysis, household survey, interviews, and focused group discussions among others.

## ES 4.1 Biophysical Environment

Climate and Meteorology

Bauchi State has a rainfall regime ranging from 1,300 mm per annum in the south (savanna zone) to only 700 mm in the far north (BSADP, 2007). This is due to rainfall patterns in the West African sub-region. The rain comes from the south and moves northwards. The rainy season begins earlier in the southern part of the state, where it is heaviest and lasts longer.

Air Quality and Noise

The results of the ambient air quality assessment revealed that NH3 and PM10 fell within the acceptable guideline values. However, SO2, H2S, and CH4 were not detected in all the locations sampled, which may be due to low vehicular movement in the vicinity of the project sites at the time of measurement. Furthermore, the results of the measurements of the ambient noise levels in the study area show that the recorded levels ranged between 40dB (A) and 46.5 dB (A).

Soil Quality

The analysis of soil collected at the vicinity of the model schools’ sites revealed normal values typical of soils of Bauchi State. The soil pH averages 7.0, 6.9 and 7.0 for Mashema, Yelwan Duguri and Dagauda respectively, this meaning that the pH of soil in the area is generally neutral.  The Electrical Conductivity (EC) values of 35µS/cm each was recorded for soil samples collected at Mashema and Dagauda while 30µS/cm was recorded at Yelwan Duguri project sites. The EC of the soil in all the project sites is generally low.

Ground Water Quality

The result of the ground water quality analysis showed no serious pollution problems as parameters were below the limits set by NSDWQ (2007) and WHO (2022) except for some few parameters. The turbidity (18NTU) recorded at Mashema project site exceeded the 5NTU limit set by NSDWQ and WHO.  The mean dissolved oxygen values of 8.10mg/l, 8.40mg/l and 7.30mg/l recorded from the project sites at Mashema, Dagauda and Yelwan Duguri respectively are considered to be optimum as they are well above the 3.0mg/L and 6.5mg/L recommended by NSDWQ (2007) and WHO (2022) respectively.

Vegetation

The project area is located in the Sudan savannah and the northern semi-arid zone. The most common tree species found in the Sudan savannah in southern Bauchi includes Khaya senegalensis, Terminalia laxifora, Detarium macrocarpurn, Anogeissus leiocarpus, Vitellaria paradoxa and Bosweillia dalzielii.

Wildlife

Mammal species known to inhabit the project area include: Rattus rattus (Rat), Epixerus ebii (Squirrel), Thryonomys swinderianus (Grass cutter), Atherupus africanus (Porcupine) and Felix libya (Wild cat) among others.

Geology

The geology of Bauchi state is broadly divided into areas underlined by crystalline basement complex rocks and the sedimentary rocks. The southwestern part of the State is covered by Precambrian-Paleozoic basement rocks, while the southeastern part of the state is covered by the Paleocene Kerri-Kerri formation.

## ES 4.8 Socioeconomic Environment Assessment

The project will take place at Dambam (in Dambam LGA), Mashema (Itas/Gadau LGA) and Yelwan Duguri (in Alkaleri LGA) all in Bauchi State.

Dambam Local Government Area is located in the northern part of the State and shares borders with Darazo, Misau, Katagum and Gamawa local government areas. With an administrative headquarters at Dambam, the LGA has an area of 1,077 km2 and a population of 150,922 as at the 2006 census. Major towns in the LGA include Dagauda, Dambam, Jalam, and Yamai.

Itas/Gadau is also located in the norther part of the state. The LGA has an area of 1,398 km2 and a population of 229,996 at the 2006 census. The predominant ethnic groups in the area includes the Hausa, Fulani and Kanuri. Mashema the project community is one of the major towns in Itas/Gadau LGA.

Alkaleri is a Local Government Area It has an area of 5,918 km2 and a population of 329,424 at the 2006 census. The predominant ethnic groups in the area is the fulani, Kanuri, Dugurawa, Guruntawa and Labur "Jaku" people.

### ES 4.8.1 Socioeconomic and health status of the project communities

Majority of the respondents in the three communities are between the ages of 41-50 followed by those between 31-40 years. This shows that most of the respondents are within their active age group and can offer a labour pool from which contractors can source for workers for the sub-projects. The result showed that 67 % of the respondents were male while 33 % were female.

The educational level of the respondents showed that 10% of the respondents had less than primary education, 19.5% had Qur’anic education, about 37% have attended and completed primary school, 20% completed secondary school, while 13.4% had tertiary education qualification, this includes those that have a diploma, Nigerian Certificate in Education and Degree certificates.

The number of children per household was one of the socioeconomic characteristics examined; the findings revealed majority representing 57.6% had between 4 to 7 people in their household. The study also revealed that the project communities speak different languages including Hausa, Fulani, Karai-Karai, Yelwan Duguri, Gerawa and Jarawa. Primary occupation of the respondents in the study area revealed that 62.5% of the respondents were into farming, The majority (66%) of the respondents had an income of N200,000 -N400,000 per annum The projects will boost the health status of the community members which in turn will enable them to improve their personal income and wellbeing.

The major source of water as reported by 70% of the respondents is borehole. Other sources are tap water and rainwater as reported by 22% and 8% respectively. Majority of the respondents experience seasonal water shortage during the dry months. Pit latrine is the main type of toilet used by households in the sampled communities as indicated by 82% of the respondents.

Malaria fever is the most prevalent (57.5%) disease affecting the communities. Substance abuse has become a very serious menace in various communities more especially among the youths in the society.

## ES 5.0 Potential Impacts and Mitigation Measures

The construction/rehabilitation works of the Model Primary School may result in environmental and social impacts, which may be negative or positive. Some of the potential positive and negative impacts are discussed in Tables ES 2 and ES 3 below.

Table ES 2: Identified Positive Impacts of Proposed interventions at selected facilities

| No. | Impact | Key receptor(s) | Evaluation |
| --- | --- | --- | --- |
| 1 | Provision of good school environment reduce absenteeism among teachers and students Increase in enrolment and reduction in the number of drop-outs and out of school children Complementing the efforts of achieving Sustainable Development Goal 4. | Pupils, teachers, communities and Responsible government agencies | The proposed project when completed will deliver these benefits: Better learning environment and Improvement in students’ performance |
| 2. | Employment generation | Community members | The proposed project activities will create employment opportunities for skilled and unskilled labour during the construction and operational stages. In addition, indirect employment opportunities such as food vendors, petty traders and suppliers of raw materials for construction will be created. During the operational phase, job opportunities will be created for healthcare workers, maintenance workers and suppliers, waste management companies, etc. |
| 3. | Improvement in local and national economy | Neighboring communities, LGAs and national economy | The creation of direct and indirect job opportunities during the construction and operational phases of the project will boost the local and national economy |
| 4. | Improvement in public goodwill | Bauchi State Government, LGAs (Alkaleri, Dambam and Itas/Gadau) | Improved trust and satisfaction in governance in Bauchi State. |
| 5. | Improvement in management of resources | Neighboring communities, State Government, MDAs | Provision of a lead way to drive the State Government towards ensuring improved infrastructure and sustainability |
| 6. | Capacity building and strengthening of institutions | State Government, MDAs | Capacity building through: Strengthening of facility rehabilitation works and supervision systems of personnel involved in the project activities, including improvement in institutional responsibilities for construction and maintenance. Skills transfer |

Table ES 3: Identified Negative Impacts of proposed interventions

| Project Phase and Activities | Environmental Aspect | Environmental Receptor |  | Associated and Potential Impacts | Evaluation |
| --- | --- | --- | --- | --- | --- |
| Mobilization of equipment, machinery, and heavy-duty vehicles | Movement of heavy-duty vehicles transporting personnel, equipment and materials to site Fugitive dusts and vehicular exhaust emissions Noise & Vibration Stationary positioning of heavy-duty vehicles and equipment Presence of valuable assets on site Engagement of local staff | Surrounding Communities, Air, Soil, Flora and Fauna, Project Workers |  | Movement of heavy-duty vehicles transporting personnel, equipment and materials to site Fugitive dusts and vehicular exhaust emissions Noise & Vibration Generation Stationary positioning of heavy-duty vehicles and equipment Increased risk of social unrest if construction workers are not recruited from the local community Increased risk of social unrest if construction workers are not recruited from the local community Landscape disruption and visual intrusion due to presence of equipment, vehicles and trucks Risks of accidents from struck-by injuries to workers from the movement of heavy-duty vehicles Risks of Gender Based Violence (GBV)/Sexual Exploitation Abuse (SEA) resulting from the interaction between contractors and members of the communities Disruption of traffic flow and increased risk of Road Traffic Accidents (RTAs) due to movement of heavy-duty vehicles. Risk of security breaches and threat to lives and properties due to storage of materials and equipment on site Presence of valuable assets on site Respiratory and eye related problems in residents of surrounding communities from exposure to fugitive dusts Engagement of local staff Soil compaction and increased susceptibility to erosion as a result of operation and stationary positioning of heavy-duty vehicles | Low-Medium, Direct, Short-term and Local |
| Mobilization of workers to site | Movement of heavy-duty vehicles transporting personnel, equipment and materials to site Fugitive dusts and vehicular exhaust emissions | Surrounding communities, Air, Soil, Flora and Fauna, Project Workers |  | Unauthorized movements of construction workers, construction equipment, machinery, and heavy-duty vehicles (during and after working hours) could result in trespassing Damage to local land and property and invasion of privacy of local residents Disparity of pay, increase in disposable income and potential availability of illegal substances, illicit or culturally inappropriate lifestyle choices, leading to increased tension between local communities and the workers. Increasing incidents of crime and or violence and threats to the safety of local community members. Occupational accidents and injuries to workers and risk to community health and safety Exposure to communicable diseases | Medium, Direct, Short-term, Local |
| Supply of materials – cement, sand, pipes, planks etc. | Noise & Vibration Generation | Air, Land, Workers |  | Traffic congestion and risk of road traffic Occupational accidents and injuries to workers and risk to community health and safety | Medium, Direct, Short-term |
| Site clearing and preparation | Clearing of land for new construction | Surrounding communities, vegetation, soil, air and water, |  | Air quality deterioration from release of dusts and gaseous emissions from exposed soil surfaces and vehicles Occupational accidents and injuries to workers and risk to community health and safety Noise and vibration from the use of machineries and motorized equipment Loss of vegetation cover due to clearing of project site Reduction in carbon sequestration in the project area due to removal of trees Disturbance/Destruction of flora and fauna habitat and loss of fauna due to site clearing including susceptibility of plants to pathogenic infections due to mechanical bruises Increase in amounts of fugitive dust, exhaust fumes and GHGs from movement of heavy-duty vehicles and equipment into work areas Noise and vibration from movement of heavy-duty vehicles Landscape disruption and visual intrusion | High, Direct, Long-term |
| Installation of Temporary Structures for workers including storage area, water supply system, electricity, sanitation and waste disposal areas etc. | Waste Generation Noise and Vibration Generation Installation of Site Structures | Affected communities, Workers, Soil and Land |  | Noise and vibration disturbances in surrounding communities from the use of machineries and motorized equipment. Generation of hazardous and non-hazardous wastes from construction activities. Soil contamination from indiscriminate dumping of hazardous wastes. Risk of occupational accidents and injuries to workers | Medium, Short-term, Direct |
| CONSTRUCTION PHASE |  |  |  |  |  |
| Excavation for foundations of new buildings |  | Air, Soil, Communities | Deterioration of local air quality due to the release of fugitive dusts from excavation for foundations of new buildings Noise and vibration from construction equipment, traffic and activities, may disturb sensitive noise receptors (i.e. humans). Loss, damage, erosion, and disruption of soil from exposure of soil surfaces to rain and wind. Real or perceived disruption to normal operational life of the facilities, through the physical presence of a workforce. Direct employment of local population in workforce and stimulation of local economy Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems, and result in conflicts over water use. Inefficient estimation of materials during construction leading to excess consumption of materials, generation of wastes/emissions, pollution of soils and water. Increased respiratory and eye related problems from exposure to dusts and gaseous emissions. |  | Medium, Direct, Short-term |
| Earthworks and concrete works including floor paving and Fencing | Engagement of local staff | Air, Soil, Communities |  |  | Medium, Direct, Short-term |
| Roofing of renovated and new building and installation of internal and external finishing materials as well as painting | Noise level Waste Generation Engagement of local workers | Air, Water, Soil, People | Increased noise level within the environment as a result of roofing works Generation of Hazardous waste like paint cans and other aerosols Generation of non-hazardous waste from other material packages |  | Low, Direct, Short-term |
| Renovation of existing structures | Noise Generation of waste Disturbance to facility | Air, Land, Water, People | Generation of noise from removal and replacement of materials during renovation Generation of Hazardous and Non-Hazardous waste during renovation Disruption of the activities at the facilities as a result of renovation of existing structures |  | Low, Direct, Short-term |
| OPERATIONAL PHASE |  |  |  |  |  |
| Site Operation activities | Waste Generation (Including Health Care Wastes | Air, Water, Soil, People | Generation of solid waste from the usage of renovated and new buildings Generation of Hazardous waste streams like used batteries, used solar panels, fluorescent tubes and spent oil, Generation of increased medical waste as the interventions will improve, utilization of the facilities |  | Medium, Direct, Short-term |
|  | Use of generators Soil contamination (from accidental diesel/lubricant spills), Occupational health issues etc. all need to be assessed. Congestion if too many staff are recruited Potential water shortage | Air, Water, Soil, People | Deterioration of local air quality due to emission from generators Noise and vibration from generators, may disturb sensitive noise receptors (i.e. humans). Soil pollution from generator house Risks of accidents, incidents and near misses from use of healthcare facilities, vehicles and equipment Disruption to normal operational life of the facilities, through the physical presence of too many staff. Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems, and result in conflicts over water use. |  | Medium, Direct, Short term, Local |
| Decommissioning Phase |  |  |  |  |  |
| Occupational/ public safety and traffic impacts |  | Workers, pupils, teachers, public | The relocation of all construction facilities and remaining materials including concrete mixers, trucks, and water tanks to new sites or the contractor’s office could result in accidents and injury to workers. The removal and transport of such equipment and materials could also pose traffic risks and public safety concerns within the schools and along the routes. |  | Medium, Direct, Short-term, Local |
| Waste management |  | Workers, pupils, teachers, public | The dismantling and removal of equipment and materials at the site, as well as landscape restoration works could generate waste such as scraps of metal, wood, concrete debris, vegetative material, and garbage (pieces of plastic bags, food wrappers, etc.). |  | Medium, Direct, Short-term, Local |

ES 6.0 Mitigation and Enhancement Measures

This project is envisaged to generate both positive and negative impacts on the biophysical and socioeconomic environment. However, the negative impacts anticipated will be localized in spatial extent, short in duration and can be reduced through compliance with appropriate mitigation measures. In this section, technically and financially feasible mitigation measures will be proffered to address environmental and social impacts associated with the construction and upgrade of the model schools in Dambam, Mashema, and Yelwan Duguri in Bauchi State.

Table ES 4: Proposed Mitigation Measures

| Project Phase and Planned Activities | Associated and Potential Impacts | Pre mitigation (Significance) | Mitigation Measures | Post Mitigation (Residual Significance) |
| --- | --- | --- | --- | --- |
|  | Pre-Construction Phase |  |  |  |
| Mobilization of personnel, equipment and materials to project sites | Deterioration of local air quality due emissions from heavy duty vehicles transporting personnel, equipment and materials to site | Medium | Implement Dust control through dampening and wetting. Use of modern equipment and regular maintenance. Avoiding the use of ozone depleting substances during construction. | Low |
|  | Noise and vibration disturbances from movement of heavy-duty vehicles | Medium | Use of modern, well-maintained equipment fitted with abatement devices (e.g. mufflers, noise enclosures) Strict controls of timing of activities | Low |
|  | Soil compaction and increased susceptibility to erosion as a result of operation and stationary positioning of heavy-duty vehicles | Medium | Retention of topsoil for restoration (including tilling and Re-vegetation) as soon as practicable. | Low |
|  | Disturbance and displacement of terrestrial fauna as a result of noise and vibration from heavy duty vehicles. | Medium | Observance of seasonal sensitivities (e.g. breeding seasons), and alteration of activity to reduce noise levels at that time | Low |
|  | Disruption of traffic flow and increased risk of road traffic accidents | High | Develop and implement a traffic management plan | Low |
|  | Increase in revenue and job creation | Medium | Give priority to local people who have expertise | Medium |
|  | Security breaches and threat to lives and properties. | Medium | Develop a security management plan | Low |
|  | Respiratory and eye related problems in residents of surrounding communities from exposure to fugitive dusts. | medium | Implement Dust control and suppression measures, such as use of dampening and wetting | Low |
|  | Landscape disruption and visual intrusion due to presence of equipment, vehicles and trucks | Medium | Rehabilitation of trampled areas with native species, and ecosystem restoration. | Low |
|  | Risks of Gender Based Violence (GBV)/Sexual Exploitation Abuse (SEA) resulting from the interaction between contractors and members of the communities | Medium | Develop and Implement Code of Conduct for workers that specifically prohibit GBV and SEA | Low |
|  | Disruption of traffic flow and increased risk of Road Traffic Accidents (RTAs) due to movement of heavy-duty vehicles. | High | Ensure that heavy duty trucks and major haulages are done during traffic off-peak periods to reduce the possibility of Road Traffic Accidents | Low |
|  | Risks of accidents from struck-by injuries to workers from the movement of heavy-duty vehicles | High | Train drivers driving project’s heavy-duty trucks on evasive and defensive driving to avoid accidents at all time | Low |
| Site Preparation | Deterioration of local air quality due to the release of fugitive dusts and gaseous pollutant from vegetation clearance, soil disturbance and heavy-duty vehicles | Medium | Implement Dust control and suppression measures, such as use of dampening and wetting | Low |
|  | Noise and vibration disturbances from operation of earth moving equipment | Medium | Use of noise barriers to screen receptors, e.g. with berms or bunds. Use of modern, well-maintained equipment Strict controls of timing of activities e.g. blasting. | Low |
|  | Loss, damage, erosion and disruption of soil from exposure of soil surfaces to rain and wind. | Low | Retention of topsoil for restoration (including tilling and re-vegetation) as soon as practicable. | Low |
|  | Waste generation from accumulation of cleared vegetal materials and spoils. | Medium | Ensure that all wastes are managed by authorized waste management contractor. | low |
|  | Construction Phase |  |  |  |
| Roofing of renovated and new building and installation of internal and external finishing materials as well a painting | Interaction between workforce and local communities may increase occurrence of communicable diseases, including HIV/AIDS and sexually transmitted diseases (STDs). | Medium | Training and awareness raising for workforce and their dependents on HIV/AIDS and other STDs, Provision of opportunities for workers to regularly return to their families. | Low |
|  | Accidents, injuries and illnesses among workers | High | Develop and Implement HSE Plan | Low |
|  | Increased noise level within the environment as a result of roofing works | Medium | Provide noise attenuator for workers and restrict such works to times when it will create lesser nuisance to people | Low |
|  | Generation of Hazardous waste like paint cans and other aerosols | High | Dispose all waste through licensed waste management contractor | Low |
|  | Generation of non-hazardous waste from other material packages | High | Same as above | Low |
|  | Operational Phase |  |  |  |
| Operations and Usage of intervention’ physical component | Generation of solid waste from the usage of renovated and new buildings | High | Preparation of Waste Management Plan. | Low |
|  | Generation of Hazardous waste streams like used batteries, used solar panels, fluorescent tubes and Spent oil | High | Use of authorized contractors for hazardous and any other wastes which the project cannot dispose of safely | Low |
|  | Intervention will increase utilization of facilities which will in turn increase medical waste | High | Ensure that medical waste is managed by authorized waste management contractors | Low |
|  | Use of generators Soil contamination (from accidental diesel/lubricant spills), Occupational health issues etc. all need to be assessed. | High | Deterioration of local air quality due to emission from generators Noise and vibration from generators, may disturb sensitive noise receptors (i.e. humans). Soil pollution from generator house | Low |
|  | Congestion if too many staff are recruited Potential water shortage | High | Risks of accidents, incidents and near misses from use of healthcare facilities, vehicles and equipment Disruption to normal operational life of the facilities, through the physical presence of too many staff. Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems, and result in conflicts over water use. | Low |
|  | Demobilization Phase |  |  |  |
| Occupational/ public safety and traffic impacts | The relocation of all construction facilities and remaining materials including concrete mixers, trucks, and water tanks to new sites or the contractor’s office could result in accidents and injury to workers. The removal and transport of such equipment and materials could also pose traffic risks and public safety concerns within the schools and along the routes. | High | Develop and Implement HSE Plan to cater for proper management of Occupational Health and Safety. | Low |

ES 7: ENVIRONMENTAL AND SOCIAL MANAGEMENT AND MONITORING PLAN (ESMMP)

The overarching objective of the ESMP is to ensure that all potential impacts of the project are contained and brought to an acceptable level to guarantee the economic, environmental, and social sustainability of the projects.

The ESMP has been developed to meet international and national standards on environmental and social (E&S) performance and covers the project implementation phases (i.e. Pre-construction, construction, and operation phases) of the project. Furthermore, it details the mitigation and enhancement measures that the Bauchi State government and their Contractors will be committed to implementing throughout the project life cycle as well as desired outcomes, performance indicators, monitoring, the timing for actions, and responsibilities.

The IBSDELIP PIU shall have principal responsibility for the implementation of all measures outlined in this ESMP but will delegate certain responsibilities to its contractors. Such delegation of responsibility shall be adequately documented as part of contractual agreements to guarantee absolute compliance and commitment on the part of the contractors to implement the ESMP. Consequently, the contractor shall prepare a Contractor Environmental Management Plan (C-ESMP) from this ESMP to guide implementation. The significant potential E&S impacts for which management actions are required have been identified in Chapter 5 of this report.

## ES 7.1 	Institutional Arrangements

Robust institutional arrangements are essential for the successful implementation of this ESMP. The capacities of these institutions also need to be improved for optimum project implementation. Some of the key stakeholders and their roles are as follows:

- Federal Ministry of Environment

  - Approve disclosure of ESMP in-country

  - Environmental monitoring to ensure country standards is complied with.

- IBSDLEIP Project Implementation Unit (PIU)

  - Ensuring approval & disclosure of Environmental and Social safeguards instruments to the public

  - Facilitate M&E implementation and monitoring functions.

  - Responsible for coordination to ensure that parties to implementation carry out their responsibilities as and when due

- Bauchi State Ministry of Environment

  - Responsible for overseeing environmental monitoring and compliance at the State level

  - Site assessment and monitoring of ESMP implementation.

- PIU Environmental & Social Safeguard Units

  - Collate environmental baseline data on relevant environmental characteristics for monitoring and auditing

  - Ensure that project activities are implemented in accordance with good practices and guidelines set out in the site-specific ESMP;

  - Identify and liaise with all stakeholders involved in environment-related issues in the project and be responsible for the overall monitoring of mitigation measures and the impacts of the project during implementation.

  - Coordinate and ensures the implementation of the social aspects of the ESMP

The detailed roles and responsibilities of institutions in implementing the ESMP are explained in the report.

## ES 7.2 Cost of Implementing the ESMMP

The cost of environmental and social management actions is estimated at Twenty Seven Million Three Hundred and Ninety Thousand Naira Only (27,390,000-00), which is equivalent to Fifty Nine Thousand Five Hundred and Forty-Three Dollars Forty Seven Cents (USD59,543.47).The cost of implementing the ESMP is presented in Table ES 5.

The cost of mitigation by the Contractor will be included in the contract as part of the implementation cost by the Contractor. The Bauchi PIU will coordinate the implementation of this ESMP in conjunction with the relevant State MDAs.

## ES 8.0 STAKEHOLDER CONSULTATION

Consultations and public participation enable the project to understand and document concerns about environmental and social impacts associated with the project. During the preparation of the ESMP, significant consultations and public participation were carried out. Stakeholder consultations and public participation was carried out:

(i) To provide an opportunity for people likely to be affected by the project to get clear, accurate, and comprehensive information about the proposed project and it’s anticipated environmental and social impacts;

(ii) To provide an opportunity for people to give their views and raise their concerns;

## ES 8.1 Process and the methodology of Stakeholder consultation

During the project preparation mission, several consultative meetings were held. Consultations were carried out with the technical officers from different ministries, civil society institutions, and community members of Mashema, Dagauda and Yelwan Duguri communities in Itas-Gadau, Dambam, and Alkaleri Local Government Areas respectively. The meetings were facilitated by the Environmental/Social Safeguard officer of the IBSDEIP SPIU. Specific meeting dates and content of meetings held are presented in Table ES 6.

Table ES 6. Record of Engagement carried out at the various model primary schools project sites

| Date of the meeting | Site | Content | Attendees |
| --- | --- | --- | --- |
| 13th September, 2022 | Mashema Model School Site | - Briefing on the objectives of the Bauchi State IBSDEIP Model School project particularly it Benefits, nature, size and resources required. - The need for conducting the ESMP as part of the requirements for execution of projects under the AfDB. - Obtaining feedback and opinions. | Community, youth and women leaders from the three communities See Appendix X for list of participants |
| 13th September, 2022 | Dagauda Model School Site |  |  |
| 14th September, 2022 | Yelwan Duguri Model School Site |  |  |

## ES 8.3 The outcome of the Stakeholder Engagement

All the project communities visited were happy with the construction/upgrade work which according to them will have a positive impact on educational status of the community. They applauded the project and promised to give their maximum support and cooperation.

The major issues rose by the community members and how they were addressed at the various project sites are presented in Table ES 7.

Table ES 7: Stakeholder Engagement

| Issues raised during consultations | How they were addressed |
| --- | --- |
| In all the communities visited, members were eager to see the commencement and completion of the project. | All arrangements have been put in place for the commencement of the project and it will start immediately. The project monitoring unit will ensure quality work and speedy completion of the project as scheduled. |
| The construction of fencing wall at Mashema is not good enough as domestic animals were seen crossing and entering into the school premises. | The attention of the contractor will be drawn to do the needful. |
| Involvement of member of the communities as menial workers during construction/rehabilitation stage of the project | Issues regarding labour hiring would be handled in conjunction with contractor & village heads. |
| The community hoped that with the expansion of the schools, their wards would be employed as teachers because they have unemployed university graduates | Regarding the employment of more teachers. Appropriate recommendation would be made in the ESMP document |

## ES 9.0: GRIEVANCE REDRESS MECHANISM

The Grievance Redress Mechanism (GRM) outlines a process for documenting and handling project grievances that may be raised by affected individuals or community members regarding specific project activities, environmental and social performance, the engagement process, and/or unanticipated social impacts because of project activities.

## ES 9.1 Designated staff coordinating Grievance Redress

The PIU Environmental and Social Safeguard specialist will be designated as the person in charge of Grievance Redress and has the following responsibilities in respect of the GRM;

- Coordinate formation of Grievance Redress Committees (GRCs) before the commencement of construction to resolve issues.

- Act as the Focal Point at PIU on Grievance Redress issues and facilitate the grievance mechanisms.

- Create awareness of the Grievance Redress Mechanism (GRM) among all the stakeholders through public awareness campaigns.

- Provide resources to cover the operational costs of the GRM.

## ES 9.2 Mode of receipt and recording of Complaints

The complaints can be made in writing, verbally, over the phone, by fax, email, or any other media. As soon as the officer receives a complaint, he /she would issue an acknowledgment of the complaint, including the details of the person bringing the grievance.

## ES 9.3 Structure of Grievance Redress

The Bauchi State IBSDLEIP PIU shall receive and act upon complaints from stakeholders or Project Affected Persons (PAPs) in relation to any occurrences for which the Project is directly responsible (or believed to be responsible), and which are perceived by the aggrieved party to have involved corrupt, illegal, unjust, or unfair activities, omissions, or behaviour.

## ES 9.4 Grievance Redress Mechanism Process

The stakeholders are informed of various points of making complaints (if any) and the PIU collect the complaints from these points on a regular basis and record them. This is followed by coordinating with the concerned people to address the grievances.

## ES 1.0 Conclusion

This project with the associated activities outlined in this ESMP for the construction/upgrade of the model primary schools at Dagauda, Yelwan Duguri, and Mashema towns of Bauchi State will have highly beneficial impacts by improving critical service delivery infrastructure within this community and thereby scaling up living conditions, through which social cohesion can be improved.

The civil works associated with the construction/upgrade of the model primary schools are anticipated to lead to some limited adverse environmental and social impacts which will largely be localized in spatial extent, short term, and occurring within less sensitive environmental areas.

# CHAPTER ONE: INTRODUCTION

## 1.1 Introduction

The Bauchi State AfDB-Assisted IBSDLEI Programme (hereinafter referred to as ‘the Project Implementation Unit’ or the ‘PIU’), wishes to construct/upgrade three (3) Model Primary Schools at Yelwan Duguri, Dagauda and Mashema townships in Bauchi State. Considering the importance, the PIU attaches to the protection of the environment as well as the health and safety of the host communities, and in order to comply with the African Development Bank’s (AfDB) safeguards policies, national and Bauchi States environmental policies, it commissions the preparation of an Environmental and Social Management Plan (ESMP) with a view to ascertaining the potential and associated impacts of the project on the environment and people’s health and well-being.

An ESMP is a plan which describes the actions that will be taken to enhance positive impacts and to avoid, minimize, mitigate, compensate / offset negative impacts of a project or intervention. It describes the mitigation and management measures, clarifies responsibilities for implementation, provides an implementation plan with the necessary time schedule and costs and indicates how environmental and social monitoring measures are to be implemented.

## 1.2 Project Background

The Government of the Federal Republic of Nigeria (hereinafter called ‘the Borrower”) has received financing from the African Development Bank in the form of a “loan” toward the cost of the Inclusive Basic Service Delivery and Livelihood Empowerment Integrated Programme (IBSDLEI). The Bauchi State AfDB IBSDLEI PIU, an implementing agency of the Borrower, intends to apply a portion of the proceeds of this loan to eligible payments towards the preparation of an Environmental and Social Management Plan (ESMP).

The Inclusive Basic Service Delivery and Livelihood Empowerment Integration Program (IBSDLEIP) is part of Federal Government efforts toward Northeast States Emergency Transition, Recovery, and Peace- building, elaborated by the five-year programmatic “Buhari Plan” of 2016. The programme aligns with interventions by Development Partners (DPs) within the Recovery and Peace Building framework which seeks to support the implementation of the “Buhari Plan”. The overall budgetary requirement for the “Buhari Plan” is currently estimated at 2.13 trillion naira.

The Programme will contribute to 4.7 % of existing funding gaps in the development strategies priority needs which constitutes 71% of budget needs of the Buhari Plan to help address the inherent socio-economic drivers of the insurgency. The Program emphasizes selectivity, integration and prioritizes support to;

- infrastructure with emphasis on restoration, reconstruction and improvements for Water and sanitation; Primary Health Clinics, basic schools and markets;

- food security and nutrition;

- Water, sanitation and hygiene, primary health care and basic education services and systems strengthening;

- Entrepreneurship, job creation and livelihoods for youth, women and the vulnerable; and

- Social cohesion and psychosocial support as cross cutting.

The Program will help address the needs of an estimated 14 million affected people, including over 2.3 million Internally Displaced Persons, of whom nearly 80 % are women, children, and youth, and with special attention to rural households in Local Government Areas affected by the insurgency. The implementation of the Program will span a five-year period, beginning January 2017 to December 2021, and will be financed through an AfDB loan of UA 107.65 million, ADF loan of UA 71.77 million, and RWSSI-TF Grant of UA 3.98 million, with an estimated counterpart funding of up to 5.8% (of the Bank’s total financing) by the Federal Government of Nigeria (FGN) and State Governments in the context of reduced revenues spawned by the oil crisis (IBSDLEIP, PAD, 2020)

### 1.2.1 Programme Description

The Program is anchored on three major reinforcing components. The respective sub-components are elaborated on below.

Component 1: Service Delivery

This component will promote restoration, access, and utilization of basic social services in health, education, water, and sanitation (with targeted interventions in infrastructure provision, skills acquisition, and upgrading, rural water, and sanitation reform) and community-based nutrition support programmes. The key principle to be applied in the reconstruction and rebuilding of the Northeast is “building back better” i.e., ensuring better construction standards and contract terms to ensure durable infrastructure, systems development, and human resources for sustainable services. The main outputs to be delivered include (i) improved Gender-sensitive infrastructure/facilities for primary health care, basic education, and Water and sanitation; (ii) Enhanced skills acquisition/upgrading for service workers in water, sanitation, health, and education systems; (iii) strengthened awareness on hygiene, sanitation water conservation, and environment and Open Defecation Free Environment; (iv) Enhanced Monitoring and Evaluation and demand side accountability in service delivery in health, education and water, and sanitation through social accountability measures and (v) enhanced nutrition for infants and pregnant women.

Component II: Economic Recovery

This component will promote job creation and entrepreneurship with a focus on youth and women. It will also support the reconstruction of Major markets to recover commerce. Additionally, tailored training to upgrade the skills of artisans and equip them to take better, the economic opportunities arising from public work programmes resulting from reconstruction and rehabilitation of infrastructure in component 1 and other economic integration activities will be undertaken. The component will also support vulnerable households (IDPs) to enhance their economic reintegration and the building of livelihoods with a focus on agribusiness. To ensure better targeting of interventions for the vulnerable, the Bank will support the development of a state-unified social registry which in turn contributes to the development of the national registry compilation for the safety nets programme, co-financed by the World Bank. Given the socio-cultural context, promoting women’s entrepreneurship and job for females, accessing skills and training programs, and facilitating women’s access to the market, require specific gender-focused interventions.  Expected results for this component will therefore include (i) youth/women MSMEs and Entrepreneurship promoted; (iii) unskilled youth (50% female) trained in viable economic ventures and life skills; (iii) Poor household food security and agricultural livelihood opportunities enhanced Intervention Organization Funding framework.

Component III: Institutional Strengthening and Project Management

Institutional strengthening interventions include technical assistance to the Women Empowerment  Fund to facilitate loan disbursement to women SMMEs, enhanced capacities of the ministry of Labour and Employment for enforcement and monitoring of the Private Agency Employment Regulation; enhanced capacity of the Universal Basic Education Commission (UBEC) to implement the National Education Management Information System to support and National Primary Health Care evidenced-based policy and strategy development in the sub-sectors of basic education and Primary Health. In addition, the office of the Vice President’s Social Investment Unit will be supported to put in place an MIS to facilitate coordination and monitoring of cluster programmes. The programme will also facilitate the development of programme implementation manuals and monitoring and evaluation framework as well as an impact evaluation. The Project Coordination and Implementation Units capacities will also be built to enhance implementation efficiency.

## 1.3 Objectives of the ESMP

The objective of the Environmental and Social Management Plan (ESMP) for the proposed Upgrade/Construction of three (3) Model Primary School at Yelwan Duguri, Dagauda and Mashema is to ensure compliance with applicable national environmental and social legal requirements and the AfDB’s safeguards policies and procedures which requires the identification of likely impacts of the intervention and their enhancement (positive impacts) or mitigation (negative impacts).

The specific objectives include the followings:

- Identify the beneficial and negative impacts that could emanate from the proposed project and associated activities

- Identify measures to prevent and mitigate undue harm to people and their environment because of the project,

- Recommend mitigation/enhancement measures, monitoring, consultations, and institutional strengthening measures to be undertaken during project implementation and operations.

- Ensure the robustness of mitigating/enhancing, monitoring, consultative and institutional measures required to prevent, minimize, mitigate, or compensate for adverse environmental and social impacts, or to enhance the project’s beneficial impacts.

- Address capacity building requirements to strengthen the needed safeguards capacities as necessary.

- Ensure that the environmental and social safeguard measures meet the AfDB’s safeguards requirements and the national legislation.

- Ensure project sustainability in relation to environmental, social, and climate change aspects,

## 1.4 Scope of ESMP and Applicability

### 1.4.1	Scope

This ESMP aimed to ensure the safe construction and sustainable operations of three (3) Model Primary Schools at Yelwan Duguri, Mashema and Dagauda Towns of Bauchi State. It emphasizes the incorporation of environmental, occupational health & safety, and a social aspect associated, with the construction and operational activities of the Model Primary Schools and is in line with the applicable national laws, Bauchi State legislations, international guidelines, and best practices adopted internationally. The ESMP also complies with the applicable national employment & social, Health & Safety, and Environmental Standards, Codes, and Regulations.

### 1.4.2	Applicability

The ESMP covers all activities during the construction, operational, and decommissioning phases and shall be implemented to ensure that all Environmental and Social impacts are identified and appropriately mitigated.

## 1.5 Study Methodology

The methodology comprised a desk review of documentation (such as the project appraisal document (PAD), and engineering designs to obtain secondary data on the project area. Field visits, stakeholder engagement, and consultations were also carried out during rainy season from 13th to 14th September 2022 in the three communities. A Socioeconomic survey was also carried out to collect the baseline information on the project areas. This approach adopted involved a combination of the following:

- Questionnaire administration for data collection on existing livelihood opportunities, income, gender characteristics, age profile, health, transport access

- Focus group discussion (FGD) was conducted to obtain information about the analysis of existing formal and informal grievance redress mechanisms, the fears, and expectations of the people

- Key informant interviews to elicit in-depth information about community structure, norms, and values, among others.

This methodology has enabled the identification of environmental and social sensitivities associated with the project and have facilitated the preparation of mitigation measures aimed at eliminating or minimizing adverse environmental and social impacts of specific actions, projects, or programs while also enhancing positive effects.

## 1.6 Administrative, Policy, Legal, and Regulatory Frameworks

### 1.6.1	Nigerian Administrative Framework

This section presents the relevant national, state and Local Government institutions with the core mandate for environmental protection and the health sector governance in Nigeria. The section discusses their roles and responsibilities as applicable to the implementation of the proposed projects.

Federal Ministry of Environment

The Federal Ministry of Environment (FMEnv) which was formerly known as the Federal Environmental Protection Agency (FEPA) was established in 1999 through Decree No. 58 of 1988 as amended by Decree No. 59 of 1992. The Ministry is the statutory government institution mandated to coordinate environmental protection and natural resources conservation for sustainable development in Nigeria. In addition, the Ministry is also saddled with the following responsibilities:

- Advising the Federal Government on national environmental policies and priorities, conservation of natural resources, sustainable development as well as scientific and technological activities affecting the environment and natural resources; and

- Prescribing standards and formulating regulations on water quality, effluent limitations, air quality, atmospheric protection, ozone protection, noise control as well as the removal and control of hazardous substances.

As established in the EIA Act Cap12 LFN, 2004, all public and private projects likely to negatively affect the environment must be go through the EIA process administered by the FMEnv including oil and gas production and mining activities. The EIA Division of the Environmental Assessment (EA) Department at the FMEnv is the main administrative unit responsible for overseeing the EIA process, preparing documents, and developing the procedures necessary for decision making on project certification by the Minister of Environment.

National Environmental Standards and Regulations Enforcement Agency

The National Environmental Standards and Regulations Enforcement Agency (NESREA) was established by the NESREA Act of 30th July 2007 as an Agency of the FMEnv. NESREA is charged with the responsibility of enforcing all environmental laws, guidelines, policies, standards, and regulations in Nigeria. It also has the responsibility to enforce compliance with provisions of international agreements, protocols, conventions, and treaties on the environment to which Nigeria is a party.

Bauchi State Ministry of Environment

The Bauchi State Ministry of Environment (BASMEnv) has the responsibilities of protecting the environment within the state. The ministry’s functions include:

- Liaise with Federal Ministry of Environment in order to achieve the National Policy on the Environment.

- Promote environmental education in the State

- Monitor compliance with environmental laws and standards in the state

- Responsible for general environmental matters in the state including the negative effects of soil degradation due to flood and erosion, mineral and oil exploitation and exploration, deforestation, physical planning including amusement parks, gardens and beautification programmes, sewerage matters, water quality and pollution control.

Monitor the implementation of the environmental impact assessment, environmental assessment, environmental audit, environmental evaluation report guidelines and procedures on all development policies and companies within the state.

Local Government Areas (LGA)

The Model Primary Schools are within the jurisdiction of three (3) Local Government Areas. These are: Dambam, Itas/Gadau and Alkaleri Local Government Areas. These LGAs have relevant departments overseeing health, education and Water, Sanitation and Hygiene (WASH). Environmental matters at the local government level are essentially guided by relevant state laws.

### 1.6.2 Policy Framework

The relevant legal, Institutional, and regulatory framework upon which this ESMP is based are outline in Table 1:

Table 1: Policies, Legal and Regulatory Frameworks

| S/N | Policy Instrument | Year | Provisions |
| --- | --- | --- | --- |
| 1 | National Policy on the Environment | 1991, revised 2016 | Describes the conceptual framework and strategies for achieving the overall goal of sustainable development in Nigeria. |
| 2 | National Climate Change Policy | 2021 - 2030 | Describes the strategies for achieving its goal of meaningfully contributing of reducing greenhouse gas (GHG) emissions and reduce the socio-economic impacts of adverse effects of climatic change |
| 3 | National Climate Change Policy and Respond Strategy | 2013 | The National Policy on Climate Change is a strategic policy response to climate change that aims to foster low-carbon, high growth economic development path and build a climate-resilient society |
| 4 | National Forest Policy | 2006 Revised 2020 | It seeks to improve sustainable management of the resource and increase total forest cover. |
| Legal/Regulatory Instrument |  |  |  |
| 1 | Climate Change Act. | 2021 | The Act provides a framework for mainstreaming of Climate Change actions, provide for a system of carbon budgeting and the establishment of the National Council on Climate Change. |
| 2 | Nigerian Urban and Regional Planning Act CAP N.138, LFN 2004 | 2004 | This Act provides guidelines and regulations for land use planning, development control, and the implementation of physical development plans. |
| 3 | National Guidelines on Environmental Management Systems | 1999 | To promote and implement EMS by 2030, increasing the number of organizations implementing EMS and attaining related certifications, and improving environmental stewardship. |
| 4 | Renewable Energy Act | 2006 | Aim to collaborate and attract resources to achieve its renewable energy goals aligned with the United Nations Framework on Climate Change |
| 5 | Standard Organization of Nigeria Act | 2015 | The Act makes provision for the procedure for establishment of Industrial Standards. |
| 6 | National Environmental (Noise Standards and Control) Regulations. | 2009 | The Regulations prescribe maximum permissible noise levels from a facility and other permissible noise levels and require measures for the mitigation and reduction of noise to be introduced |
| 7 | Employee's Compensation Act | 2011 | Aims to provide a fair and guaranteed compensation system for employees or their dependents in cases of death, injury, disease, or disability arising from employment |
| 8 | Workmen’ Compensation Act | 1987 | An Act to make provisions for the payment of compensation to workmen for injuries suffered in the course of their employment. |
| 9. | Environmental Impact Assessment (EIA) Act No. 86 now LFN EIA Act Cap LFN 2004 | 2004 | Provide guidelines for activities of developmental projects for which EIA is mandatory in Nigeria. The act also stipulates the minimum content of an EIA as well as a schedule of projects, which require mandatory EIAs. |
| 10. | Environmental Impact Assessment (EIA) Procedures and Charges Regulations | 2021 | EIA mandatory for all major development projects, individuals and organizations seeking to carry out EIA studies should go through certain procedures to ensure that the project is implemented with maximum consideration for the environment |
| 11 | Water Use and Licence Regulations | 2016 | The license sets out the conditions for water use in the country |
| 12 | Land Use Act CAP 15 LFN | 2004 | The act vests all land comprised in the territory of each state in the Federation to the Governor of the state and requires that such land shall be held in trust and administered for the use and common benefit of all Nigerians in accordance with the provisions of the act. |
| 13 | Forestry Act | 1994 | Provides for the preservation of forests and the setting up of forest reserves. |
| 14 | Endangered Species Act (Cap 108) | 2016 | Provides for the conservation and management of Nigeria’s wildlife and the protection of some of her endangered species in danger of extinction because of over-exploitation |
| 15 | FEPA/FMEnv EIA Procedural Guidelines | 1995 | The Procedural Guidelines indicate the steps to be followed in the EIA process from project conception to commissioning to ensure that the project is implemented with maximum consideration for the environment. |
| 16 | National Guideline and Standard for Environmental Pollution Control | 1991 | Provide guidelines for the management of pollution control measures |
| 17 | The Nigerian Urban and Regional Planning Act CAP N.138, LFN 2004. | 2004 | Planned development of urban areas (to include and manage waste sites). |
| 18 | Factories Act and Labour Law (Cap F1 LFN 2004) | 2004 | It is obligatory for the employer, under employment contract to provide safe system and place of work and to take measures to ensure the safety of the worker. |
| 20 | Bauchi State Environmental Protection (BASEPA) Law | 1994 | Making and enforcing environmental and health policies and laws |
| 21 | The National Environmental Standards and Regulations Enforcement Agency Act 2007 (NESREA Act) | 2007 | The act makes provision for solid waste management and its administration and prescribes sanctions for offenses or acts, which run contrary to proper and adequate waste disposal procedures and practices |
| 22 | Dambam, Itas/Gadau and Alkaleri Local Government Areas Bylaws | 2001 | To ensure provision of safe and adequate water supply to the local communities through stakeholder consultation and participation. |

### 1.6.3 Specific Policies and Institutions in the Educational Sector

In the education sector, the institutional responsibilities are shared by three tiers of Government – Federal, State, and Local.

- Federal Ministry of Education (FME): At the Federal level, FME has a policy formulation and coordination mandate in the education sector. The National Council on Education coordinates policy-making across the different tiers of government, gathering more than 1200 stakeholders including the Federal Minister of Education and all state-level Commissioners of Education. It plays an important role in ensuring the effectiveness of the basic education policy across the country as a collegial decision-making body. The Council decides on the national curriculum and has been instrumental in the institutionalization of SBMCs across the states. UBEC is the executive agency of the Federal government responsible for basic education policy implementation. The National Commission of Nomadic Education (NCNE) is responsible for addressing the education of children of migrant farmers and nomadic people. The National Commission for Mass Literacy, Adult and Non-Formal Education (NCME) is the agency that works for national literacy agendas.

- Bauchi State Ministries of Education (BASME): At the State level, the BASME has primary responsibility for the coordination and implementation of educational affairs in the state in conjunction with other agencies and institutions. The BASME has the mandate for monitoring and evaluation, quality assessment and control, coordination, and providing information on a range of procedural and project management issues. The operational responsibility for basic education rests with the Bauchi State Universal Basic Education Board (BASUBEB).

- Local Government Education Authorities (LGEA): While the institutional framework is not clearly delineated at the local level, LGEAs – the local arm of SUBEBs -- are in charge of basic education, and Local Governments are involved in the management and financing of primary education. At the local government level, the governance framework of basic education rests in principle on participatory school-level management and school supervision by the State Government through LGEAs.

- At the school level, some public schools are managed by school principals and head teachers, assisted by functional SBMCs that support the schools in developing education improvement plans, and managing activities under such plans.

Child Rights Act (2003)

The Child Rights Act codifies the rights of children in Nigeria. The Act was designed to incorporate into its laws all the rights guaranteed in the United Nations Convention on the Rights of the Child adopted in 1989. It defines a child as a person below the age of 18 years, consolidates all laws relating to children into a single law and specifies the duties and obligations of government, parents and other authorities, organizations and bodies. The Act mandates parents, guardians, institutions and authorities to provide the necessary guidance, education and training to enable the children to live up to these responsibilities.

National Policy on Education (2004)

The education system in Nigeria is based on the National Policy on Education (NPE). The policy document addresses the issue of imbalance in the provision of education in different parts of the country with regard to access, quality of resources, and girls’ education. It seeks to inculcate national consciousness, unity, training, and appropriate skills acquisition as well as mental and physical competence for the survival of the individual and Nigerian society.

Universal Basic Education Act (2004)

The Universal Basic Education Act provides the legal framework for the implementation of the UBE Program, which makes basic education not only free but also compulsory. Subsequently, the UBE Commission (UBEC) was established as a way of ensuring the proper implementation of the UBE Program. The commission is responsible for the coordination of the activities of the program.

National Policy on HIV and AIDS for the Education Sector in Nigeria (2005)

The Policy acknowledges that HIV&AIDS is a critical national issue that must be addressed as a matter of priority, if Nigeria is to achieve Education for All and MDGs. The Policy provides the basis to address issues and complications from the epidemic as well as strategies to respond to them. For orphans and vulnerable children, the Policy requires the education sector to: (i) ensure that the HIV status of a child or parents is not used as a criterion for admission or exclusion from school activities; (ii) enforce the principle of non-discrimination and non-stigmatization of such children; (iii) sensitize all staff and learners to the special physical and psychosocial needs of such children and provide medical, psychosocial support and counseling services for them; (iv) ensure that such children have free access to education and advocate for the removal of all barriers that prevent them from obtaining quality education; and (v) ensure that such children have access to bursaries, loans and scholarships for higher education.

National Gender Policy (2006)

The Government of Nigeria adopted the National Gender Policy in 2006 as a substitution of the Women's Policy adopted in 2000. The goal of the National Gender Policy: eliminates cultural/ religions gender-based biases and harmful cultural and religious practices, eliminates all forms of gender-based violence; gives women education priority; ensures equal access to women, boys and girls to both formal and informal education; empowers women and ensures that women have access to critical resources and invest in their human capital as a means of reducing extreme poverty in families among others.

National School Health Policy (2006)

The National School Health Policy is aimed at promoting the health of learners to achieve the goals of Education for All, outlining roles of relevant line ministries like Education, Health, Environment, Water Resources, Information and other stakeholders. The Policy and its implementation guidelines promote School Health Programme that comprises of all projects and activities in the school environment for the promotion of the health and development of the school community. It includes (i) Healthful School Environment; (ii) School Feeding Services; (iii) Skill-Based Health Education; (iv) School Health Services; and (v) promotion of School, Home and Community Relationship.

National Policy on Inclusive Education in Nigeria (2016)

The policy document is intended to address the challenges associated with the inclusion of Nigerian children with disabilities and unmet learning needs into the school system. Under the Vision “A society with an inclusive education system with unhindered access to quality education and active participation of all leaners in the same safe school environment,” the policy sets out policy framework, monitoring and evaluation mechanism, and the implementation guideline.

Ministerial Strategic Plan (MSP) (2016-2019)

The FMOE drafted the Ministerial Strategic Plan 2016-2019 (MSP), which was adopted by the National Council on Education on September 29, 2016. The MSP affirms that the security and stability of the country hinge to a large extent on its ability to provide functional education to its citizens, and that no nation can achieve economic prosperity without a sound and functional education system.

## 1.6.4 International Conventions and Treaties

Nigeria is a party to a number of international Treaties and Conventions. Some of which are listed in Table 2.

Table 2: International Treaties and Conventions on Environment to which Nigeria is a Party

| S/N | Treaties and Conventions | Year | Agreement |
| --- | --- | --- | --- |
| 1. | The United Nations Environmental Guidance Principles | 1972 | Provide guidelines for protecting the integrity of the global environment and the development system |
| 2 | Convention on International Trade in Endangered Species of Wild Fauna and Flora | 1973 | Restricts the trade of fauna and flora species termed as endangered Species |
| 3. | Convention on Conservation of Migratory species of Wild animals (Bonn Convention) | 1979 | Stipulates actions for the conservation and management of migratory species including habitat conservation |
| 4. | Montreal Protocol on Substances that deplete the Ozone Layer | 1987 | An international treaty to eliminate Ozone depleting chemical production and consumption. |
| 5. | Vienna Convention for the Protection of the Ozone Layer | 1985 | Places general obligation on countries to make appropriate measures to protect human health and the environment against adverse effects resulting from human activities, which tend to modify the ozone layer. |
| 6. | United Nations Convention on Biological Diversity | 1992 | Places general obligations on countries to observe sustainable use and equitably share the plants and animals of the earth |
| 7. | United Nations Framework Convention on Climate Change | 1994 | It calls on developed countries and economies to limit her emissions of the greenhouse gases which cause global warming |

## 1.7 African Development Banks Environmental and Social Safeguards Policies

To ensure environmental sustainability by protecting the people and environment from potential adverse impacts of projects, the African Development Bank Group developed an Integrated Safeguards System (ISS) in December 2013. Through the ISS, the Bank also helps borrowers/clients to strengthen their safeguards systems and develop their capacity to manage environmental and social risks. The Bank’s Integrated Safeguards Policy Statement sets out the Bank’s own commitments to and responsibilities for delivering the ISS to

- ensure the systematic assessment of E&S impacts and risks;

- apply the OSs to the entire portfolio of Bank operations;

- support clients and countries with technical guidance and practical support in meeting the requirements;

- implement an adaptive and proportionate approach to E&S management measures to be agreed with clients as a condition of project financing;

- ensure that clients engage in meaningful consultations with affected groups;

- respect and promote the protection of vulnerable groups, in a manner appropriate to the African context.

The ISS consists of four parts: (i) an overall Policy Statement; (ii) five Operational Safeguards (OSs); (iii) technical guidance in the form of Environmental and Social Assessment Procedures (ESAP); and (iv) a set of Integrated E&S Impact Assessment (IESIA) guidance notes.

The AfDB’s environmental and social safeguards policies require projects to be subjected to environmental and social assessment to safeguard the communities, environment, people’s health, and safety.

The guiding principle of environmental and social assessment procedures is to ensure that the Bank’s projects, programs, and plans have been designed to make them environmentally and socially sustainable, involving stakeholder participation and timely public disclosure. These procedures were developed to ensure Bank financed projects do not cause undue harm to the environment and well-being of project beneficiaries and ensure environmental sustainability.

The main purpose of the Environmental and Social Assessment Procedures (ESAP) is to improve decision-making and project results to ensure that Bank-financed projects, plans, and programs are environmentally and socially sustainable as well as in line with Bank’s policies and guidelines.

The ESAP also formalises the use of Environmental and Social Impact Assessment (ESIA), Environmental and Social Management Plan (ESMP) and Environmental and Social Audits as instruments to enhance project benefits and (in order of priority) to prevent, minimise, mitigate, or compensate for adverse impacts. The ESAP describe the various steps that shall be followed to mainstream crosscutting issues along the project cycle, from country programming to post-evaluation. The first step consists in developing and updating baseline data on environmental and social components, policies, programs, and capacities to better integrate environmental and social dimensions into lending priorities during country programming.

AfDB Operational Safeguards:

The AfDB have five operational safeguards that are used to ensure adequate protection of the environment and people from negative impacts of projects. These are a set of five safeguard requirements that Bank clients are expected to meet when addressing social and environmental impacts and risks. Bank staff use due diligence, review, and supervision to ensure that, clients comply with these requirements during project preparation and implementation. Over time the Bank may adopt additional safeguard requirements or update existing requirements to enhance effectiveness, respond to changing needs, and reflect evolving best practices. The objectives of the five OSs include:

- To integrate considerations of E&S impacts into Bank operations to promote sustainable development in Africa;

- Ensure projects are prevented from adversely affecting the environment and local communities or, where prevention is not possible, minimise, mitigate and/or compensate for adverse effects and maximize development benefits;

- Avoid the impact of climate change on the sustainability of investment projects and the contribution of projects to global greenhouse gas emissions;

- Delineate the roles and responsibilities of the Bank and its borrowers or clients in implementing projects, achieving sustainable outcomes, and promoting local participation; and

- Assist regional member countries and borrowers/clients in strengthening their own safeguards systems and their capacity to manage E&S risks.

Out of these five, four are triggered while one is not triggered in this project as outlined in Table 3 below:

Table 3: AfDB Operational Safeguards Policies Triggered

| AfDB Operational Safeguards Policies | Description | Triggered (Yes/No) |
| --- | --- | --- |
| OS 1: Environmental and Social Assessment | This overarching safeguard governs the process of determining a project’s environmental and social category and the resulting environmental and social assessment requirements | This OS is triggered because the construction and upgrade activities will have environmental interactions with potential negative impacts to the environment and humankind |
| OS 2: Involuntary Resettlement: Land Acquisition, Population displacement and compensation | This OS consolidates the policy commitment and requirements set out in the Bank’s policy on involuntary resettlement and incorporates a few refinements designed to improve the operational effectiveness of those requirements | This OS is not triggered. All activities are within existing footprint. |
| OS 3: Biodiversity and Ecosystem Services | This OS aim to conserve biological diversity and promote the sustainable use of natural resources. | This OS is triggered. Triggered due to land clearing operations and potential disturbance of vegetation |
| OS 4: Pollution Prevention and Control, Greenhouse Gases, Hazardous Materials and Resource Efficiency | This safeguard covers the range of key impacts of pollution, waste and hazardous materials for which there are agreed international conventions as well as comprehensive industry-specific and regional standards, including greenhouse gas accounting that other multilateral development banks follow. | This OS is triggered Triggered because construction and medical wastes will be generated during construction and operational phases respectively |
| OS 5: Labour Conditions, Health and Safety | This safeguard establishes the Bank’s requirements for its borrowers or clients concerning workers’ conditions, rights and protection from abuse or exploitation. It also ensures greater harmonization with most other multilateral development bans | This OS is triggered. Triggered because local and migrant workers as well as skilled and unskilled workers will be engaged in the project. There is therefore potential for risks to health and safety of workers during project implementation |

## 1.8 Structure of the ESMP

The structure of this ESMP report is presented below.

Chapter1. Introduction: Provides a background to the proposed Project, its key stakeholders and the ESMP. The Administrative, Policy and Regulatory Frameworks within which the ESMP was undertaken were also covered in the chapter.

Chapter2. Project Justifications: It justifies the project.

Chapter3. Project Description: The chapter provides a description of the Project

Chapter4. Biophysical and Socio-economic baseline: The chapter defines the areas of direct and indirect influence of the Project. It describes the biophysical and socio-economic baseline of the Project’s areas of influence.

Chapter5. Impact Assessment: The chapter presents the approach and methodology for the ESMP process. It identifies and assesses potential Project impacts (biophysical and socioeconomic impacts).

Chapter 6: Mitigation Measures: This chapter defines relevant mitigation measures to avoid, reduce, compensate or enhance Project impacts (as applicable).

Chapter7. Environmental and Social Management Plan (ESMP): It presents the Project ESMP, organizing all mitigation, management and monitoring requirements and management programs.

Chapter 8: Stakeholder Consultation

Chapter 9: Grievance Redress Mechanism

References: Lists the references cited in the report

Appendices. This section provides support information referenced throughout the ESMP.

# CHAPTER TWO: PROJECT JUSTIFICATION

## 2.1	Introduction

This chapter discusses the rationale as well as the sustainability of the proposed Model Primary School project at Mashema, Dagauda and Yelwan Duguri under the Bauchi State ISBDLEP AfDB assisted project. The chapter also considers the various alternatives to the projects.

## 2.2	Project Justification

### 2.2.1	Need for the Project

Various international conventions and national laws at state and federal level agree that education is essential to the development of every nation and that basic education should be compulsory and free. The most popular of these acts is the Universal Basic Education Act 2004 which not only outlines the role of government and divides responsibility between the three levels, but also emphasizes the role of parents/guardians and the funding of this basic education. According to the law, basic education starts from pre-school to upper secondary school and the federal government has a responsibility to ensure consistency and support the state and local governments whose duty it is to provide this free education and to ensure that all parents and guardian uses the opportunity for their children/career to benefit from free education or risks being sanctioned under the provisions of the law. The law also established the Universal Basic Education Commission (UBEC) to oversee implementation at the federal level and the State Universal Basic Education Board (SUBEB) at the state level.

One important gap that exists in the attainment of free education as outlined in the UBE Act is the inability of the school system to absorb all the school-age children in the country. A report by UNICEF (2022) revealed that even though primary education is officially free and compulsory, about 10.5 million of the country’s children aged 5-14 years are not in school. Only 61 percent of 6–11-year-old regularly attend primary school and only 35.6 percent of children aged 36-59 months receive early childhood education.

Educational infrastructure is an important factor in the quality of learning and the number of graduates, but most public schools lack basic infrastructure such as a laboratory, library, electricity, and a quality learning environment. While the existing infrastructure in some public schools is in a deplorable state, others are below acceptable standards and, in some cases, non-existent. Some of these schools lack functioning public sanitation facilities, forcing the student to defecate outdoors. The inability of students to pass their mandatory exam is attributed to the lack of infrastructure. For example, classrooms in most primary schools are typically overcrowded, with up to seventy or more students receiving instruction in classrooms designed for only thirty or forty students. The education sector needs a quantum overhaul. We need improvements starting in elementary school, where we see many children who do not go to school.

This intervention will go a long way in creating an enabling environment for children to be in school thereby reducing the number of out of school children through increase enrolment. The project would also complement the government effort in meeting sustainable Development Goal 4 - Ensuring inclusive and equitable quality education and promote life-long learning opportunity for all.

### 2.2.2	Benefits of the Project

Primary school is globally recognized as the foundation of all level education. It provides the mini-structural framework on which the quality of other levels of education is anchored. The following are the major benefits of the Model Primary Schools project

- Better learning environment and Improvement in students’ performance

- Provision of good school environment reduce absenteeism among teachers and students

- Increase in enrolment and reduction in the number of drop-outs and out of school children

- Complementing the efforts of achieving Sustainable Development Goal 4.

## 2.3	Project Sustainability

### 2.3.1	Technical Sustainability

The Project Implementation Unit (PIU) will ensure that competent contractors with proven track records in terms of the work quality and timely project delivery are engaged for the construction work. The contractor should ensure all the structures are built to international standards using high-quality materials, where possible, raw materials for the construction work will be sourced locally. The involvement of EIA consultants further complements the technical expertise of contractors both at the construction and operation stages of the project. The best available technology not exceeding reasonable cost will be used during project implementation

### 2.3.2	Socio-economic Sustainability

The following measures should be considered to guarantee the social sustainability of the project:

- The project’s social sustainability is guaranteed because of deep engagement and consultation with local stakeholders at all stages of the project’s planning, construction and operations.

- Prompt payment of adequate compensation package to displaced project affected persons and communities (PAPCs)

- Creation of employment opportunities to local people and provision of social infrastructure and amenities

- Creation of opportunities for trading of locally produced material.

- The employment opportunity created would reduce joblessness, increase the economic status of the community and reduce youth restiveness.

### 2.3.3	Environmental Sustainability

To ensure environmental sustainability, the following measures would be considered

- Implementation of the Environmental Management Plan

- Proper monitoring of the environmental management plan developed in the EIA study at construction and operational stages of the project

- Consultation and participation of the project affected persons and communities

- Standard site layout to ensure proper alignment of the facilities to minimise the risks of water erosion, flooding etc.

- Use of standard and environment-friendly construction materials including those that can be reused/recycled and having longer life expectancy to minimise the volume of waste going to landfill

- Enforcement of safety measures at the site during construction and operational stages of the project

- Adoption of water and energy conservation programme at operational stage

- Adoption of effective waste management programme at the operational phase of the project.

- Enforcement of safety measures at the site during construction and operational stages of the project

# CHAPTER THREE: PROJECT DESCRIPTION

## 3.1 Introduction

This chapter describes the proposed construction and upgrade of the three (3) Primary Schools in Yelwan Duguri, Mashema, and Dagauda in Alkaleri, Itas/Gadau and Dambam LGAs respective all in Bauchi State. The details also cover the nature of the key project activities, facilities, equipment, and operations. The aim is to enable the scope and extent of the project to be understood, and for all potential sources of impacts because of the construction/upgrade to be identified. Proper project description will also facilitate the selection of the best mitigation measure as required by the relevant environmental legislation in Nigeria.

The proposed model primary schools are expected to form the bedrock of development where the children learn foundational skills that prepare them for life, work and active citizenship. Quality education empowers children and young people, safeguards their health and well-being, and breaks cycles of poverty. It also empowers countries, ushering in economic prosperity and social cohesion.

## 3.2 Project Location

The projects will be in Yelwan Duguri, Mashema and Dagauda towns located at Alkaleri, Itas/Gadau and Dambam Local Governments of Bauchi State as shown in Figure 1 and Table 4.

### 3.2.1 Bauchi State

Bauchi State is a state in the North-East geopolitical zone of Nigeria, bordered by Kano and Jigawa to the north, Taraba and Plateau to the south, Gombe and Yobe to the east, and Kaduna to the west. It takes its name from the historic town of Bauchi, which also serves as its capital city. The state was established in 1976 from the former North-Eastern State. It originally included the area that is now Gombe State, which became a distinct state in 1996.

Bauchi is the fifth largest in area and seventh most populous with an estimated population of over 6,530,000 as of 2016. Geographically, the state is divided between the West Sudanian savanna in the south and the drier, semi-desert Sahelian savanna in the north with a small part of the montane Jos Plateau in the southwest. The state is home to the Yankari Game Reserve, a large wildlife park in Alkaleri Local Government Area of the state. The Reserve contains large populations of waterbuck, African buffalo, patas monkey, hippopotamus, roan antelope, and western hartebeest along with some of Nigeria's last remaining West African lion, African leopard, and African bush elephant populations.

What is now Bauchi State has been inhabited for years by various ethnic groups, including Gerawa, Hausa, Fulani, Kanuri, and Sayawa among others, Islam and Christianity are the predominant religions in the state although there is small percentage of followers of traditional religions.

Majority of the population rely on crop and livestock production as a means of livelihood. Key crops grown include maize, groundnuts, millet, tomatoes, cowpeas, guinea corn among others.

Bauchi State occupies a total land area of 49,119 km2 (18,965 sq mi) representing about 5.3% of Nigeria's total land mass and is located between latitudes 9° 3' and 12° 3' north and longitudes 8° 50' and 11° east.

The state spans two distinctive vegetation zones, namely, the Sudan savannah and the Sahel savannah. The Sudan savannah type of vegetation covers the southern part of the state. Here, the vegetation gets richer towards the south, especially along water sources or rivers, but generally the vegetation is less uniform and grasses are shorter than what grows even farther south, that is, in the forest zone of the middle belt.

The Sahel type of savannah, also known as semi-desert vegetation, becomes manifest from the middle of the state towards the north. This type of vegetation comprises isolated stands of thorny shrubs. The southwestern part of the state is mountainous as a result of the continuation of the Jos Plateau, while the northern part is generally sandy.

The vegetation types as described above are conditioned by the climatic factors, which in turn determine the amount of rainfall received in the area. For instance, the rainfall in Bauchi state ranges between 1,300 millimetres per annum in the south and only 700 millimetres per annum in the extreme north. In addition to rainfall, Bauchi state is watered by a number of rivers. They include the Gongola and Jama'are rivers.

### 3.2.2 Dambam Local Government Area

Dambam Local Government is one of the Local Government Areas in Bauchi State located in the northern part of the State and shares borders with Darazo, Misau, Katagum and Gamawa local government areas. With an administrative headquarters at Dambam, the LGA has an area of 1,077 km2 and a population of 150,922 as at the 2006 census. Major towns in the LGA include Dagauda, Dambam, Jalam, and Yamai. Tel predominant tribe in the area is Kare-kare.

### 3.2.3 Itas/Gadau Local Government Area

Itas/Gadau is a Local Government Area of Bauchi State, Nigeria. Its headquarters are in the town of Itas. The town of Gadau is in the east of the area at 11°50′08″N 10°10′02″E. It has an area of 1,398 km2 and a population of 229,996 at the 2006 census. The predominant ethnic groups in the area includes the Hausa, Fulani and Kanuri. Mashema is one of the major towns in Itas/Gadau LGA.

### 3.2.4 Alkaleri Local Government Area

Alkaleri is a Local Government Area of Bauchi State, Nigeria. It’s headquarter is in the town of Alkaleri on the A345 highway in the north of the area at10°15′58″N 10°20′07″E. The northeasterly line of equal latitude and longitude passes through the LGA. It has an area of 5,918 km2 and a population of 329,424 at the 2006 census. The predominant ethnic groups in the area are the fulani, Kanuri, Dugurawa, Guruntawa and Labur "Jaku" people. The districts of the local government are Pali, Duguri, and Gwana. Major towns and villages of the local government like Fanti, Gar, Gokaru, Guma, Gwaram etc. including the local government headquarters, Alkaleri are located in the Pali district. Duguri district is the home to Yankari -West Africa's premier game reserve, and consists of towns and villages like Badara, Dagudi, Dan, Gajin Duguri, Mainamaji, Yashi, Yelwan Duguri, and the historic Duguri. Gwana is located in the southeastern part of the local government.

Figure 1   Map of Bauchi State showing the proposed sites for the 3 Model Primary Schools.

## 3.3 Description of the Construction Activities of 3 Model Primary Schools

The Construction activities of the Model primary schools at Yelwan Duguri, Dagauda, and Mashema will involve the construction of a perimeter fence around the clinic, the construction of the main building renovation of some existing structures, the provision of teaching aids and the construction of staff quarters with furnishings.

The scope of work will comprise the following activities:

- The Pre-Construction Phase

  - Mobilization of equipment and personnel to site: This activity involves deployment of labour force for work and mobilization of lorry trucks & equipment to the site.

  - Site clearing: Clearing of existing structures, vegetation and earth from the construction/upgrade sites in the three sites.

  - Setting out: Involves establishing the location points for the site boundaries, foundations and columns. The activity also involves establishing the correct extent, angle and levels.

- Construction Phase

- Excavation works:  This activity involves digging the soil to layout the plan to enable the commencement of ground works

- Ground works: This involves preparing the ground and below ground in order to lay out the building foundation

- Substructure: This is the below ground construction upon which the entire building will based on. This structure will include the damp proof course, formwork and foundation

- Superstructure: This refers to the construction of above ground features of the building. It includes floors, walls, beams, columns, finishes, windows, doors, the roof, floors etc.

## 3.4 Sourcing of water & other materials

Naturally occurring construction materials such as water, fine sand, and aggregates are available in the project area. Where applicable, approvals would be obtained for the extraction of raw materials. Materials that will be used are:

- Water: Water for the proposed primary healthcare center work can be sourced from existing boreholes or streams/rivers within the vicinity of the subproject area and this would be delivered by water truck to the site.

- Fine Sand: There are no rivers close to the project sites for the construction of the three model primary school sites. Therefore, fine sands need to be sourced from other places. In doing so, all the necessary measures to ensure material transport and handling are carried out according to Health, Safety, and Environment (HSE) standards in this ESMP will be in place.

- Energy:

Energy will be provided from petrol powered generators during the construction process. The locations of sub-projects are shown in Table 4.

Table 4:  Bauchi State AfDB-Assisted IBSDLEIP Construction of model Primary schools.

| S/N | Sub-project Location | L.G.A. | State | Coordinates |
| --- | --- | --- | --- | --- |
| 1 | Mashema | Itas-Gadau | Bauchi | N11o 47’ 07.2’’ E009o 56’ 28.7’’ |
| 2 | Dagauda | Dambam | Bauchi | N11o 42’ 02.7’’ E010o 51’ 45.3’’ |
| 3 | Yelwan Duguri | Alkaleri | Bauchi | N09o 57’ 44.8’’ E010o 10’ 55.4’’ |

## 3.5 Site Layout

The site layouts for the schools are shown in Figures 2, 3 and 4.

Figure 2: Proposed Site Plan, Model Primary Health Care Centre, Dagauda

Figure 3: Proposed Site Plan, Model Primary School, Yelwan Duguri

Figure 4:  Proposed Site Plan, Model Primary School, Mashema

## 3.6 Project Facilities

The 3 Model Primary Schools were designed according to the prescribed national standard and in conformity with the international based practices. The Construction/upgrade activities of 3 Model Primary Schools at Yelwan Duguri, Dagauda and Mashema involves;

- Provision of perimeter fencing using concrete walls

- Renovation of some existing structures,

- Demolition and alteration and Construction of class room blocks,

- Offices

- Stores libraries

- Laboratories

- School garden

- Recreational facilities

- Construction of staff quarters including furnishings.

## 3.7 Typical Model Primary Schools Activities at the Operational Stage

The activities in the model schools during the operational stage teaching and learning, practical demonstrations in the laboratories, gardening, arts and crafts instructions, debates, quizzes and different sporting activities.

## 3.8 Manpower

The project will require both skilled and unskilled manpower at the pre-construction, construction and operational phases as shown in Table 5:

Table 5: Estimate of manpower required at various stages of project

| S/N | Project Stage | No. of unskilled labour | No. of skilled labour |
| --- | --- | --- | --- |
| 1 | Pre-construction | 6 | 12 |
| 2 | Construction | 60 | 15 |
| 3 | Operations | 30 | 45 |
| 4 | Demobilization Phase | 5 | 15 |
|  | Total | 101 | 88 |

# CHAPTER FOUR: DESCRIPTION OF BASELINE ENVIRONMENT

## 4.1 Introduction

This chapter describes the baseline condition of the project sites’ physical, chemical, biological, and socio-economic characteristics.  It provides information on the features, quality, and sensitivity of the proposed project environment. The baseline data were generated using several methods, some of which are discussed below.

## 4.2 Data Acquisition Methods

A survey was conducted to collect socio-economic and cultural baseline information of the project area. To achieve the objectives of the study the approach adopted involved a combination of the following:

- Questionnaire administration for data collection on existing livelihood opportunities, income, gender characteristics, age profile, health, transport access.

- Focused group discussion (FGD) to gather information on the existing formal and informal grievance redress mechanisms, and to document people's fears and expectations.

Key informant interviews to elicit in-depth information about community structure, norms and values, participatory observation, and estimation.

## 4.3 Spatial Boundary for the Study

The project Area of Influence (AoI) is the area likely to be affected by the proposed construction/upgrade of the Model Primary Schools at Mashema, Dagauda and Yelwan Duguri communities. This area is defined based on the extent to which the proposed project activities may interact with the surrounding environment whilst taking into considerations the nature of the project and associated activities, nature of surrounding ecosystem and ecosystem resources and spatial distribution of the affected communities.

Consequently, the AoI was determined to include the project site and adjoining physical surroundings (in terms of air, water, and soil quality) up to 2km radius drawn from the center of the project site as well as benefiting communities which are not more than 4km away from the project site.

## 4.4 Environmental Components of the Study

A comprehensive description of the baseline conditions of the study area was intended. To this end, data collection covered meteorology, air quality and noise level, soil quality, vegetation and wildlife, hydrogeology, groundwater quality, socioeconomic and human health.

## 4.5 Study Approach and Methodology

Data collection and information gathering for the preparation of the ESMP document was carried out as described in the following subsections.

### 4.5.1 Description of Sampling Locations

Samples were collected from various sampling points, taking into account the distribution of project components, existing ecological features, and the geographical locations of nearby communities. The coordinates of the soil, water and air sampling point were recorded using the Global Positioning System (GPS), as detailed in Annex II.

Soil auger was used to collect samples at a depth of 0-15 cm from Six different locations per community along with one control sample taken from a site away from the project area. The samples were transported to the laboratory in polyethylene bags for analysis.

For water samples, two groundwater sources near the project site were identified for sampling, in addition to one source located further away. To collect water from the hand-dug well, a plastic container was prepared by tying a rope to it. A weight was secured under the plastic bottle and lowered until the bottle was submerged in the water. The filled bottle was raised when it appeared to be full, and care was taken to ensure that it did not touch the inner walls of the well to prevent contamination.

To preserve the integrity of the collected water samples, they were cooled to 4°C using a slurry of ice. This step minimized the potential for volatilization and other biochemical activities between the time of sampling and analysis (APHA, 2005). Some parameters were measured in situ, while others were analyzed at the Public Health Laboratory in the Civil Engineering Department at Abubakar Tafawa Balewa University, Bauchi.

### 4.5.2 Literature Review

A review of the existing baseline information from the past similar studies was carried out. This is with a view to understanding the existing environmental and social conditions of the project’s sites. Additionally, document relevant to the project such as the Project Implementation Manual (PIM), Engineering Designs of the Sub-projects, Nigeria’s National laws, edicts and regulations on environmental assessments, National Policies, AfDB E&S Safeguards Policies, and other relevant information.

### 4.5.3 Field Visits

The project sites were visited by the consultants on the 7th of September 2022 for data collection and information gathering. The visits helped the consultants to assess the existing social and environmental challenges related to the projects. The visits were conducted considering the security challenges around the project sites.

### 4.5.4 Biophysical Components

Field sampling and observations involved using standard methods such as: In-situ measurements with appropriate equipment having certified calibration; Laboratory analysis of samples using standard methods; Quality assurance and quality control management principles. Socioeconomics and Health Components Key methods have been used: Informant interviews; Focus Group Discussion (FGD); direct observation; Administration of structured questionnaires and Collection of secondary data. The field procedures adopted for data collection follow statutory requirements and in line with national and international policy on the protection and conservation of the environment.

## 4.6 Quality Assurance/Quality Control

The QA/QC programmes covered all aspects of the study, including sample collection and handling, laboratory analyses, generation of data and coding, data storage and treatment as well as report preparation. The quality assurance programme used in the fieldwork and laboratory analyses is in accordance with international and National regulatory recommendations such as:

- Ensuring that only experienced and qualified personnel are engaged in the study;

- Ensuring proper sampling in pre-cleaned sampling containers and after sampling proper labelling by capturing sample ID, location and date. 

- Carrying out field calibrations of equipment and running distilled water blanks to reduce errors that could arise from field measurements; 

- Ensuring that replicate samples are collected and used as checks on measurements; Carrying out field analytical operations in a defined sequence to avoid cross contamination of instruments.

- Collected samples were submitted on time to an FMEnv approved laboratories, which are well equipped with latest sophisticated instruments and managed by well experienced professionals.

Parameters such as temperature, pH, turbidity, electrical conductivity, and dissolved oxygen were determined in situ to avoid possible deterioration of samples due to microbial degradation and transformation. Therefore, the parameters were analyzed within the shortest possible time after collection.

## 4.7 Biophysical Environment

### 4.7.1 Climate/Meteorology

Bauchi State has a rainfall regime ranging from 1,300 mm per annum in the south (savanna zone) to only 700 mm in the far north (BSADP, 2007). This pattern is due to the fact that rains in the West African sub-region generally come from the south as they are carried by the southwest winds and dry weather prevails in the north due to the action of the northeast wind from the Sahara. The rainy season begins earlier in the southern part of the state, where it is heaviest and lasts longer. In contrast, in the northern tip of the state towards the end of June/July it rains at a maximum of 700 mm per year. The project region is located in the tropical zone, where the average hours of sunshine range from 5.25 hours per day in July to approximately 7.68 hours per day in December. Figures 5 and 6 presents the annual mean Temperature and precipitation respectively recorded in Bauchi state over a 15-year period.  The mean monthly temperature ranged from 26.43 °C to 27.44 °C. The mean annual precipitation for the period under review however ranges 810.75mm to 1105.48 (World Bank, 2023).

Figure 5: State mean annual temperature in Bauchi State 2007-2021(Data source: World Bank, 2023)

Figure 6: State mean annual Precipitation in Bauchi State 2007-2021(Data source: World Bank, 2023)

The records of wind speed and direction for 31 year-period is also provided for the individual project sites. Figure 7 presents the annual mean wind direction recorded at Mashema project site over a 30 years period. The least annual mean wind direction (36.25) recorded in the year 2008 and the highest mean value of 51.94 was recorded in the 2020. The highest mean annual wind speed (3.28 m/s) was recorded in the year 2015 while the least (2.39 m/s) was reported in 1990 (Figure 8).

Figure 7: Wind  direction at Mashema Model Primary School project site(Data source: NCRS, 2023)

Figure 8: Wind speed at Mashema Model Primary School project site (Data source: NCRS, 2023)

The mean annual wind direction at Dagauda site recorded for 30 years period is presented in Figure 9.  The highest value (88.25) was recorded in the year 2010 while the least record of 43.88 was in 1998. The highest mean annual wind speed (2.94 m/s) was recorded in the year 2013 while the least (2.59 m/s) was reported in 2013 as shown in Figure 10.

Figure 9: Wind direction at Dagauda Model Primary School project site (Data source: NCRS, 2023)

Figure 10: Wind speed at Dagauda Model Primary School project site (Data source: NCRS, 2023)

At Yelwan Duguri project site, the highest mean annual wind direction of 351.81was recorded in the year 2015, while the least value (111.06) was recorded in 2017 as presented in Figure 11.  However, the highest mean wind speed (3.87 m/s) was recorded in the year 2000 while the least record of 3.25 was in 1998 as shown in Figure 12.

Figure 11: Wind direction at Yelwan Duguri Model Primary School project site (Data source: NCRS, 2023)

Figure 12: Wind speed at Yelwan Duguri project site (Data source: NCRS, 2023)

### 4.7.2 Ambient Air Quality and Noise Level

The ambient air quality in the vicinity of the project sites is shown in Table 7.

Table 6: The ambient air quality and noise levels

| Parameters | Unit | Mashema | Dagauda | Yelwan Duguri | FMEnv LIMIT |
| --- | --- | --- | --- | --- | --- |
| S02 | ppm | 0.0 | 0.0 | 0.0 | 0.5 |
| NH3 | ppm | 0.0 | 0.5 | 0.3 | 1.0 |
| (H2S) | ppm | 0.0 | 0.0 | 0.0 | 8.0 |
| C0 | ppm | 0.0 | 0.0 | 0.0 | 10 |
| CH4 | ppm | 0.0 | 0.0 | 0.0 | - |
| PM10 | µg/m3 | 45 | 37 | 28 | 250 |
| Temp | 0C | 38.6 | 30.0 | 34.5 | Ambient |
| Noise | dB(A) | 46.5 | 46.9 | 40.0 | 90 |

The results show a general trend of acceptable values against FMEnv. Standards as pollutants measured including NH3 and PM10 fell within the acceptable guideline values while others like SO2, H2S, CO and CH4 were not detected in all the locations sampled. This may be due to low vehicular movement in the vicinity of the project sites as at the time of measurement.

The results of the measurements of the ambient noise levels in the study area show that the recorded levels ranged between 40 dB and 46.5dB. These values were generally below 90dB limit set by the FMEnv.

### 4.7.3 Soil Quality Assessment

The physicochemical characteristics of soil collected around the project sites are shown in Table 7.

Table 7: Physico-chemical characteristics of soil collected from the project sites

| S/N | Parameters | Mashema | Dagauda | Yelwan Duguri |
| --- | --- | --- | --- | --- |
| 1 | pH | 7.90 | 7.95 | 8.05 |
| 2 | EC (µs/cm) | 3.00 | 5.00 | 4.50 |
| 3 | Phosphorous P (mg/kg) | 0.48 | 0.56 | 1.38 |
| 4 | Phosphate PO4 (mg/kg) | 1.47 | 1.68 | 4.29 |
| 5 | TOC (%) | 3.95 | 1.49 | 1.97 |
| 6 | TOM (%) | 6.78 | 2.56 | 3.39 |
| 7 | CEC meq/100g | 0.57 | 0.63 | 0.59 |
| 8 | NitrateNO3 (mg/kg) | 34.85 | 43.00 | 41.95 |
| 9 | Nitrogen N (mg/kg) | 7.85 | 9.60 | 9.55 |
| 10 | Magnesium Mg (mg/kg) | 3.39 | 5.49 | 4.32 |
| 11 | Calcium Ca (mg/kg) | 6.15 | 5.56 | 5.41 |
| 12 | Potassium K (mg/kg) | 43.14 | 44.20 | 41.19 |
| 13 | Sodium Na (mg/k) | 92.68 | 100.85 | 97.22 |
| 14 | Nickel Ni (mg/kg) | BDL | 0.002 | BDL |
| 15 | Zinc Zn (mg/kg) | 0.12 | 0.12 | 0.13 |
| 16 | Copper Cu (mg/kg) | 0.24 | 0.16 | 0.08 |
| 17 | Lead Pb (mg/kg) | 0.07 | 0.05 | 0.04 |
| 18 | Iron Fe (mg/kg) | 1.38 | 4.45 | 5.00 |
| 19 | Cadmium Cd(mg/kg) | 0.008 | BDL | 0.02 |
| 20 | Chromium Cr (mg/kg) | 0.013 | BDL | 0.02 |

*BLD = Below Detection Limit

4.7.3.1 Soil pH

Soil pH is a measure of the concentration of hydrogen ions (H+) in the soil solution. pH is measured on a scale from 1 (acidic) to 14 (alkaline), with 7 being neutral on a negative logarithmic scale (base 10). Soil pH is essential because it influences the availability of plant's essential nutrients, microbial activities, and rate of organic matter decomposition. The optimum pH range for most crops is between 5.5 and 7.5. When soil pH is too low, it affects plant's growth and survival. Acidic soil causes deficiencies in plant essential nutrients. The mean soil pH values measured in soil samples obtained from Mashema, Dagauda and Yelwan Duguri were 7.0, 6.9 and 7.0 respectively, meaning that the soil in the area is generally neutral.

4.7.3.2 Electrical Conductivity

In soil, electrical conductivity (EC) is a measure of the ability of the soil to conduct an electrical current. Most importantly to fertility, EC is an indication of the availability of nutrients in the soil.  The EC values of 35µS/cm each was recorded for soil samples collected at Mashema and Dagauda while 30µS/cm was recorded at Yelwan Duguri project sites. The EC of the soil in all the project sites is generally low. This may not be unconnected with the low amount of Organic Matter (OM) and other nutrients. The particle size distribution could also account for the low EC as the soil had very low clay and high sand content.

4.7.3.3 Phosphorus

Soil Phosphorus (P) exists in organic and inorganic forms. Organic forms are found in humus and other organic material. Phosphorus in organic materials is released by a mineralization process involving soil organisms. The activity of these microbes is highly influenced by soil moisture and temperature (MSUES, 2010).

Soil samples collected at Yelwan Duguri site had more Available P (1.276mg/kg) compared to samples collected at Mashema and Dagauda with mean Available P values of 0.33mg/kg and 1.07mg/kg respectively.

4.7.3.4 Total organic carbon

Total organic carbon (TOC) is the carbon stored in soil organic matter. Organic carbon enters the soil through the decomposition of plant and animal residues, root exudates, living and dead microorganisms, and other soil biota. Soil Organic Carbon (SOC) is the main source of energy for soil microorganisms.

The soil samples obtained close to Yelwan Duguri project sites had the highest mean TOC (4.411%) compared to those collected at Mashema and Dagauda with mean TOC values of 1.449% and 3.97% respectively.

4.7.3.5 Total Organic Matter

Total Organic Matter (TOM) is a heterogeneous, dynamic substance that varies in particle size, carbon content, decomposition rate, and turnover time. SOM contains approximately 58% C; therefore, a factor of 1.72 can be used to convert OC to SOM. The soils samples collected in the vicinity of Yelwan Duguri projects had the highest mean TOM content of 7.57% while those collected close to a site at Mashema had the least mean TOM content of 2.493%.

4.7.3.6 Cation Exchange Capacity

Soils hold onto nutritional elements similar to the way they retain water. Positively charged nutrient molecules, called cations, are attracted to the negative charges on soil particles. This is called adsorption. The sites where cations attach to particles are cation exchange sites. The ability to hold cation nutrients is called the cation-exchange capacity (CEC). It is the ability of the soil’s negatively charged colloids to hold onto nutrients and prevent them from leaching beyond plant roots. The greater cation-exchange capacity a soil has, the more likely the soil will have a higher fertility level. When combined with other measures of soil fertility, CEC is a good indicator of soil quality and productivity.

Soil samples collected at Mashema project site had the highest mean CEC value (2.862cmol/kg), while those samples collected at Mashema and Dagauda sites had the least with mean values of 0.530cmol/kg and 0.597cmol/kg.

4.7.3.7 Nitrate

Nitrate concentration in soil is a good indicator of available nitrogen to plants. The required soil nitrate-nitrogen (NO3-N) for specific crops varies from crop to crop but in general, a concentration range of 10-50 mg/kg is desired.

The highest mean Nitrate content (161.7mg/kg) was recorded in soils obtained near the Model Primary Schools sites at Yelwan Duguri while the least content (65.1mg/kg) was recorded in samples collected at Mashema project site.

4.7.3.8 Nitrogen

Nitrogen is the seventh most abundant element in the universe. Nitrogen is found in all soils and is required by all living creatures. In plants, nitrogen is the nutrient required in the largest amounts. It is a key constituent of critical organic molecules such as amino acids, nucleic acids, and proteins. The analysis shows that soil sample collected at Dagauda site has the highest value recorded (31.00mg/kg), while the least value (14.35mg/kg) is recorded at Mashema sub project site.

4.7.3.9 Magnesium

Magnesium (mg) in the soil originates from the decomposition of rocks containing primary minerals including, biotite, dolomite, serpentine etc. Magnesium is also found in secondary clay minerals viz. chlorite, illite, montmorillonite and vermiculite. The soil analysis revealed that samples collected around the Model Primary Schools project site at Dagauda contain Mg (22.4 mg/kg) higher than those obtained from the other projects. Yelwan Duguri projects site had soil with the lowest level (4,66 mg/kg) of Mg content.

4.7.3.10 Calcium

Calcium (Ca) has two major effects in the soil. Firstly, Calcium works as a bonding agent in the aggregation of soil particles, in which it helps to bind organic and inorganic substances. This is important for the development of a good soil structure. Secondly, it acts as a nutrient filler, to maintain balance amongst nutrients and occupy space which otherwise would be taken up by acidic elements.

The concentrations of Ca contained in soils obtained from Mashema, Dagauda and Yelwan Duguri Model Primary Schools sub project sites were 4.968mg/kg, 4.890mg/kg and 4.956mg/kg respectively.

4.7.3. 11 Potassium

Potassium (K) is one of the essential nutrients in plants and in recent years is one of three (including nitrogen and phosphorus) that are commonly in sufficiently short supply in the soil to limit crop yields on many soil types. Potassium is commonly found in plants at levels above all other macro nutrients except carbon, oxygen, hydrogen and occasionally nitrogen. Potassium has many functions including the regulation of the opening and closing of stomata and therefore regulates moisture loss from the plant.

Soil samples collected in the vicinity of school sub project at Mashema had the highest mean K concentration of 185mg/kg. The mean K content of soils recorded at Dagauda and Yelwa Duguri sub project sites were 49.76mg/kg and 48.59mg/kg respectively.

4.7.3.12 Nickel

Nickel (Ni) is found in many ores as sulphide, silicates, and oxides. In polluted environments, nickel forms soluble complexes with organic material. Nickel is an interesting element because it acts both as a toxic heavy metal and an essential micro-element for plants. Although Ni is metabolically important in plants, it is toxic to most plant species when present at excessive amounts in soil and in a nutrient solution.

The mean Ni concentrations (0.008mg/kg and 0.022mg/kg) recorded in soil samples collected around the project sites at Mashema and Yelwan Duguri were very low and did not constitute any soil health hazard. The Metal was not detected in Dagauda project site.

4.7.3.13 Zinc

The mean Zinc (Zn) concentrations of 0.128mg/kg, 0.091mg/kg and 0.086mg/kg were recorded in soil samples obtained from Mashema, Dagauda and Yelwan Duguri project sites respectively. The Zn content in soils from all the project sites did not exceed the maximum permissible limit of 200-300mg/kg recommended by FMEnv.

4.7.3.14 Copper

Copper (Cu) occurs in the soil almost exclusively in divalent form. The largest fraction of Cu is usually present in the crystal lattices of primary and secondary minerals. In addition, a high proportion of Cu is bound by the soil organic matter. The Cu ion is adsorbed to inorganic and organic negatively charged groups and is dissolved in the soil solution as Cu2+ and organic Cu complexes (Mengel et al., 2001). Cu was detected in soil samples collected from all the project sites.

4.7.3.15 Lead

Lead (Pb) occurs naturally in small amounts in the earth's crust but is a metal that is widely distributed in the earth’s crust (soil and rocks), air and water. Lead is one of the most widespread heavy metal contaminants in soils. It is highly toxic to living organisms including plants. Lead has no biological function but can cause morphological, physiological, and biochemical dysfunctions in plants. Pb concentrations of 0.172mg/kg, 0.122mg/kg and 0.129mg/kg recorded in soil samples collected around the project sites at Mashema, Dagauda and Yelwan Duguri respectively did not exceed the limit of 85mg/kg set by DPR (2001).

#### 4.7.3. 16. Iron

The mean Iron (Fe) concentration (8.081mg/kg, 7.087mg/kg and 14.201mg/kg) were recovered in soil samples obtained at Mashema, Dagauda and Yelwan Duguri respectively. The Fe content of soils from all the subprojects did not exceed the 35 mg/kg background concentration in the standard soil as reported by Reimann and de Caritat (1998).

4.7.3.17 Cadmium

Cadmium (Cd) is a non-essential trace element that is widely distributed in the environment. Cd is considered to be one of the most toxic pollutants persistent in soil and is ranked on seventh position among all environmental pollutants (Khanna et al., 2022). The project sites at Mashema and Dagauda and Yelwan Duguri had mean soil Cd concentrations of 0.054mg/kg, 0.058.g/kg and 0.043mg/kg respectively. The Cd content of all the soil samples did not exceed the Target Value of 0.8mg/kg proposed by DPR (2002).

4.7.3.18 Chromium

The mean Cr concentrations recorded in soil samples in the vicinity of project sites at Mashema and Yelwan Duguri were 0.01mg/kg and 0.02mg/kg respectively. These values fall within the Target Value of 100mg/kg set by DPR (2002). Cr content detected in soil samples obtained from Mashema, Dagauda and Yelwan Duguri were 0.049mg/kg, 0.081mg/kg and 0.080mg/kg respectively. The mean Cr concentrations in soil samples collected at the various project sites, therefore, revealed no immediate threat to the environment as the metal concentrations are generally low.

### 4.7.4 Groundwater Quality

The result of the water quality analysis for the Model Primary Schools sites is shown in Table 8

Table 8:  Water quality parameters at 3 Model Primary Schools.

| S/N | PARAMETERS | Mashema | Dagauda | Yelwan Duguri | NSDWQ LIMTS 2007 | WHO LIMIT 2022 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Temperature OC | 27.5 | 27.8 | 27.4 | Ambient | Ambient |
| 2 | pH | 7.3 | 7.5 | 7.7 | 6.5-8.5 | 6.5 - 8.5 |
| 3 | Electrical Conductivity EC(μs/cm) | 520 | 170 | 90 | 1000 | 400-1200 |
| 4 | Total Dissolved Solid (mg/L) | 375 | 126 | 71 | 500 | 1000 |
| 5 | Turbidity (NTU) | 18 | 3 | 0 | 5 | 5 |
| 6 | Sulphate SO4-2(mg/L) | 21 | 4 | 7 | 100 | 250 |
| 7 | Chloride Cl-2 (mg/l) | 15 | 59 | 36 | 250 | 250 |
| 8 | Dissolved oxygen DO (mg/l) | 7.3 | 8.4 | 7.5 | 3.0 | 6.5-8.5 |
| 9 | Nitrate, NO3-2 (mg/l) | 19.1 | 9.1 | 21.5 | 50 | 45 |
| 10 | Salinity(mg/l) | 286 | 94 | 50 | 50 | 200 |
| 12 | Oil & Grease(mg/l) | 0.4 | 0.3 | 0.3 | 10 | NA |
| 13 | COD (mg/l) | 49.23 | 16.58 | 14.25 | - | 10.0 |
| 14 | BOD5(mg/l) | 2.1 | 1.3 | 4.9 | 6 | 5.0 |
| 15 | Nickel, Ni 2+(mg/l) | 0.000 | 0.000 | 0.000 | 0.02 | 0.07 |
| 16 | Zinc, Zn2+ (mg/l) | 0.110 | 0.242 | 0.122 | 3 | 5 |
| 17 | Copper, Cu2+ (mg/l) | 0.016 | 0.009 | 0.002 | 1 | 2.00 |
| 18 | Lead, Pb2+ (mg/l) | 0.001 | 0.000 | 0.000 | 0.01 | 0.01 |
| 19 | Iron Fe, 2+ (mg/l) | 0.116 | 0.249 | 0.209 | 0.3 | 0.3 |
| 20 | Cadmium, Cd2+ (mg/l) | 0.000 | 0.000 | 0.000 | 0.003 | 0.003 |
| 21 | Chromium, Cr2+ (mg/l) | 0.000 | 0.000 | 0.011 | 0.06 | 0.005 |

#### 4.7.4.1 Temperature

The Temperature of water should be maintained at certain limit for aesthetic reason. People complain about tab water when the temperature exceeds certain limit. The intensity of taste is greatest for water at room temperature and is significantly reduced by chilling or heating the water. Increasing the temperature will also increase the vapour pressure of trace volatiles in drinking water and, therefore, could lead to increased odour. It is also possible that micro fungi can grow inside the internal plumbing systems of buildings, leading to complaints of musty, earthy, or mouldy tastes and odours if the temperature rises.

The temperature of the Groundwater is affected by the ambient air temperature. The mean temperature values of 27.60C, 27.80C and 27.70C were recorded in water samples obtained at the Mashema, Dagauda and Yelwan Duguri Model Primary School sites respectively.

#### 4.7.4.2 pH

pH is a measure of the relative amount of free hydrogen and hydroxyl ions in the water. Water that has more free hydrogen ions is acidic, whereas water that has more free hydroxyl ions is basic. The range goes from 0 - 14, with 7.0 being neutral. pH of less than 7.0 indicate acidity, whereas a pH of greater than 7 indicates a base. The pH of the water samples obtained from Mashema, Dagauda and Yelwan Duguri were 7.2, 7.5 and 7.3 respectively. The pH of all the water samples falls within the limit of 6.5 – 8.5 recommended by both NSDWQ (2007) WHO (2022).

#### 4.7.4.3 Electrical Conductivity

Electrical Conductivity (EC) is a measurement of the ability of an aqueous solution to carry an electrical current. Water samples collected from Model Primary School sites at Mashema had the highest mean value of conductivity of 520µS/cm whereas the site at Yelwan Duguri had the lowest mean value of 35.0µS/cm. However, all values did not exceed the threshold limits of 1,000µS/cm and 400-1200µS/cm recommended by the NSDWQ (2007) and WHO (2022) respectively.

#### 4.7.4.4 Total Dissolved Solids

This parameter arises from the dissolved substances from organic compounds as well as decomposition of inorganic substances such as nitrate and carbonate. From the results obtained, mean TDS values of 97.0mg/l, 120mg/l and 29.0mg/l were recorded for ground water samples collected from the Model Primary Schools sites at Mashema, Dagauda and Yelwa Duguri respectively. The values from all the samples did not exceed the limits of 500 and 1000 recommended by NSDWQ (2002) and WHO (2022) respectively.

#### 4.7.4.5 Turbidity

Turbidity is the measure of relative clarity of water. Turbidity makes water cloudy or opaque. Excessive turbidity, or cloudiness, in drinking water is aesthetically unappealing, and may also represent a health concern.  Mean turbidity values of 1.00NTU, 3.00NTU and 5.00NTU were recorded in water samples collected from Mashema, Dagauda and Yelwan Duguri respectively. The mean turbidity values of water collected from all the sampling points did not exceed the limits of 6.0NTU and 5.0 MTU recommended by NSDWQ (2007) and WHO (2022) respectively.

#### 4.7.4.6 Sulphate

Sulphates exist in nearly all natural waters and their concentrations vary according to the nature of the terrain through which the water flows. They are often derived from the sulphide of heavy metals (iron, nickel, copper and lead). Iron sulphides are present in sedimentary rocks from which they can be oxidized to sulphate in humid climates; the latter may then leach into water courses so that ground waters are often excessively high in sulphates. The highest mean Sulphate concentrations was recorded in water samples collected from Dagauda (4.00mg/L) while the least was recorded in samples from Yelwan Duguri (2.00mg/L). The mean sulphate concentrations from all the Model Primary Schools sites were far below the recommended limit of 100 mg/L and 250mg/L set by NSDWQ (2007) and WHO (2022) respectively.

#### 4.7.4.7 Chloride

In natural water, chlorides originate from weathering of chloride minerals. Such minerals are widely distributed and exist in form of potassium, calcium and sodium salts. The concentrations of chloride in water collected from Mashema, Dagauda and Yelwa Duguri were 45.0mg/L, 69.0mg/L and 49.0mg/L respectively. The levels of Chloride detected in the water from all the three project sites did not exceed the maximum allowable limits of 250mg/l and 250mg/l set by the NSDWQ (2007) and WHO (2022) respectively.

#### 4.7.4.8 Dissolved oxygen

The Dissolved Oxygen (DO) content of water is influenced by many factors including the water source, temperature and other biochemical processes taking place within the water body. Reduced oxygen level encouraged microbial conversion of sulphate to sulphite and nitrate to nitrite. The mean dissolved oxygen values of 8.10mg/l, 8.40mg/l and 7.30mg/l recorded from the project sites at Mashema, Dagauda and Yelwan Duguri respectively are considered to be optimum as they are well above the 3.0mg/L and 6.5mg/L recommended by NSDWQ (2007) and WHO (2022) respectively.

#### 4.7.4.8 Nitrate

There is a growing concern on level of Nitrate in drinking water because high concentration can cause "blue baby" syndrome (methemoglobinemia). The nitrate itself is not a direct toxicant but is a health hazard because of its conversion to nitrite which reacts with blood hemoglobin to cause methemoglobinemia. The mean Nitrate values of 12.8mg/l, 9.10mg/l and 11.8mg/l recorded in water samples collected from Mashema, Dagauda and Yelwan Duguri respectively did not exceed the limit of 50.0mg/L and 45mg/L recommended by NSDWQ (2007) and WHO (2022) respectively.

#### 4.7.4.10 Salinity

Salinity is the total amount of salts contained in water. The salts could be in various forms such as sodium, potassium, magnesium, chlorides etc. The taste of water can be affected by the total amount of salts in that water. The highest level of salinity (94.0mg/L) was recorded in water samples collected from Dagauda project site while the least mean value (20mg/L) was found in sample obtained from Yelwan Duguri.  The samples from Mashema had mean salinity of 66.0mg/L. From the analysis, it is very clear that the water samples from Mashema and Dagauda had their salinity values in excess of 50mg/l and the recommended value set by NSDWQ (2007) but falls withing the 200mg/L limit set by WHO (2022).

#### 4.7.4.11 Oil & Grease

Oil and grease normally float on water surface due to its low density compared to the water. However, not all oil and grease is liquid form as some amount may remain disperse in the water in finely divided emulsified form. Due to the importance of ion and grease for water quality and safety, regulatory authorities set limit in order to control the amount that enters water aquifers and reservoirs. The oil and grease recovered from the water samples collected from the entire project sites did not exceed the limit of 10.0mg/L recommended by NSDWQ (2007).

#### 4.7.4.12 Biochemical Oxygen Demand and Chemical Oxygen Demand

The biochemical oxygen demand (BOD) represents the amount of dissolved oxygen (DO) consumed by biological organisms when they decompose organic matter in water. The chemical oxygen demand (COD) is the amount of oxygen consumed when the water sample is chemically oxidized. The highest COD (18.13mg/L) was recorded in samples obtained from Mashema project site, while the least was recorded from Yelwan Duguri sites with mean value of 12.2mg/L. The BOD recorded in samples obtained from Mashema, Dagauda and Yelwan Duguri were 3.10mg/L, 1.30mg/L and 3.10mg/L respectively. Both the BOD recorded in groundwater around the project sites falls within the accepted limits of 5.0mg/L recommended by WHO (2022). However, the COD recorded in the water samples exceeded the 10 mg/L recommended by the WHO.

#### 4.7.4.13 Nickel

Nickel is one of many heavy metals widely distributed in the environment. Drinking water generally contains nickel at concentrations less than 10 μg L-1. Elevated nickel levels may exist in drinking water because of the corrosion of nickel-containing alloys used for pipes and other components in the water distribution system as well as from nickel-plated fittings. However, nickel may also be present in some ground waters as a consequence of dissolution from nickel ore-bearing rocks (Mansour and Hasieb, 2012). Ni was not detected from water samples obtained from all the project sites.

#### 4.7.4.14 Zinc

Zinc is a very common substance that occurs naturally in air, water, and soil.  But zinc concentrations are rising unnaturally, due to addition of zinc through human activities.  Most zinc is added to the environment during industrial activities such as mining of coal and waste combustion and steel processing. Water – soluble zinc that is found in soil can contaminated ground and surface water. Although, humans can handle proportionally large concentrations of zinc, too much zinc can still cause eminent health problems, such as stomach cramps, skin irritations, vomiting, nausea and anemia.

The mean Zn concentrations recorded in water samples collected from all the three model Primary Schools sites were 0.095mg/L, 0.242mg/L and 0.140mg/L respectively for Mashema, Dagauda and Yelwan Duguri. These values are far below the limit of 3.00mg/L and 5.00mg/L recommended by NSDWQ (2007) and WHO (2022).

#### 4.7.4.15 Copper

Copper is a mineral and natural component of soil. It is an essential nutrient for humans and plants. Industrial pollution, domestic sewage, mining effluents, and weathering of copper-bearing rocks are the major sources of copper in surface and groundwater. Copper is an essential nutrient for all higher plants and animals. In animals, it is mainly found in the bloodstream, as a cofactor in various enzymes, and in copper-based pigments. However, exposure to higher doses can be harmful. Long-term exposure to copper can irritate the nose, mouth, and eyes and cause headaches, dizziness, nausea, and diarrhea.

The mean values of Cu recorded in water samples from Mashema (0.108mg/L), Dagauda (0.009mg/L) and Yelwan Duguri (0.024mg/L) falls within the threshold limit of 1.0 mg/L and 3.0mg/L set by NSDWQ (2007) and WHO (2022) respectively.

#### 4.7.4.16 Lead

Lead (Pb) occurs naturally in the environment.  However, in recent times most lead concentrations found in the environment results from human activities.  Lead can pose a threat to the environment if it moves through the soil and contaminates groundwater and surface waters, or if it is transferred to biota. Many factors influence the mobility and bioavailability of lead: pH, soil texture (especially clay content), and organic matter content. Since dissolved lead in soils is commonly in the form of Pb2+, the adsorption on cation exchange sites of clays or organic matter can decrease the mobility and availability of lead in the short term. Lead was not detected in the water samples collected around the project sites except for Mashema where a mean Pb concentration of 0.012mg/L was recorded which falls within the limit of 0.01mg/L set by the NSDWQ (2007) and WHO (2022).

#### 4.7.4.17 Iron

The primary source of iron in drinking water is the natural geologic source. High concentrations of dissolved iron can result in poor tasting, unattractive water that stains clothing. The results of the analysis indicated that mean iron concentrations of 0.329mg/L, 0.149mg/L and 0.323mg/L were recorded in samples from Mashema, Dagauda and Yelwan Duguri respectively.  The mean values in samples collected at Mashema and Yelwan Duguri slightly exceeded the limit of 0.30mg/L recommended by NSDWQ and WHO for Total Fe in drinking water.

#### 4.7.4.18 Cadmium

Groundwater rarely contains high concentrations of cadmium unless contaminated by mining or industrial effluents or seepage from hazardous waste sites. Soft or acidic water tends to dissolve cadmium from water pipes; Cadmium levels are elevated in stagnant water in domestic plumbing. These sources have not been reported to cause clinical cadmium poisoning, but even low levels of contamination contribute to the accumulation of cadmium in the body. No Cd was detected from the samples obtained from all the project sites.

#### 4.7.4.19 Chromium

The environmental contamination of Cr is of increasing concern as it is distributed worldwide with high concentrations in both ground and surface water due to natural and anthropogenic activities. No chromium was detected in all the water samples collected at Dagauda and Yelwan Duguri and thus, the water sources within and around the proposed project sites were free of the metals contamination either from natural or anthropogenic source(s). At Mashema however, mean Cr concentration of 0.008mg/l was detected which is a very low and safe level compared to the limit of 0.30mg/L and 0.05mg/L recommended by NSDWQ (2007) and WHO (2022) respectively.

### 4.7.5 Biodiversity Assessment

4.7.5.1 Vegetation

The State is one of the few states in Northern Nigeria that has two distinctive ecological zones; namely, the Sudan savannah and the northern semi-arid zone. The Sudan savannah covers the Southern part of the State where the vegetation gets richer and richer towards the South, whereas the Sahel also known as the semi-arid vegetation covers the Western and Northern parts of the State. On the other hand, the south-western part of the State is mountainous as a result of continuation of the Jos-Plateau while the Northern part is generally sandy as a result of the influence of the desert. The vegetation types shown above are conditioned by the climatic factors, which in turn determine the amount of rainfall received in the area.

The Mashema and Dagauda project sites falls within the Sahel savanna zone characterized by isolated strands of horny shrubs and sandy soils.  The grasses in the area are short, 0.5m to 1.0m high. The Yelwan Duguri site for the proposed Model Primary Schools projects however falls within the Sudan vegetation zone in southern Bauchi characterized by the presence of short grasses, about 1-2 m high, and some relatively more luxuriant tree species.

4.7.5.2 Faunal species

The faunal species found at the three project sites are described below.

Mashema Model Primary School project site

The most common mammals, birds, reptiles and invertebrates known to inhabit the Mashema, Dagauda and Yelwan Duguri Model Primary School project sites as shown in Table 9

Table 9: Biodiversity of the project sites

| Sampling Location | Coordinates |  | Floral Species Composition |  |  |
| --- | --- | --- | --- | --- | --- |
| Mashema Model School | N: 11o 47’ 04’’ E: 009o56’ 25’’ |  | Cereals Pennisetum glaucum (Millet) Sorghum bicolar (Guinea corn) Vegetables Ipomea batatas (Sweet potato) Manihot esculentus (Casava) Arachis hypogea (Ground nut) Amaranthus cruentus (Amaranthus) Abelmoschus esculentus (Okro) Solanum melongena (Garden egg) Trees Mangifera indica (Mango) Anacardium occidentale (Cashew) Acacia albida (Apple-ring acacia) Azadirachta indica (Neem) Parkia biglobosa (African locust bean) Adansonia digitata,(Baobab) Acacia arabica (Gum Arabic tree) Prosopis africana (African mesquite) Grasses Digitaria debilis, Dactyloctenium aegyptium, Elusine indica, Cenchrus biflorus, Cynadon dactylon Pennisetum purpureum Acanthospernum hispidum Ageratum conyzoides Tridex procumbens. |  |  |
| Dagauda Model School | N: 11o 42’ 47’’ E: 010o 51’ 51’’ |  | Cereals Pennisetum spp. (Millet) Sorghum bicolar (Guinea corn) Tubers and Vegetables Ipomea batatas (Sweet potato) Manihot esculentus (Casava) Arachis hypogea (Ground nut) Amaranthus cruentus (Amaranthus) Abelmoschus esculentus (Okro) Trees Azadirachta indica (Neem) Parkia biglobosa (African locust bean) Adansonia digitata,(Baobab) Acacia senegalensis (Gum Mangifera indica (Mango) Anacardium occidentale (Cashew) Acacia albida (Apple-ring acacia) Arabic tree) Prosopis africana (African mesquite) Grasses Pennisetum setosum Tridex procumbens Digitaria debilis, Dactyloctenium aegyptium, Elusine indica, Cenchrus biflorus, Cynadon dactylon Pennisetum purpureum Acanthospernum hispidum Ageratum conyzoides Imperata cylindrical (Spear grass) |  |  |
| Yelwan Duguri Model School | N: 09o 57’ 54’’ E: 010o 11’ 12’’ |  | Cereals Oryza sativa Zea mays (Maize) Celosia esculentus (cocoyam) Sorghum bicolar (Guinea corn) Tubers and Vegetables Ipomea batatas (Sweet potato) Manihot esculentus (Casava) Musa sapientum (Banana) Arachis hypogea (Ground nut) Amaranthus cruentus (Amaranthus) Abelmoschus esculentus (Okro) Solanum melongena (Garden egg) Trees Mangifera indica (Mango) Anacardium occidentale (Cashew) Carica papaya (Pawpaw) Khaya senegalensis Terminalia laxifora Detarium macrocarpurn Anogeissus leiocarpus Vitellaria paradoxa Bosweillia dalzielii. Azadirachta indica (Neem) Parkia biglobosa (African locust bean) Grasses Striga hermonthica Imperata cylindrical Talinum triangulare Andropogon pseudapricus, Andropogon gayanus Anthrophora nigritane Aristida stipoides Dactyloctenium aegyptium Elusine indica Cynadon dactylon Pennisetum setosum Pennisetum purpureum Hyparrhenia spp. |  |  |
| Sorghum bicolar (Sorghum) |  |  | Adansonia digitata (Baobab) |  | Cynadon dactylon (Bamuda grass) | Arachis Hypogaea (Peanut) |  |
| Zea mays (Maize) |  |  | Azadirachta indica (Neem) |  | Pennisetum purpureum (Elephant grass) | Amaranthus cruentus (Amaranth) |  |

### 4.7.5.2 Faunal species

The most common mammals, birds, reptiles and invertebrates known to inhabit the Mashema, Dagauda and Yelwan Duguri model primary school project sites as shown in Table 10.

Table 10: Common faunal species found in the vicinity of the project sites.

| Sampling Location | Coordinates |  | Faunal Species Composition |  |  |
| --- | --- | --- | --- | --- | --- |
| Mashema Model School | N: 11o 47’ 04’’ E: 009o56’ 25’’ |  | Mammals Ovis aries (Domestic Sheep) Felis catus Domestic cat Capra aegagrus-hircus (Domestic goat) Xerus erythropus (Ground squirrel) Thryonomys swinderianus (Grass cutter) Rattus rattus (House rat) Lepus victoriae (African Hare) Erinaceus europaeus (Hedgehog) Avian Columba guinea (Speckled pigeon) Streptopelis senegalensis (Laughing dove) Streptopelia decipiens (African Mourning Dove) Haliaetus vocifer (West African eagle) Corvus albus (Pied Crow) Passer griseus (Grey headed Sparrow) Centropus senegalensis (Senegal coucal) Reptiles Agama agama (Agama Lizard) Veranus niloticus (Nile Monitor) Chamaeleo gracilis (Cameleon) Kinixys erosa (Tortoise) Hemidactylus mabouia (Wall Gecko) Echis Ocellatus (Carpet viper) Invertebrates Marcotermes bellicosus (Termites) Lepisiota sp. (Black ant) Musca domestica (House Flies) Achaeranea tepidariorum (Spider) Buthus occitanus (Scorpion) Anopheles sp. (Mosquitoes) Lumbricus terrestris (Earthworm) Lithobius spp. (Centipede) |  |  |
| Dagauda Model School | N: 11o 42’ 47’’ E: 010o 51’ 51’’ |  | Mammals Domestic goat Ovis aries (Domestic Sheep) Felis catus Domestic cat Capra aegagrus-hircus (Domestic goat) Xerus erythropus (Ground squirrels) Rattus rattus (House rat) Lepus victoriae (African Hare) Erythrocebus patas (Patas monkey) Erinaceus europaeus (Hedgehog) Avian Milvus aegyptius (Yellow-billed Kite) Lophoceros nasutus (African Grey Hornbill) Passer griseus (Grey headed Sparrow) Bubulcus ibis (Cattle egret) Euplectes franciscanus Northern Red Bishop Ploceus luteolus (Little Weaver) Columba guinea (Speckled pigeon) Reptiles Naja nigricollis (spitting cobra) Python regius (Python) Python sebae (Forest Python) Agama agama (Agama Lizard) Veranus niloticus (Nile Monitor) Chamaeleo gracilis (Cameleon) Kinixys erosa (Tortoise) Hemidactylus mabouia (Wall Gecko) Invertebrates Achaeranea tepidariorum (Spider) Archispirostreptus gigas (Milipede) Musca domestica (House Fly) Lumbricus terrestris (Earthworm) Marcotermes bellicosus (Termites) |  |  |
| Yelwan Duguri Model School | N: 09o 57’ 54’’ E: 010o 11’ 12’’ |  | Mammals Tragelaphus scriptus (Bush buck) Hysteric cristata (Porcupine) Lepus victoriae (African Hare) Ceviticus civeta (Civet cat) Erythrocebus patas (Patas monkey) Erinaceus europaeus (Hedgehog) Xerus erythropus (Ground squirrels) Thryonomys swinderianus (Grass cutter) Rattus rattus (House rat) Avian Aqulia rapax (Tawny eagle) Milvus migrans (Black kites) Corvus albus (Pied Crow) Passer griseus (Grey headed Sparrow) Bubulcus ibis (Cattle egret) Streptopelis senegalensis (Laughing dove) Cuculus gularis (African cuckoo) Corvus albus (Pied Crow) Milvus aegyptius (Yellow-billed Kite) Columba guinea (Speckled pigeon) Reptiles Pelusios castaneus (Forest Tortoise) Python regius (Python) Agama agama (Agama Lizard) Hemidactylus mabouia (Wall Gecko) Chamaeleo gracilis (Cameleon) Kinixys erosa (Tortoise) Veranus niloticus (Nile Monitor) Invertebrate Lithobius spp. (Centipede) Lumbricus terrestris (Earthworm) Lepisiota sp. (Black ant) Musca domestica (House Flies) Achaeranea tepidariorum (Spider) Buthus occitanus (Scorpion) Anopheles sp. (Mosquitoes) |  |  |
| Felis catus (Domestic cat) |  |  | Bubulcus ibis (Cattle egret) |  | Agama agama (Agama Lizard) | Lumbricus terrestris (Earthworm) |  |
| Capra hircus (Domestic goat) |  |  | Columba guinea (Speckled pigeon) |  | Hemidactylus mabouia (Wall Gecko) | Lithobius spp. (Centipede) |  |

### 4.7.7 Hydrogeology

The geology of Bauchi state is broadly divided into areas underlined by crystalline basement complex rocks and the sedimentary rocks. The southwestern part of the State is covered by Precambrian-Paleozoic basement rocks, while the southeastern part of the state is covered by the Paleocene Kerri-Kerri formation. The Quaternary Chad formation covers some parts of the northern part of the State. Groundwater occurs in the Basement Complex either in the weathered basement or in the Joint and fracture system in the unweathered rocks (Dike and Dan-Hassan, 1990). The presence of groundwater in any given area, therefore, depends on whether a sufficient thickness and extent of decomposed material are present to provide a reservoir, or whether joints and fractures are present in the fresh rock. The Basement Complex generally forms a poor source of groundwater. The decomposed mantle is often too thin to harbour large quantities of water and is usually too clayey to be highly permeable (Abdulrahman, Shehu and Ibrahim 2016).

## 4.8 Socioeconomic Environment Assessment

The project will take place at Dambam (in Dambam LGA), Mashema (Itas/Gadau LGA) and Yelwan Duguri (in Alkaleri LGA) all in Bauchi State. The socio-economic characteristics of these communities are discussed below:

### 4.8.1 Sex, Age and Marital Status of the Respondents

Age Distribution

Majority of the respondents in the three communities are between the ages of 41-50 followed by those between 31-40 years. This shows that most of the respondents are within their active age group that can efficiently and effectively participate in the project. Also, they can offer a labour pool from which contractors can source for workers for the projects.

Table 11: Age Distribution of Respondents

| Age | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| 18-30 | 5.7% | 3.1% | 6.1% | 5.0% |
| 31-40 | 32.9% | 29.8% | 27.3% | 30.0% |
| 41-50 | 35.6% | 36.0% | 36.4% | 36.0% |
| 51-60 | 17.2% | 20.4% | 18.2% | 18.6% |
| Above 60 | 8.6% | 10.7% | 12.1% | 10.5% |

Sex Distribution

The result showed that 67 % of the respondents were male while 33 % were female. This indicates that the men will provide sufficient human capital from the communities that the contractors can recruit personnel for the execution of this project.

Table 12: Sex Distribution of Respondents

| Sex | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Male | 68.1% | 66.7% | 65.2% | 66.6% |
| Female | 31.9% | 33.3% | 34.8% | 33.4% |

Marital Status

Majority of the respondents in all the three communities are married with a few that are single or divorced.

Figure 13: Marital status

### 4.8.2 Education

The educational level of the respondents showed that 10% of the respondents had less than primary education, 19.5% had Qur’anic education, about 37% have attended and completed primary school, 20% completed secondary school, while 13.4% had tertiary education qualification, this includes those that have a diploma, Nigerian Certificate in Education and Degree certificates.

Figure 14: Educational qualification

### 4.8.3 Number of children per household

The number of children per household was one of the socioeconomic characteristics examined; the findings revealed majority representing 57.6% had between 4 to 7 people in their household. This is encouraging as number of people in a household is a source of pool of people that are needed to be trained in different types of vocation more especially many of them already have one form of educational certificate or the other, since government jobs or the so-called white-collar jobs are not readily available. This further shows that this project when completed will have wide-reaching positive impact on beneficiaries in the community.

Table 13: Number of children per household

| Number of Children | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| 1-3 | 27.5% | 23.1% | 21.2% | 23.9% |
| 4-7 | 55.1% | 61.5% | 56.1% | 57.6% |
| 8-11 | 10.1% | 9.2% | 13.6% | 11.0% |
| Above 11 | 7.2% | 6.2% | 9.1% | 7.5% |

### 4.8.4 Languages Spoken

The study also examined the languages spoken in the study area, it was revealed that 29% of the respondents speak Hausa, 17.5% speak Fulani, 19.5% speaks Karai-Karai, 15% speaks Duguri, and 7.5% speaks Gerawa, while 5% speak Jarawa language.

Figure 15: Ethnic composition

### 4.8.5 Occupation

Primary occupation of the respondents in the study area revealed that 62.5% of the respondents were into farming, 11% were involved in Agric trading, 10% were into Agric processing, 6.5% are into public sector employment, 5% are into domestic duties, while 1.5% of the respondents were into fish capture.

Table 14: Primary Occupation

| Primary Occupation | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Farming | 66.7% | 63.1% | 57.6% | 62.4% |
| Agric Trading Business | 11.6% | 10.8% | 10.6% | 11.0% |
| Agric Processing | 10.1% | 10.8% | 9.1% | 10.0% |
| Fish Capture | 1.4% | 1.5% | 1.5% | 1.5% |
| Formal Private Employment | 1.4% | 3.1% | 6.1% | 3.5% |
| Public Sector Employment | 5.8% | 6.2% | 7.6% | 6.5% |
| Domestic Duties | 2.9% | 4.6% | 7.6% | 5.0% |

### 4.8.6 Income Level

The majority (66%) of the respondents had an income of N200,000 -N400,000 per annum, 10% earn between N1.00 -N100,000 per annum, 7% reported that they generate between N101,00-N200,000 as income per annum, 12% generate between N400,000-N500,000 per annum, while 5% of the respondents earn above N500,000 as income per annum. The projects will boost the health status of the community members which in turn will enable them to improve their personal income and wellbeing.

Table 15: Income levels

| Income (Amount in Naira) | Dagauda | Mashema | Yelwa Duguri | Total |
| --- | --- | --- | --- | --- |
| ₦1.00- ₦100,000 | 5.8% | 15.3% | 9.1% | 10.1% |
| ₦101,000 - ₦200,000 | 8.7% | 7.7% | 4.6% | 7.0% |
| ₦201,000 - ₦300,000 | 50.7% | 50.9% | 51.1% | 50.9% |
| ₦301,000 - ₦400,000 | 14.5% | 12.3% | 18.2% | 15.0% |
| ₦401,000 - ₦500,000 | 13.0% | 10.7% | 12.0% | 11.9% |
| Above ₦500,000 | 7.2% | 3.1% | 5.0% | 5.1% |

### 4.8.7 Housing

Findings with regards to types of housing used by the respondents in Table 12 showed that 73% of the respondents live in a cement block house with corrugated roof, 17% were in house built by mud blocks with corrugated iron roof, while 10% of the respondents live in traditional huts with grass roof. The result shows that majority of the people in the project community live in houses that were built with cement blocks and having a corrugated iron roof. This also can be linked to the income of people living in the project area, by virtue of these findings, when the project is been implemented it’s going to improve the living standard and wellbeing of people living in the project communities.

Table 16: Types of Housing

| Type(s) of Housing | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Traditional hut/grass roof | 7.2% | 12.3% | 10.1% | 9.9% |
| Mud block/corrugated iron roof | 18.8% | 17.0% | 15.2% | 17.0% |
| Cement Block/corrugated roof | 73.9% | 70.7% | 74.7% | 73.1% |

### 4.8.8 Sources of water in the household

The responses of the sampled communities on the sources of water in their communities are presented in Table 17. The major source of water as reported by 70% of the respondents is borehole. Other sources are tap water and rainwater as reported by 22% and 8% respectively.

Table 17: Main Source(s) of Water in the Household

| Main source of water | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Tap | 24.5% | 18.5% | 22.0% | 21.7% |
| Borehole | 69.7% | 69.2% | 70.0% | 69.6% |
| Rain | 5.8% | 12.3% | 8.0% | 8.7% |

### 4.8.9 Experience of water shortage in the household

The result in Table 18 presents the opinions of the respondents on the experience of water shortage in their households. Although about 13% of the respondents reported that they experience water shortage in their households, majority representing 87% said they do not experience water shortage. The water shortage is only seasonal, normally during the dry months.

Table 18: Experience of water shortage in the households

| Response | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Yes | 9.1% | 15.4% | 14.8% | 13.1% |
| No | 90.9% | 84.6% | 85.2% | 86.9% |

### 4.8.10 System of sewage disposal

The system adopted for sewage disposal in the sampled communities was examined. The distributions of the respondents by type of the systems of sewage disposed are presented in Figure 16. The result shows that 80% of the respondents use communal gutters as their system of sewage disposal, while 20% of the respondents dispose their sewage through releasing the wastewater to individual septic tanks.

Figure 16: System of Sewage Disposal

### 4.8.11 Toilet types

The distributions of the respondents based on the type of toilet used by households are presented in Figure 9. Pit latrine is the main type of toilet used by households in the sampled communities as indicated by 82% of the respondents, 9.5% use open defecation, 6% uses VIP latrine. While 2.5% reported that their toilet types are the conventional water system closet.

Figure 17: Toilet types

### 4.8.12	Sanitation

Frequency of cleaning households’ surroundings is one of the good sanitary practices and respondents’ responses on this are presented in Table 19. Seventy five percent of the respondents reported that they clear their household surrounding weekly. However, 15% of the respondents reported that the clear their households surrounding bi-weekly while 10% reported cleaning of the household surrounding monthly.

Table 19: Frequency of clearing bushes around household surroundings

| Response | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Weekly | 5.8% | 9.2% | 15.2% | 10.1% |
| Biweekly | 13.0% | 9.2% | 22.7% | 15.0% |
| Monthly | 81.2% | 81.5% | 62.1% | 74.9% |

### 4.8.13 Methods of refuse/solid waste disposal

The commonest methods of refuse/solid waste disposal in the sampled communities are open dumping and burning as reported by 67% and 23% of the respondents respectively. Composting is also practiced to a lesser degree.

Figure 18: Methods of solid wastes disposal

### 4.8.14 Health and Hygiene

The respondents were asked if they have knowledge on their health and hygiene status and their responses are presented in Table 20. Majority of the respondents representing 75.5% said they have knowledge on their health and hygiene status while 24.5% of the respondents reported that they do not have knowledge with regards to their health and hygiene status. This shows that a good number of people living in the project communities a well-educated with regards to knowing their health and hygiene status.

Table 20: Information on health and hygiene status of the household

| Response | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Yes | 79.7% | 69.2% | 77.3% | 75.4% |
| No | 20.3% | 30.8% | 22.7% | 24.6% |

### 4.8.15 Factors responsible for good health

Respondents were asked to give their responses on four (4) identified factors responsible for good health in their households and their responses are presented in Table 21. Access to health care and clean environment are the first two factors responsible for good health in their household as reported by 39.5% and 48% of the respondents respectively. Emergency preparedness (2.4%) and education/good job accounted for 10.0%.

Table 21: Factors responsible for good health in the households

| Response | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Access to health care | 42.2% | 35.4% | 40.9% | 39.5% |
| Clean environment | 45.1% | 49.2% | 50.0% | 48.1% |
| Emergency preparedness | 2.5% | 3.1% | 1.5% | 2.4% |
| Education/Good job | 10.2% | 12.3% | 7.6% | 10.0% |

### 4.8.16 Factors responsible for household health risk

Respondents were probed on about six (6) factors responsible for their households’ health risk and their responses are shown in Table 23. About 92.5% and 87.5% of the respondents reported that indiscriminate disposal of waste and pollution is the two topmost factors that put their households at health risk. Poor sanitation, poorly/non ventilated housing, lacks of access to health facility were other factors reported by 86%, 84% and 83% of the respondents respectively. While 76% of the respondents reported un-cleared bushes around the houses is responsible for their households’ health risk.

Table 22: Factors responsible for household health risk

| Factors | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Pollution (air water, land) | 16.5% | 17.8% | 17.3% | 17.2% |
| Poorly/Non ventilated housing | 18.3% | 14.4% | 16.7% | 16.5% |
| Poor sanitation/poor personal hygiene | 17.0% | 16.6% | 17.0% | 16.9% |
| Lack of access to health care facility | 16.4% | 16.3% | 16.2% | 16.3% |
| Indiscriminate disposal of waste | 17.8% | 19.4% | 17.4% | 18.2% |
| Uncleared bushes around the houses | 14.0% | 15.6% | 15.3% | 15.0% |

### 4.8.17 General health status of the respondents in the study area

The respondents who indicate that their general well-being is excellent were 10%, for those that indicated very good were 23.5%, 34.4% reported that their general well-being is good, 22% of the respondents indicated that their general well-being is fair, 7.5% of the respondents reported that their general health status is poor, while 2.5% revealed that their general health status is very poor.

Table 23: General Health Status of the respondents in the study area

| Variables | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| General well being | 8.7% | 12.3% | 10.0% | 10.3% |
| Very good | 24.6% | 21.5% | 23.5% | 23.2% |
| Good | 36.1% | 30.8% | 36.3% | 34.4% |
| Fair | 20.2% | 21.5% | 24.2% | 22.0% |
| Poor | 7.5% | 10.8% | 4.5% | 7.6% |
| Very poor | 2.9% | 3.1% | 1.5% | 2.5% |

### 4.8.18 Hygiene Practice of the Respondents

Findings on the hygiene practice of the respondents in the project communities are presented on Table 24. From the table there are 10 different hygiene practice/protocol practiced by the respondents in the community. Of these, 92.5%  of the respondents reported that they don’t handle food when they are infected with a diseases, 86.5%  revealed that they always wash their hands before preparing food, 84% showed that they cover their head while cooking food, 87% showed they preserve their food properly, 77.5%  attested that they always ensure that their drainage channels are always kept clean, 73.5% of the respondents showed that the dispose their waste properly, 75% of the respondents reported that they ensure the safety of their premises, 42.5% of the respondents said that they purify their water at home, while 2.5% of the respondents reported that they spend much money on water treatment at home.

Table 24: List of Hygiene Practice/Protocol Practiced by Respondents

| Statement | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| I don’t handle food when I am infected with disease | 16.3% | 17.0% | 17.1% | 16.8% |
| I always wash my hand before preparing food | 16.3% | 14.8% | 16.0% | 15.7% |
| I ensure the safety of my premises | 13.4% | 13.9% | 13.5% | 13.6% |
| I always cut grasses around my house | 11.3% | 11.7% | 11.0% | 11.3% |
| I properly dispose my wastes | 13.6% | 13.1% | 13.2% | 13.3% |
| I always ensure that my drainage channels are clean | 14.4% | 13.4% | 14.3% | 14.0% |
| I cover my head while cooking | 14.7% | 16.2% | 14.9% | 15.2% |
| I preserve my food properly | 15.5% | 16.2% | 15.8% | 15.8% |
| I purify my water at home | 7.7% | 7.2% | 8.3% | 7.7% |
| I spend much money on water treatment at home | 0.5% | 0.3% | 0.6% | 0.5% |

### 4.8.19 Types of Diseases Contracted by Respondents Households in the Past One Year

Table 25 reports the findings on types of diseases contracted by the households in the past one year. The result showed that malaria fever has the highest percentage of 57.5% as reported by the respondents, 15% of the respondent’s reported dysentery, 10% reported worm infestation, 7.5% reported typhoid fever, 5% attested that they contracted skin diseases, 2.5% reported cholera, 1.5% reported guinea worm infestation, while 0.5% reported contracting river blindness and STIs respectively. Health and wellbeing are very important component of human living, without it, it will be very difficult to live a normal life.

Table 25: Types of Diseases Contracted by the Household in the Past One Year

| Types of Disease | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| River blindness | 0.0% | 1.5% | 0.0% | 0.5% |
| Guinea worm | 1.5% | 1.5% | 1.5% | 1.5% |
| Malaria | 61.1% | 57.1% | 54.4% | 57.5% |
| Typhoid fever | 7.5% | 7.5% | 7.5% | 7.5% |
| Cholera | 2.5% | 2.5% | 2.5% | 2.5% |
| Dysentery | 13.1% | 18.3% | 13.6% | 15.0% |
| STIs | 0.5% | 0.5% | 0.5% | 0.5% |
| HIV/AIDS | 0.0% | 0.0% | 0.0% | 0.0% |
| Skin diseases | 5.0% | 5.0% | 5.0% | 5.0% |
| Worm infestations | 8.7% | 6.1% | 15.1% | 10.0% |

### 4.8.20 Number of Deaths recorded as Result of Contracting Diseases in the Past One Year

Results on Table 26 showed the number of deceased persons in the various communities of the respondents. The result showed that ten (10) persons died after contracting malaria, four (4) persons died from typhoid fever, one (1) person died after contracting cholera, and another one (1) also died after being infected with dysentery.

Table 26: Number of Deceased Persons Recorded after Contracting the Below Listed Diseases in the Past One Year.

| Diseases | Dagauda |  | Mashema |  | Yelwan Duguri |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | % | Deceased | % | Deceased | % | Deceased | % | Deceased |
| River blindness | 0.0% |  | 1.5% |  | 0.0% |  | 0.5% |  |
| Guinea worm | 1.5% |  | 1.5% |  | 1.5% |  | 1.5% |  |
| Malaria | 61.1% | 3 | 57.1% | 4 | 54.4% | 3 | 174.5% | 10 |
| Typhoid fever | 7.5% | 1 | 7.5% | 2 | 7.5% | 1 | 64.5% | 4 |
| Cholera | 2.5% | 1 | 2.5% |  | 2.5% |  | 26.9% | 1 |
| Dysentery | 13.1% |  | 18.3% |  | 13.6% | 1 | 15.0% | 1 |
| STIs | 0.5% |  | 0.5% |  | 0.5% |  | 0.5% | - |
| HIV/AIDS | 0.0% |  | 0.0% |  | 0.0% |  | 0.0% | - |
| Skin diseases | 5.0% |  | 5.0% |  | 5.0% |  | 5.0% | - |
| Worm infestations | 8.7% |  | 6.1% |  | 15.1% |  | 10.0% | - |

### 4.8.21 Age Group of Respondents Mostly Infected/Affected by Diseases

Findings in Table 27 from the survey showed the age group that were mostly infected/affected by diseases in the project community. The study revealed that 42.5% of the respondents that were infected/affected by diseases falls between the ages of zero to 5 years, 12.5% were between the ages of 21-25 years, 10% of the respondents that were mostly affected falls within the age bracket of 5 to 10 years, 8.5% of the respondents that were mostly affected falls within the ages of 16 to 20 years, 7.5% of the respondents were between the ages of 11 to 15 years and 26 to 30 years respectively, 6.5% of the respondents that were mostly affected by diseases falls within the ages of 31 to 35 years, while 5% of the respondents reported that most of the persons that were affected/infected by the diseases there were above 35 years of age.

Table 27: Age Group of Respondents Mostly Infected/Affected by Diseases

| Age group (Years) | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| 0-5 | 43.7% | 41.4% | 42.5% | 42.5% |
| 5-10 | 10.0% | 9.2% | 10.0% | 9.8% |
| 11-15 | 7.5% | 9.2% | 6.1% | 7.6% |
| 16-20 | 8.7% | 10.7% | 6.1% | 8.5% |
| 21-25 | 12.6% | 10.7% | 13.6% | 12.3% |
| 26-30 | 5.8% | 7.7% | 9.1% | 7.5% |
| 31-35 | 7.3% | 6.5% | 6.5% | 6.8% |
| Above 35 | 4.4% | 4.6% | 6.1% | 5.0% |

4.8.22 Substance Abuse

Substance abuse has become a very serious menace in various communities more especially among the youths in the society. Table 28 shows the substances commonly abused by people within the project community. About 32.5% of drugs abused in the community is tramadol, 16% abuse Kurkura (which is a stimulant), 15% abuse Zakami (which is a stimulant and tranquilizer), 11.5% abuse Snuff (Angur), 10% abuse Cannabis and Codeine respectively, while 5% abuse Rubber solution. This drugs that is been abused by persons in the community have a very serious medical effect on those that abuse it and it aids them to commit different types of criminal activity.

Table 28. Substances Commonly Abused by within the Community

| Substance(s) | Dagauda | Mashema | Yelwan Duguri | Total |
| --- | --- | --- | --- | --- |
| Cannabis | 11.6% | 10.0% | 7.6% | 9.7% |
| Codeine | 7.2% | 12.3% | 10.7% | 10.1% |
| Tramadol | 36.2% | 32.6% | 29.0% | 32.6% |
| Zakami | 13.0% | 15.0% | 16.8% | 15.0% |
| Kurkura | 16.0% | 12.3% | 19.8% | 16.1% |
| Snuff (Angur) | 11.5% | 11.5% | 11.6% | 11.5% |
| Rubber solution | 4.3% | 6.2% | 4.6% | 5.0% |

# CHAPTER FIVE: POTENTIAL IMPACTS AND MITIGATION MEASURES

## 5.1 Introduction

In this chapter, the environmental and social risks and impacts associated with the construction and upgrade of the three Model Primary Schools at Yelwan Duguri, Dagauda, and Mashema will be identified and evaluated in accordance with standard methodology.

## 5.2 Impact Assessment Approach and Methods

The broad approach (and methods) adopted for assessing the impacts of the proposed interventions is adapted from the International Organization for Standardization (ISO) 14001 requirements for risk and impact assessment as well as Environmental Management System Procedure (EMSP) Aspects and Impacts – Determining Significance developed by the University of Bristol in 2015.

The assessment was conducted by analyzing the data collected during the baseline study and applying professional judgement of the EIA team. The impact assessment process followed these key stages:

### 5.2.1 Impact Prediction or Identification:

This stage entails prediction of changes to the environment that could result from the proposed construction and installations at the selected facilities. The prediction of these changes is based on the identification of potential interactions between aspects/ activities of the project and the physical, biological, and social resources/receptors as follows:

- Physical: including air, surface water, groundwater, landscapes, soils, etc.;

- Biological: essentially terrestrial ecology (i.e. habitat, flora and fauna); and

- Human: including staff of the various facilities, residents of nearby communities, local economy, community health and safety etc.

### 5.2.1 Impact Characterization:

This entails characterizing/forecasting the nature, magnitude, extent, duration, frequency, and scale of the impacts. The characterization will essentially help determine the magnitude of impacts and degree of change the impact is likely to have on the receptor. The impact characterization further qualifies the impacts of the proposed project activities on the environment and people, as well as characterizes these impacts based on their nature, duration, scale, and reversibility.

Table 29: Impact categories used in this study

| Impact Parameters | Definition |
| --- | --- |
| Beneficial Impacts | Impacts with positive and beneficial effects. |
| Adverse Impacts | Impacts with negative and untoward effects. |
| Direct Impacts | Impacts that are most obvious result solely and are directly related to the proposed project and can be connected to the action that caused them. |
| Indirect Impacts | Secondary impacts that do not occur directly from a project activity but occur as consequence of the project |
| Cumulative Impacts | Impacts that typically occur from the incremental impact of an action when combine with impacts from projects that have been undertake recently of would be carried out soon |
| Reversible Impacts | Impacts over which the components involved can recover after the disturbances caused by the impact |
| Irreversible Impacts | Impacts whose effects are such that the affected environmental/socioeconomic component cannot be returned to its original state even after adequate mitigation measures are applied |
| Residual Impacts | Impacts whose effects remain after mitigation measures have been applied. |
| Short Term Impacts | Impacts which last only within the period of a specific project activity. |
| Long Term Impacts | Impacts which have their effects remain after a specific project activity. |

### 5.2.3 Impact Evaluation:

This entails determination of the significance of impacts based on the magnitude of impacts and the value, sensitivity/fragility, and recoverability of the affected receptors. This requires an in-depth appraisal of the attributes of potential receptors which has been carried out in the baseline studies and documented in this Chapter. The evaluation is done by using the Risk Assessment Matrix (RAM). The risks of the impacts occurring were analyzed by determining the consequence/severity of the impacts and the probability of occurrence. The severity of the consequences was determined using a Consequence Severity Table and the probability of an impact resulting from a pathway was determined with a Likelihood Ranking Table. The RAM was then used to determine the level of risk and the significance or otherwise of the impacts.

Table 30: Probability of Impact Occurrence

| Probability | Attributes |
| --- | --- |
| Certain | Impacts that can reasonably be expected to occur during the project |
| Likely | Impacts that are likely to occur during the project |
| Possible | Impacts that might occur sometime during the project |
| Unlikely | Impacts that can reasonably be expected NOT to occur during the project |
| Rare | Impacts that are unlikely to occur except in exceptional circumstances |

Table 31: Consequence and Severity of Impacts

| Severity | Attributes |
| --- | --- |
| Negligible | No detectable environmental and socio-economic impact |
| Marginal | Minimum environmental and socio-economic impact. Localized reversible habitat loss or minimal long-term effects on habitat species or media/public health and safety |
| Critical | Significant environmental & socio-economic harm. Significant widespread & persistent changes in species, habitat, and media (e.g., widespread habitat degradation/public health and safety) |
| Catastrophic | Detrimental environmental and socio-economic impact. Loss of a significant portion of a valued species of effective ecosystem function on a landscape scale injury and death is possible |

Table 32: Risk Assessment Matrix

|  |  |  |  | Severity |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Probability |  | Negligible | Marginal | Critical | Catastrophic |
|  | Certain |  |  |  |  |  |
|  | Likely |  |  |  |  |  |
|  | Possible |  |  |  |  |  |
|  | Unlikely |  |  |  |  |  |
|  | Rare |  |  |  |  |  |

Table 33: Impact Rating

| Impact Rating | Impact Description |
| --- | --- |
| Low | Low Risk: No response plans will be needed for these risks. |
| Medium | Medium Risk: Actions may be required to control acceptable risk. |
| High | High Risk: Adequate action and management attention are required to control |
| Extreme | Extreme Risk: Significant additional action and high priority management attention will be required to control risk. There is need for an in-depth response plan for these risks |

Based on the evaluation methodology described above, the potential and associated impacts associated with the project are evaluated in the impact assessment matrix in Table 34 below:

| Table 34 Impact Assessment Matrix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Impact Quantification |  |  |  |  |  |  |  |  |  |  | Risk |  |
| Project Activity | Potential Impact | Direct | Indirect | Reversible | Irreversible | Cumulative | Long-term | Short-term | Beneficial | Adverse | Residual | Probability |  | Impact Category |
| Pre-construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site clearing and preparation | Air quality deterioration from release of dusts and gaseous emissions from exposed soil surfaces and vehicles Occupational accidents and injuries to workers and risk to community health and safety Noise and vibration from the use of machineries and motorized equipment Loss of vegetation cover due to clearing of project site Reduction in carbon sequestration in the project area due to removal of trees Disturbance/Destruction of flora and fauna habitat and loss of fauna due to site clearing including susceptibility of plants to pathogenic infections due to mechanical bruises Increase in amounts of fugitive dust, exhaust fumes and GHGs from movement of heavy-duty vehicles and equipment into work areas Noise and vibration from movement of heavy-duty vehicles Landscape disruption and visual intrusion | X |  | X |  |  | X |  |  | X |  | Certain | Marginal | High |
| Mobilization of equipment, machinery, and heavy-duty vehicles | Movement of heavy-duty vehicles transporting personnel, equipment and materials to site Fugitive dusts and vehicular exhaust emissions Noise & Vibration Generation Stationary positioning of heavy-duty vehicles and equipment Increased risk of social unrest if construction workers are not recruited from the local community Increased risk of social unrest if construction workers are not recruited from the local community Landscape disruption and visual intrusion due to presence of equipment, vehicles and trucks Risks of accidents from struck-by injuries to workers from the movement of heavy-duty vehicles Risks of Gender Based Violence (GBV)/Sexual Exploitation Abuse (SEA) resulting from the interaction between contractors and members of the communities Disruption of traffic flow and increased risk of Road Traffic Accidents (RTAs) due to movement of heavy-duty vehicles. Risk of security breaches and threat to lives and properties due to storage of materials and equipment on site Presence of valuable assets on site Respiratory and eye related problems in residents of surrounding communities from exposure to fugitive dusts Engagement of local staff Soil compaction and increased susceptibility to erosion as a result of operation and stationary positioning of heavy-duty vehicles | X |  | X |  | X |  | X |  | X |  | Possible | Marginal | Medium |
| Mobilization of workers to site | Unauthorized movements of construction workers, construction equipment, machinery, and heavy-duty vehicles (during and after working hours) could result in trespassing Damage to local land and property and invasion of privacy of local residents Disparity of pay, increase in disposable income and potential availability of illegal substances, illicit or culturally inappropriate lifestyle choices, leading to increased tension between local communities and the workers. Increasing incidents of crime and or violence and threats to the safety of local community members. Occupational accidents and injuries to workers and risk to community health and safety Exposure to communicable diseases | X |  | X |  | X |  | X |  | X |  | Possible | Marginal | Medium |
| Supply of materials – cement, sand, pipes, planks etc. | Traffic congestion and risk of road traffic Occupational accidents and injuries to workers and risk to community health and safety | X |  | X |  | X |  | X |  | X |  | Possible | Marginal | Medium |
| Installation of temporary structures for workers including storage area, water supply system, electricity, sanitation and waste disposal are as etc. | Noise and vibration disturbances in surrounding communities from the use of machineries and motorized equipment. Generation of hazardous and non-hazardous wastes from construction activities. Soil contamination from indiscriminate dumping of hazardous wastes. Risk of occupational accidents and injuries to workers | X |  | X |  | X |  | X |  | X |  | Possible | Marginal | Medium |
| CONSTRUCTION PHASE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Excavation for foundations of new buildings | Deterioration of local air quality due to the release of fugitive dusts from excavation for foundations of new buildings Noise and vibration from construction equipment, traffic and activities, may disturb sensitive noise receptors (i.e. humans). Loss, damage, erosion, and disruption of soil from exposure of soil surfaces to rain and wind. Real or perceived disruption to normal operational life of the facilities, through the physical presence of a workforce. Direct employment of local population in workforce and stimulation of local economy Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems, and result in conflicts over water use. Inefficient estimation of materials during construction leading to excess consumption of materials, generation of wastes/emissions, pollution of soils and water. Increased respiratory and eye related problems from exposure to dusts and gaseous emissions. |  |  |  |  |  |  |  |  |  |  | Possible | Marginal | Medium |
| Roofing of new building and installation of internal and external finishing materials as well as painting | Increased noise level within the environment as a result of roofing works Generation of Hazardous waste like paint cans and other aerosols Generation of non-hazardous waste from other material packages | X |  | X |  | X |  | X |  | X |  | Possible | Marginal | Moderate |
| OPERATIONAL PHASE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site Operation activities | Generation of solid waste from the usage of renovated and new buildings Generation of Hazardous waste streams like used batteries, used solar panels, fluorescent tubes and spent oil, Generation of increased medical waste as the interventions will improve, utilization of the facilities | X |  | X |  | X |  | X |  | X |  | Likely | Marginal | Moderate |
| Commissioning of Community Town Hall | Generation of construction waste and debris | X |  | X |  | X |  | X |  | X |  | Possible | Marginal | Moderate |
| DECOMMISSIONING PHASE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Occupational/ public safety and traffic impacts | The relocation of all construction facilities and remaining materials including concrete mixers, trucks, and water tanks to new sites or the contractor’s office could result in accidents and injury to workers. The removal and transport of such equipment and materials could also pose traffic risks and public safety concerns within the schools and along the routes. | X |  | X |  | X |  | X |  | X |  | Possible | Marginal | Moderate |
| Waste management | The dismantling and removal of equipment and materials at the site, as well as landscape restoration works could generate waste such as scraps of metal, wood, concrete debris, vegetative material, and garbage (pieces of plastic bags, food wrappers, etc.). | X |  | X |  | X |  | X |  | X |  | Likely | Marginal | Moderate |

## 5.3 Identification of Environmental and Social (E&S) Impacts

The E&S impacts were identified by assessing the interactions of the environmental aspects of project activities and the environmental (and social) receptors in the project area of influence during the pre-construction, construction, and operational phases of the project. The prediction of impacts is based on the linkages (the source-pathway-receptor approach) among project activities, aspects, and receptors. The significance of these impacts was determined by assessing the value, sensitivity, and importance of the receptors to these impacts. The mitigation measures were then proffered based on these findings.

### 5.3.1 Potential Positive Environmental Impacts

The project is envisaged to generate some positive impacts that would be beneficial to the project communities, LGAs, Bauchi State and the Country in general. The potential positive environmental impacts identified are as shown in Table 35.

Table 35: Identified Positive Impacts of Proposed interventions at selected facilities

| No. | Impact | Key receptor(s) | Evaluation | Evaluation |
| --- | --- | --- | --- | --- |
| 1 | Improved access to improved school infrastructure in the communities and overall educational development. | Communities | The proposed project when completed will deliver these benefits: Better access to quality education in the communities | Direct and Positive |
| 2. | Employment generation | Community members | The proposed project activities will create employment opportunities for skilled and unskilled labour during the construction and operational stages. In addition, indirect employment opportunities such as food vendors, petty traders and suppliers of raw materials for construction will be created. During the operational phase, job opportunities will be created for maintenance workers and suppliers, waste management companies, etc. | Direct and Positive |
| 3. | Improvement in local and national economy | Neighboring communities, LGAs and national economy | The creation of direct and indirect job opportunities during the construction and operational phases of the project will boost the local and national economy | Direct and Positive |
| 4. | Community cohesion | Bauchi State Government, LGAs (Alkaleri, Dambam and Itas/Gadau) | Improvement of public goodwill and satisfaction towards governance in Bauchi State. | Direct and Positive |
| 5. | Improvement in management of resources | Neighboring communities, State Government, MDAs | Provision of a lead way to drive the State Government towards ensuring improved infrastructure | Direct and Positive |
| 6. | Capacity building and strengthening of institutions | State Government, MDAs | Capacity building through: Strengthening of facility rehabilitation works and supervision systems of personnel involved in the project activities, including improvement in institutional responsibilities for construction and maintenance. Skills transfer | Direct and Positive |

### 5.3.2 Potential Negative Environmental Impacts

The project is envisaged to generate some negative impacts that may adversely affect the project communities and environment. The potential negative environmental and social impacts identified are as shown in Table 36

Table 36: Identified Negative Impacts of Proposed interventions at selected facilities

| Project Phase and Activities | Environmental Aspect | Environmental Receptor | Associated and Potential Impacts | Evaluation |
| --- | --- | --- | --- | --- |
| Mobilization of equipment, machinery, and heavy-duty vehicles | Movement of heavy-duty vehicles transporting personnel, equipment and materials to site Fugitive dusts and vehicular exhaust emissions Noise & Vibration Stationary positioning of heavy-duty vehicles and equipment Presence of valuable assets on site Engagement of local staff | Surrounding Communities, Air, Soil, Flora and Fauna, Project Workers | Movement of heavy-duty vehicles transporting personnel, equipment and materials to site Fugitive dusts and vehicular exhaust emissions Noise & Vibration Generation. Stationary positioning of heavy-duty vehicles and equipment Increased risk of social unrest if construction workers are not recruited from the local community Increased risk of social unrest if construction workers are not recruited from the local community Landscape disruption and visual intrusion due to presence of equipment, vehicles and trucks Risks of accidents from struck-by injuries to workers from the movement of heavy-duty vehicles Risks of Gender Based Violence (GBV)/Sexual Exploitation Abuse (SEA) resulting from the interaction between contractors and members of the communities Disruption of traffic flow and increased risk of Road Traffic Accidents (RTAs) due to movement of heavy-duty vehicles. Risk of security breaches and threat to lives and properties due to storage of materials and equipment on site Presence of valuable assets on site Respiratory and eye related problems in residents of surrounding communities from exposure to fugitive dusts. Engagement of local staff Soil compaction and increased susceptibility to erosion as a result of operation and stationary positioning of heavy-duty vehicles | Low-Medium, Direct, Short-term and Local |
| Mobilization of workers to site | Movement of heavy-duty vehicles transporting personnel, equipment and materials to site Fugitive dusts and vehicular exhaust emissions | Surrounding communities, Air, Soil, Flora and Fauna, Project Workers | Unauthorized movements of construction workers, construction equipment, machinery, and heavy-duty vehicles (during and after working hours) could result in trespassing Damage to local land and property and invasion of privacy of local residents Disparity of pay, increase in disposable income and potential availability of illegal substances, illicit or culturally inappropriate lifestyle choices, leading to increased tension between local communities and the workers. Increasing incidents of crime and or violence and threats to the safety of local community members. Occupational accidents and injuries to workers and risk to community health and safety Exposure to communicable diseases | Medium, Direct, Short-term, Local |
| Supply of materials – cement, sand, pipes, planks etc | Noise & Vibration Generation | Air, Land, Workers | Traffic congestion and risk of road traffic Occupational accidents and injuries to workers and risk to community health and safety | Medium, Direct, Short-term |
| Site clearing and preparation | Clearing of land for new construction | Surrounding communities, vegetation, soil, air and water, | Air quality deterioration from release of dusts and gaseous emissions from exposed soil surfaces and vehicles. Occupational accidents and injuries to workers and risk to community health and safety Noise and vibration from the use of machineries and motorized equipment Loss of vegetation cover due to clearing of project site Reduction in carbon sequestration in the project area due to removal of trees Disturbance/Destruction of flora and fauna habitat and loss of fauna due to site clearing including susceptibility of plants to pathogenic infections due to mechanical bruises Increase in amounts of fugitive dust, exhaust fumes and GHGs from movement of heavy-duty vehicles and equipment into work areas Noise and vibration from movement of heavy-duty vehicles Landscape disruption and visual intrusion | High, Direct, Long-term |
| Installation of Temporary Structures for workers including storage area, water supply system, electricity, sanitation and waste disposal areas etc. | Waste Generation Noise and Vibration Generation Installation of Site Structures | Affected communities, Workers, Soil and Land | Noise and vibration disturbances in surrounding communities from the use of machineries and motorized equipment. Generation of hazardous and non-hazardous wastes from construction activities. Soil contamination from indiscriminate dumping of hazardous wastes. Risk of occupational accidents and injuries to workers | Medium, Short-term, Direct |
| CONSTRUCTION PHASE |  |  |  |  |
| Excavation for foundations of new buildings |  | Air, Soil, Communities | Deterioration of local air quality due to the release of fugitive dusts from excavation for foundations of new buildings Noise and vibration from construction equipment, traffic and activities, may disturb sensitive noise receptors (i.e. humans). Loss, damage, erosion, and disruption of soil from exposure of soil surfaces to rain and wind Real or perceived disruption to normal operational life of the facilities, through the physical presence of a workforce. Direct employment of local population in workforce and stimulation of local economy Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems, and result in conflicts over water use. Inefficient estimation of materials during construction leading to excess consumption of materials, generation of wastes/emissions, pollution of soils and water. Increased respiratory and eye related problems from exposure to dusts and gaseous emissions. | Medium, Direct, Short-term |
| Earthworks and concrete works including floor paving and Fencing | Engagement of local staff | Air, Soil, Communities |  | Medium, Direct, Short-term |
| Roofing of renovated and new building and installation of internal and external finishing materials as well as painting | Noise level Waste Generation Engagement of local workers | Air, Water, Soil, People | Increased noise level within the environment as a result of roofing works Generation of Hazardous waste like paint cans and other aerosols Generation of non-hazardous waste from other material packages | Low, Direct, Short-term |
| Renovation of existing structures | Noise Generation of waste Disturbance to facility | Air, Land, Water, People | Generation of noise from removal and replacement of materials during renovation Generation of Hazardous and Non-Hazardous waste during renovation Disruption of the activities at the facilities as a result of renovation of existing structures | Low, Direct, Short-term |
| OPERATIONAL PHASE |  |  |  |  |
| Site Operation activities | Waste Generation (Including Health Care Wastes | Air, Water, Soil, People | Generation of solid waste from the usage of renovated and new buildings Generation of Hazardous waste streams like used batteries, used solar panels, fluorescent tubes and spent oil, Generation of increased medical waste as the interventions will improve, utilization of the facilities | Medium, Direct, Short-term |
| Commissioning of model primary school Facilities | General construction wastes | Air, Water, Soil, Workers, Communities | Generation of construction waste and debris | Medium, Direct, Short-term |
| Demobilization Phase |  |  |  |  |
| Occupational/ public safety and traffic impacts | Risk of public safety | Workers, pupils, teachers, public | The relocation of all construction facilities and remaining materials including concrete mixers, trucks, and water tanks to new sites or the contractor’s office could result in accidents and injury to workers. The removal and transport of such equipment and materials could also pose traffic risks and public safety concerns within the schools and along the routes. | Medium, Direct, Short-term, Local |
| Waste management | Generation of waste materials | Workers, pupils, teachers, public | The dismantling and removal of equipment and materials at the site, as well as landscape restoration works could generate waste such as scraps of metal, wood, concrete debris, vegetative material, and garbage (pieces of plastic bags, food wrappers, etc.). | Medium, Direct, Short-term, Local |
| Demobilization Phase |  |  |  |  |
| Occupational/ public safety and traffic impacts | Risk of public safety | Workers, pupils, teachers, public | The relocation of all construction facilities and remaining materials including concrete mixers, trucks, and water tanks to new sites or the contractor’s office could result in accidents and injury to workers. The removal and transport of such equipment and materials could also pose traffic risks and public safety concerns within the schools and along the routes. | Medium, Direct, Short-term, Local |
| Waste management | Generation of waste materials | Workers, pupils, teachers, public | The dismantling and removal of equipment and materials at the site, as well as landscape restoration works could generate waste such as scraps of metal, wood, concrete debris, vegetative material, and garbage (pieces of plastic bags, food wrappers, etc.). | Low-Medium, Direct, Short-term, Local |

# CHAPTER SIX: MITIGATION AND ENHANCEMENT MEASURES

## 6.1	Introduction

This Chapter proffers technically and financially feasible mitigation measures to the impacts identified and evaluated in chapter five. The recommended mitigation measures are suitable to the nature and magnitude of the potential impacts taking into cognisance the peculiarity of the proposed project and activities as well as environmental and social condition of the project area.

## 6.2	Mitigation Approach

This project is envisaged to generate both positive and negative impacts on the biophysical and socioeconomic environment. However, the negative impacts anticipated will be localized in spatial extent, short in duration and can be reduced through compliance with appropriate mitigation measures. In this section, technically and financially feasible mitigation measures will be proffered to address environmental and social impacts associated with the construction and upgrade of Model Primary Schools in Dambam, Mashema, and Yelwan Duguri in Bauchi State. The mitigation measures recommended are commensurate with the nature and magnitude of the potential impacts taking into cognisance the peculiarity of the proposed project and activities as well as the environmental and social setting of the project area.

The approach adopted for selecting appropriate mitigation measures is based on the mitigation hierarchy which favours the avoidance of impacts over minimization, and where residual impacts remain, compensate/offset for impacts to workers, affected communities and the environment.

- Avoidance: To avoid the impact altogether by not using certain type of resources, or areas considered to be environmentally sensitive nor taking certain actions or parts of an action that could result in negative impacts. This is considered to be the most acceptable form of mitigation.

- Minimization: To minimize impacts by limiting or reducing the degree, extent, magnitude or duration of adverse impacts. Negative impacts can be minimized through environmental and social measures/treatments/design. Available options to minimize negative impacts include abate, rectify, repair, and/or restore.

- Compensation: To compensate for the impact by replacing or providing substitute resources especially for unavoidable and residual impacts. This does not eliminate the adverse impact but seeks to offset it with an (at least) comparable positive one.

## 6.3 Mitigation and Enhancement Measures

A summary of all identified impacts as well as the proposed mitigation measures is presented in Table 37.

| Table 37: Proposed mitigation measures |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Phase and Planned Activities | Associated and Potential Impacts | Pre mitigation (Significance) | Mitigation Measures | Post Mitigation Significance) | Residual Impacts Significance |
|  | Pre-Construction Phase |  |  |  |  |
| Mobilization of personnel, equipment and materials to project sites | Deterioration of local air quality due to the release of fugitive dusts and gaseous pollutant emissions from heavy duty vehicles transporting personnel, equipment and materials to site | Medium | Implement Dust control and suppression measures, such as use of dampening and wetting. Use of modern equipment meeting appropriate emissions standards, and regular preventative maintenance. Encourage increased fuel efficiency in project vehicles (e.g. selection of fuel in order to minimize harmful emissions. Avoiding the use of ozone depleting substances during construction. | Low | Low |
|  | Noise and vibration disturbances from movement of heavy-duty vehicles | Medium | Use of noise barriers to screen receptors, e.g. with berms or bunds. Use of modern, well-maintained equipment fitted with abatement devices (e.g. mufflers, noise enclosures) Strict controls of timing of activities e.g. blasting and other high noise emissions; prohibit work during the night if possible | Low | Low |
|  | Soil compaction and increased susceptibility to erosion as a result of operation and stationary positioning of heavy-duty vehicles | Medium | Avoidance of areas liable to flooding, slope instability, and water crossings where possible Retention of topsoil for restoration (including tilling and Re-vegetation) as soon as practicable. | Low | Low |
|  | Disturbance and displacement of terrestrial fauna as a result of noise and vibration from heavy duty vehicles. | Medium | Observance of seasonal sensitivities (e.g. breeding seasons), and alteration of activity to reduce noise levels at that time | Low | Low |
|  | Disruption of traffic flow and increased risk of road traffic accidents (RTAs) due to movement of heavy-duty vehicles. | Medium | Develop and implement a traffic management plan covering materials delivery as well as all project vehicles | Low | Low |
|  | Increase in revenue and job creation | Medium | Give priority to local people who have expertise in works required and patronize local businesses during interventions | Low | Low |
|  | Security breaches and threat to lives and properties due to storage of materials and equipment on site. | Medium | Develop a security management plan and work with relevant agencies to secure lives and properties within the project environment | Low | Low |
|  | Respiratory and eye related problems in residents of surrounding communities from exposure to fugitive dusts. | Medium | Implement Dust control and suppression measures, such as use of dampening and wetting | Low | Low |
|  | Landscape disruption and visual intrusion due to presence of equipment, vehicles and trucks | Medium | Rehabilitation of trampled areas with native species, and ecosystem restoration in habitats of conservation value, using specialist advice and input, backed up by a long-term monitoring programme and corrective actions as necessary. | Low | Low |
|  | Risks of Gender Based Violence (GBV)/Sexual Exploitation Abuse (SEA) resulting from the interaction between contractors and members of the communities | Medium | Develop and Implement Code of Conduct for workers that specifically prohibit GBV and SEA Create partnership with local NGO to report workers’ misconduct and complains on Gender Based Violence | Low | Low |
|  | Disruption of traffic flow and increased risk of Road Traffic Accidents (RTAs) due to movement of heavy-duty vehicles. | High | Ensure that heavy duty trucks and major haulage are done during traffic off-peak periods to reduce the possibility of Road Traffic Accidents | Low | Low |
|  | Risks of accidents from struck-by injuries to workers from the movement of heavy-duty vehicles | High | Train drivers driving project’s heavy-duty trucks on evasive and defensive driving to avoid accidents at all time | Low | Low |
| Site Preparation | Deterioration of local air quality due to the release of fugitive dusts and gaseous pollutant from vegetation clearance, soil disturbance and heavy-duty vehicles | Medium | Implement Dust control and suppression measures, such as use of dampening and wetting | Low | Low |
|  | Noise and vibration disturbances from operation of earth moving equipment | Medium | Use of noise barriers to screen receptors, e.g. with berms or bunds. Use of modern, well-maintained equipment fitted with abatement devices (e.g. mufflers, noise enclosures) Strict controls of timing of activities e.g. blasting and other high noise emissions; prohibition on night working if possible | Low | Low |
|  | Loss, damage, erosion and disruption of soil from exposure of soil surfaces to rain and wind. | Low | Minimize areas exposed to what is required for construction or pavement. Retention of topsoil for restoration (including tilling and re-vegetation) as soon as practicable. Earthworks to be designed to achieve a balance between cut and fill wherever possible. | Low | Low |
|  | Waste generation from accumulation of cleared vegetal materials and spoils. | Medium | Ensure that all wastes are managed by authorized waste management contractor. | low | Low |
|  | Construction Phase |  |  |  |  |
| installation of internal and external finishing materials as well a painting | Interaction between workforce and local communities may increase occurrence of communicable diseases, including HIV/AIDS and sexually transmitted diseases (STDs). | Medium | Training and awareness raising for workforce and their dependents on HIV/AIDS and other STDs, and communicable diseases including malaria; health awareness raising campaigns for communities on similar health issues Provision of opportunities for workers to regularly return to their families. | Low | Low |
|  | Poor management of occupational health and safety leading to accidents, injuries and illnesses among workers | High | Develop and Implement HSE Plan to cater for proper management of Occupational Health and Safety. | Low | Low |
|  | Increased noise level within the environment as a result of roofing works | Medium | Provide noise attenuator for workers and restrict such works to times when it will create lesser nuisance to people | Low | Low |
|  | Generation of noise from removal and replacement of materials during renovation | High | Provide noise attenuator for workers and restrict such works to times when it will create lesser nuisance to people | Low | Low |
|  | Generation of Hazardous waste like paint cans and other aerosols | High | Dispose all waste through licensed waste management contractor | Low | Low |
|  | Generation of non-hazardous waste from other material packages | High | Same as above | Low | Low |
|  | Operational Phase |  |  |  |  |
| Operations and Usage of intervention’ physical component | Generation of solid waste from the usage of renovated and new buildings | High | Preparation of Waste Management Plan following the waste hierarchy, supported by staff training. | Low | Low |
|  | Generation of Hazardous waste streams like used batteries, used solar panels, fluorescent tubes and Spent oil | High | Use of authorized contractors for hazardous and any other wastes which the project cannot dispose of safely | Low | Low |
|  | Intervention will increase utilization of facilities which will in turn increase medical waste | High | Ensure that medical waste is managed by authorized waste management contractors | Low | Low |
|  | Use of generators Soil contamination (from accidental diesel/lubricant spills), Occupational health issues etc. all need to be assessed. | High | Deterioration of local air quality due to emission from generators Noise and vibration from generators, may disturb sensitive noise receptors (i.e. humans). Soil pollution from generator house | Low | Low |
|  | Congestion if too many staff are recruited Potential water shortage | High | Risks of accidents, incidents and near misses from use of healthcare facilities, vehicles and equipment Disruption to normal operational life of the facilities, through the physical presence of too many staff. Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems, and result in conflicts over water use. | Low | Low |
|  | Demobilization Phase |  |  |  |  |
| Occupational/ public safety and traffic impacts | The relocation of all construction facilities and remaining materials including concrete mixers, trucks, and water tanks to new sites or the contractor’s office could result in accidents and injury to workers. The removal and transport of such as equipment and materials could also pose traffic risks and public safety concerns within the schools and along the routes. | High | Develop and Implement HSE Plan to cater for proper management of Occupational Health and Safety. | Low | Low |

# CHAPTER SEVEN: ENVIRONMENTAL AND SOCIAL MANAGEMENT AND MONITORING PLAN (ESMMP)

## 7.1	Introduction

This chapter presents the Environmental and Social Management and Monitoring Plan (ESMMP) for the construction of model primary schools at Dambam, Mashema and Yelwan Duguri of Bauchi State. This ESMP is a proactive tool that will ensure seamless integration of action plans and programmes for overall management of all identified (and unidentified) impacts of the proposed projects.

The overarching objective of the ESMP is to ensure that all potential impacts of the project are contained and brought to an acceptable level to guarantee economic, environmental, and social sustainability of the projects.

The ESMP has been developed to meet international and national standards on environmental and social (E&S) performance and covers the project implementation phases (i.e. Pre-construction, construction, operation and demobilization phases) of the project. Furthermore, it details the mitigation and enhancement measures that Bauchi State government and their Contractors will be committed to implement throughout project life cycle as well as desired outcomes, performance indicators, monitoring, timing for actions and responsibilities.

The IBSDELIP PIU shall have principal responsibility for implementation of all measures outlined in this ESMP but will delegate certain responsibilities to its contractors. Such delegation of responsibility shall be adequately documented as part of contractual agreements to guarantee absolute compliance and commitment on the part of the contractors to implement the ESMP. Consequently, the contractor shall prepare a Contractor Environmental Management Plan (C-ESMP) from this ESMP to guide implementation.

## 7.2	Environmental and Social Impacts and Mitigation (ESMP)

The significant potential E&S impacts for which management actions are required have been identified in Chapter 5 of this Report. The feasible, practical and cost-effective measures and actions to avoid, minimize, mitigate the potentially significant negative E&S impacts of the project to acceptable levels and enhance positive impacts (effectively the ESMP) are also described in Chapter 6 of this Report. The mitigation measures mainly relate to the adoption of environmentally friendly designs and the application of sound construction and operations management practices. The detailed Environmental, Social Management and Monitoring Plan is shown in Table 38 a (management plan) b (monitoring plan).

Table 34a: Environmental, Social Management and Monitoring Plan Matrix

| Project Activity | Associated and Potential Impacts | Mitigation Measures | Responsibility for Mitigation | Cost of Mitigation (=N=) |
| --- | --- | --- | --- | --- |
| Pre-construction Phase |  |  |  |  |
| Mobilization of equipment and materials to project sites | Deterioration of local air quality due to the release of fugitive dusts and gaseous pollutant emissions from heavy duty vehicles transporting personnel, equipment and materials to site. | Use water to wet ground for dust suppression. Enforce appropriate speed limit to reduce dust on unpaved surfaces. Train drivers/ workers on proper operation of vehicles& equipment to include fuel efficiency and anti-idling techniques | Contractor | 800,000 |
| Site Preparation and Clearing | Deterioration of local air quality due to the release of fugitive dust and gaseous pollutant from vegetation clearance, soil disturbance, and heavy-duty vehicles. | Use water to wet ground for dust suppression, Enforce appropriate speed limit to reduce dust on unpaved surfaces, Train drivers/ workers on proper operation of vehicles & equipment to include fuel efficiency and anti-idling techniques. | Contractor | 200,000 |
|  | Risk of occupational accidents and injuries to workers | Provide adequate first aid, first aiders, PPE, signages (in English and local languages), lighting and/or reflective tapes, engineering barriers eg, fencing to ensure safety, restrict unauthorized access to all areas of high-risk activities, collaborate with host health facilities for treatment in case of any injury | Contractor | 500,000 |
| Construction/Installation of Temporary Structures including storage area, water supply system, electricity, sanitation and waste disposal areas etc. | Noise and vibration disturbances in surrounding communities, | Same as above | Same as above | Same as above |
|  | Generation of hazardous and non-hazardous wastes from construction activities. | Same as above | Same as above | Same as above |
|  | Risk of occupational accidents and injuries to workers | Same as above | Same as above | Same as above |
|  |  | Sub-Total |  | 5,600,000 |
| Construction Phase |  |  |  |  |
| Excavation for foundations of new buildings | Deterioration of local air quality due to the release of fugitive dust and gaseous pollutant from vegetation clearance, soil disturbance, and heavy-duty vehicles. | Use water to wet ground for dust suppression. Enforce appropriate speed limit to reduce dust on unpaved surfaces. Train drivers/ workers on proper operation of vehicles& equipment to include fuel efficiency and anti-idling techniques | Contractor | 1,000,000 |
| Earthworks and concrete works including floor paving and fencing | Noise and vibration from construction equipment, traffic and activities may disturb sensitive noise receptors (i.e humans) | Select and use vehicles/equipment with lower sound power levels, install suitable mufflers on engine exhausts and compressors, Respond promptly to noise complaints | Contractor | - |
|  | Loss, damage, erosion and disruption of soil from exposure of soil surfaces to rain and wind | Ensure construction of effective drainage system and use erosion protection structures such as sediment traps, riprap, gabions, etc. | Contractor | 500,000 |
|  | Real or perceived disruption to normal operational life of the facilities, through the physical presence of a workforce | Create another access to the areas where new buildings are being built to avoid disruption of activities at the facilities, where renovation is to be done, sectionalize the work to allow smooth running of the facilities | Contractor |  |
|  | Potential for conflicts over usage of community amenities by workers | Ensure priority recruitment of local labour, ensure workers camp are equipped with all essential services (water, sanitary facilities, electricity etc), | Contractor | 1,000,000 |
|  | Direct employment of local population workforce and stimulation of local economy | Ensure construction works are targeted toward local people | Contractor | - |
|  | Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems and result in conflicts over water use | Where enough water is not available, use commercial sources to supplement during construction, avoid total dependency solely on the existing waste supply infrastructure at the facilities | Contractor | 500,000 |
|  | Inefficient waste management during construction leading to excess consumption of materials, generation of wastes/emissions, pollution of soils/water. | Ensure waste is evacuated from site by approved waste contractors to prevent unregulated dumping | Contractor | 1,000,000 |
|  | Increased respiratory and eye related problems from exposure to dusts and gaseous emissions | Provide appropriate PPEs and enforce usage | Contractor | - |
|  | Poor construction management practices may lead to adverse effects on safety, human health and wellbeing | Provide adequate first aid, first aiders, PPE, signages (in English and Local languages), lighting and/or reflective tapes, engineering barriers e.g fencing to ensure safety, restrict unauthorized access to all areas of high-risk activities, Collaborate with host health facilities treatment in case of any injury | Contractor | - |
|  | Interaction between workforce and local communities may increase occurrence of communicable diseases, including HIV/AIDS and sexually transmitted diseases (STDs) | Vaccinating workers against common diseases, Implementation of HIV/AIDS education program, Campaign on STDs and transmission among workers and local communities, Provision of condoms to workers, Raising awareness of local communities about the impacts of labour influx | PIU | 500,000 |
|  | Differences in ethnicity, religion etc. may lead to discrimination and harassment and differences (perceived or real) in working conditions between workers may lead to resentment | Ensure priority recruitment of local labour, provide information regarding workers Code of Conduct in English and Yoruba, Provide cultural sensitization training for workers regarding engagement with local community, Consultations with and involvement of local communities in project planning and implementation | Contractor | 200,000 |
| Roofing of renovated and new building and installation of internal and external finishing materials as well as painting | Increased noise level within the environment as a result of roofing works | Provide PPEs for workers and restrict such works to times when it will create lesser nuisance to people e.g weekends | Contractor | 500,000 |
| Renovation of existing structures | Generation of hazardous waste like paint cans, aerosols and material packages | Implement WMP following the waste hierarchy, conduct staff training, use licensed hazardous waste management contractors to evacuate and treat the wastes | Contractor |  |
|  | Disruption of the activities at the facilities as a result of renovation of existing structures | Where renovation is to be done, sectionalize the work to allow for smooth running of the facilities | Contractor |  |
|  |  | Sub-Total |  | 5,200,000 |
| Operational Phase |  |  |  |  |
| General Operational activities | Generation of solid waste from the usage of renovated and new buildings | Implement WMP | school | Part of operational cost |
|  | Generation of hazardous wastes streams like used batteries, used solar panels, fluorescent tubes and spent oils etc. | Implement WMP | School | Part of operational cost |
|  |  | Sub-Total |  | - |
| Grand -Total |  |  |  | 10,800,000 |

Table 37b: Monitoring Plan

| Associated and Potential Impacts | Parameters to be measured | Methods of measurement | Performance Indicators | Sampling Location | Frequency of Monitoring | Responsibility for Monitoring | Cost of Monitoring (=N=) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pre-construction Phase |  |  |  |  |  |  |  |
| Deterioration of local air quality due to the release of fugitive dusts and gaseous pollutant emissions from heavy duty vehicles transporting personnel, equipment and materials to site. | Air quality parameters (CO, NO2, SO2, CO2, SPM) | In-situ measurements, visual observations of records and interviews | Compliance with national air quality standards | Project sites, Road corridor and adjoining communities | Weekly during pre-construction | Env and Social Safeguards Officer (ESSO), FMEnv, BASMEnv | 1,000,000 |
| Deterioration of local air quality due to the release of fugitive dust and gaseous pollutant from vegetation clearance, soil disturbance, and heavy-duty vehicles. | Air quality parameters (CO, NO2, SO2, CO2, SPM) | In-situ measurements, visual observations of records and interviews | Compliance with national air quality standards | Road corridor and adjoining communities | Weekly during pre-construction | Env and Social Safeguards Officer (ESSO), FMEnv BASMEnv | 1,500,000 |
| Risk of occupational accidents and injuries to workers | No. of trained first aiders, usage of appropriate PPEs, usage of signages and demarcations | Visual observation | No. of PPEs, used; usage of signages and demarcations | Construction site | Monthly | Env and Social Safeguards Officer (ESSO), FMEnv BASMEnv |  |
| Noise and vibration disturbances in surrounding communities, | Same as above | Same as above | Same as above | Same as above | Same as above | Env and Social Safeguards Officer (ESSO), |  |
| Generation of hazardous and non-hazardous wastes from construction activities | Same as above | Same as above | Same as above | Same as above | Same as above | FMEnv BASMEnv |  |
| Risk of occupational accidents and injuries to workers | Same as above | Same as above | Same as above | Same as above | Same as above | Env and Social Safeguards Officer (ESSO), |  |
| Sub-Total |  |  |  |  |  |  | 2,500,000 |
| Construction Phase |  |  |  |  |  |  |  |
| Deterioration of local air quality due to the release of fugitive dust and gaseous pollutant from vegetation clearance, soil disturbance, and heavy-duty vehicles. | Air quality parameters (CO, NO2, SO2, CO2, SPM) | In-situ measurements, visual observations of records and interviews | Compliance with national air quality standards | Road corridor and adjoining communities | Weekly during pre-construction | Env and Social Safeguards Officer (ESSO), | 2,500,000 |
| Noise and vibration from construction equipment, traffic and activities may disturb sensitive noise receptors (i.e humans) | Noise level | In situ measurement | Noise level not to exceed FMEnv limit of 90dBA for an 8-hour period | Construction site and nearby communities | Monthly | FMEnv BASMEnv |  |
| Potential for conflicts over usage of community amenities by workers | Availability of amenities in worker's camp | visual inspection | Public perception | Workers' camp and host communities | PIU, ESSO, LGA | Env and Social Safeguards Officer (ESSO), |  |
| Direct employment of local population workforce and stimulation of local economy | No of local employed | Records and interviews | Level of satisfaction in host community | Project site and host community | Project site and host community | Env and Social Safeguards Officer (ESSO), | PIU, ESSO |
| Abstraction of significant volume of water from surface or ground water sources may affect supply for other water users and ecosystems and result in conflicts over water use | Alternative sources of water | Visual observation | Availability of water in host health facility | Host school facility and surrounding communities | Monthly | FMEnv BASMEnv | - |
| Inefficient waste management during construction leading to excess consumption of materials, generation of wastes/emissions, pollution of soils/water. | Waste management plan | Visual observation | Waste vendor licenses, waste documentation | Construction route | Bi-monthly | Env and Social Safeguards Officer (ESSO), | 500,000 |
| Poor construction management practices may lead to adverse effects on safety, human health and wellbeing | No. of trained first Aiders, Usage of appropriate PPE, Usage of signages and demarcations | Visual observation | Compliance with Factory Act, 1990 | Construction site | Monthly | Env and Social Safeguards Officer (ESSO), |  |
| Interaction between workforce and local communities may increase occurrence of communicable diseases, including HIV/AIDS and sexually transmitted diseases (STDs) | Evidence of awareness among construction workers and members of affected communities | Interview | No. of incidents/cases | Construction route and adjoining communities | Quarterly | FMEnv BASMEnv | 500,000 |
| Differences in ethnicity, religion etc. may lead to discrimination and harassment and differences (perceived or real) in working conditions between workers may lead to resentment | Developed Code of Conduct, Evidence of awareness among construction workers and members of affected communities | Interview | No. of local staff, No. of complaints | Construction site and host communities | Monthly | Env and Social Safeguards Officer (ESSO), |  |
| Increased noise level within the environment as a result of roofing works | Usage of PPE | Visual observation | Minimal service disruption, Level of satisfaction of school workers in host facility | Host school facilities | Monthly | Env and Social Safeguards Officer (ESSO), |  |
| Generation of hazardous waste like paint cans, aerosols and material packages | Developed WMP | Visual observation | Waste Consignment Note | Construction Site | Monthly | FMEnv BASMEnv |  |
| Disruption of the activities at the facilities as a result of renovation of existing structures | New access to work locations | Visual observation and interview | Minimal service disruption, Level of satisfaction of school workers in host facility | Host school facilities | Monthly | Env and Social Safeguards Officer (ESSO), |  |
| Sub-Total |  |  |  |  |  |  | 4,500,000 |
| Operational Phase |  |  |  |  |  |  |  |
| Generation of solid waste from the usage of renovated and new buildings | Developed WMP | Visual observation | Waste transfer and Consignment Note | Premises of school Facilities | Monthly | Env and Social Safeguards Officer (ESSO), FMEnv BASMEnv |  |
| Generation of hazardous wastes streams like used batteries, used solar panels, fluorescent tubes and spent oils etc | Developed WMP | Visual observation | Waste transfer and Consignment Note | Premises of school Facilities | Monthly | Env and Social Safeguards Officer (ESSO), FMEnv, BASMEnv |  |
|  |  |  |  |  | Sub-Total |  | - |
|  |  |  | Grand Total |  |  |  | 7,000,000 |

## 7.3 Institutional Arrangements

Robust institutional arrangements are essential for the successful implementation of this ESMP. The capacities of these institutions also need to be improved for optimum project implementation. Table 38 explains the arrangement as well as the roles and responsibilities of the institutions and persons that will be involved in the implementation, monitoring, and review of the ESMP.

Table 38: Institutional Arrangement for ESMP Implementation

| S/N | Category | Roles & Responsibilities |
| --- | --- | --- |
| 1 | Federal Ministry of Environment | - Approve disclosure of ESMP in-country - Environmental monitoring to ensure country standards is complied with. |
| 2 | IBSDLEIP Programme Coordinating Unit (PCU) | - Ensuring approval & disclosure of Environmental and Social safeguards instruments to the public - Facilitate M&E implementation and monitoring functions. - Responsible for coordination to ensure that parties to implementation carry out their responsibilities as and when due. |
| 3 | Bauchi State Ministry of Environment | - Responsible for overseeing environmental monitoring and compliance at the State level - Site assessment and monitoring of ESMP implementation. |
| 4 | PIU | - Ensuring approval of fund for Environmental and Social safeguards unit and M&E implementation and monitoring functions; - Ensure that the ESMP is disclosed to the public - Ensure that responsible parties carry out their responsibilities as and when due. - Ensure that AfDB’s safeguards policies and country standards are adhered to by contractors and workers through supervision and funding of mitigation measures |
| 5 | PIU Environmental & Social Safeguard Units | Environmental and Social Safeguards Officer: - Carry out supervision functions during construction to ensure that contractors and workers adhere to mitigation measures in the ESMP; - Collate environmental baseline data on relevant environmental characteristics for monitoring and auditing - Ensure that project activities are implemented in accordance with good practices and guidelines set out in the site-specific ESMP; - Identify and liaise with all stakeholders involved in environment-related issues in the project and be responsible for the overall monitoring of mitigation measures and the impacts of the project during implementation. - Coordinate and ensures the implementation of the social aspects of the ESMP - Identify and liaise with all stakeholders involved in social related issues in the project; - Conduct impact evaluation and beneficiary assessment; and - Establish partnerships & liaise with organizations, Community Based Organizations (CBOs), Civil Society Organizations (CSOs). |
| 6 | Contractor | - Compliance with BOQ specifications in the procurement of material and construction - Implement ESMP during project implementation - Develop C-ESMP - Ensuring staff good behaviour/ practices including the use of PPEs and zero gender violence - Compliance with BOQ specifications in the procurement of material and construction - Hire Safeguards personnel to implement ESMP during project implementation - Mitigate environmental and Social Impacts - Implementation of a code of conduct for all staff - Develop contractor ESMP (C-ESMP) - Preparation of work plans for environmental and social management in line with the ESMP - Ensure any changes during the construction process that may have a significant environmental and social impact are communicated to the PIU on time and managed accordingly. - Maintain records of environmental incidents as well as corrective and preventive actions taken - Supervision the implementation of all the measures and preparation of required Monitoring report - The contractor should ensure that the safety officer conducts a Job Hazard Analysis (JHA) prior to the commencement of work to identify the hazards associated with the job activities - Ensure all contractors and workers sign the Code of Conduct (CoC) and are routinely trained on the contents of the CoC - Provide adequate basic amenities and PPEs to workers and ensure that the PPEs are worn by workers during work. - Prepare and maintain records and all required reporting data as stipulated by the ESMP, for submission to the Supervising Consultant |
| 7. | Supervising Consultant | - Supervise the implementation of the ESMP by the contractors; - Review the Contractors’ Environmental and Social Implementation Plans (CESMP) to ensure compliance with the ESMP - Review site-specific environmental enhancement/mitigation designs worked out by the Contractor. - Develop good practice construction guidelines to assist the contractors in implementing ESMPs. - Prepare and submit regular environmental monitoring and implementation progress reports. - Continuous interaction with the Engineer/PIU Safeguards unit regarding the implementation of the environmental/social provisions in the ESMP - Provides independent oversight ensuring that the contractors adhere strictly to the engineering specifications and provides frequent reports on contractor/ Client’s compliance - Preparation and implementation of the Environmental and Social Monitoring Plan during the construction - Supervision of contractor performance in the implementation of the Construction and Work Camp Management Plan - Hire Safeguards personnel to implement ESMP - Thorough supervision of the mitigation of the environmental and social impacts such as labour influx and GBV - Reporting any incidents or non-compliance with the ESMP to the PIU - Ensuring adequate training and education of all staff involved in environmental supervision - Making recommendations to the BAUCHI PIU regarding ESMP performance as part of an overall commitment to continuous improvement - Supervise contractor performance of the implementation of the Construction Campsite/Staging area Camp Management Plan/CESMP - Prepare monthly safeguards report including recommendations to the BAUCHI PIU regarding ESMP performance as part of an overall commitment to continuous improvement |
| 8 | Bauchi State Ministry of Environment and Bauchi State Environmental Protection Agency | - Inspection of project premises to ensure strict compliance with sanitation and waste management standards in the state. - Collaboration with other MDAs at the State and Federal levels, NGOs, and Donor Agencies in environmental protection and management especially in areas of waste recycling, etc. |
| 9 | Dambam, Alkaleri and Itas/Gadau Local Government Authorities | - Provision of oversight function across projects within its jurisdiction for ESMP compliance. - Monitoring of activities related to public health, sanitation, and waste management amongst others. |
| 10 | Affected Community and Public | - Promote environmental awareness. - Review environmental and social performance report made available by BAUCHI PIU. - Provide comments, advice, and/or complaints on issues of non-conformity. - Attend public meetings organized by the BAUCHI PIU to disseminate information and receive feedback. - Identify issues that could derail the project and support project mitigation measures and awareness campaigns. |
| 11 | Community-Based Organizations (CBOs) | - Ensure community participation by mobilizing and sensitizing community members; |
| 12 | NGOs/CSOs | - Assisting in their respective ways to ensure effective response actions, conducting scientific research alongside government groups to evolve and devise sustainable environmental strategies and techniques. |
| 13 | AfDB | - Overall supervision and provision of technical support and guidance. - Disclosure of ESMP on Bank’s website - Oversight mission to monitor BAUCHI PIU’s implementation and performance of ESMP |

## 7.4 	Contractual Measures

Most of the mitigation measures are the obligation of the Contractor during the pre-construction and construction phases of the project. Consequently, the potential contractor will have to prepare their proposals with detailed general environmental management conditions during civil works.

Table 39: Contractual Measures

| Action | Remarks |
| --- | --- |
| The measures as described in this ESMP shall be included in the tender documents with appropriate flexibility to adjust these measures to site circumstances, and the potential contractor will have to prepare their proposals taking into account these measures. | The non-inclusion of these measures in the proposal will lead to disqualification of the proponent; The contract with the successful bidder should contain these environmental and social management measures as firm conditions to be complied with. |
| Specifically, the measures should be translated into a compilation of environmental specifications that are written in the same language style and format as the rest of the contract document | This approach will ensure that the environmental and social controls integrate seamlessly into the tender document and are presented in a familiar form to the Contractor |
| The cost of mitigation measures be added to the cost of the contractual document | The contractor must take into account and put the cost for the environmental and social requirements specified in the ESMP. |

## 7.5 	Capacity Building for Implementation of ESMP and Permit Conditions

Training and capacity building is fundamental to the successful implementation of the ESMP. A robust program will be put in place to ensure that all parties involved in the project implementation obtain E&S awareness training in areas including AfDB E&S Safeguards requirements.

The training on the ESMP implementations will include the Code of conduct for contractors and their labour force, public health and safety issues, occupational health, Grievance Redress Mechanism for the project, and ESMP monitoring and reporting. The capacity building will also involve sensitization of workers on issues such as child sexual exploitation, labour influx, Gender Based Violence, HIV/AIDS and their mitigation measures.

The capacity building plan proposed to achieve this is provided in Table 40:

Table 40: Capacity building plan for implementation of the ESMP & permit conditions

| Activity | Target Group/Participants | Timeline/ Duration | Proposed Facilitator | Cost NGN |
| --- | --- | --- | --- | --- |
| *Training Workshop on preparation of ESMP, Permit Schedule *AfDB Safeguards Policy triggered and environmental management. *Construction works safeguard requirements | *Engineering Consultants -Resident Engineers, Clerks of Works *Project Coordinator, Works Engineer, Planning Officer, Finance Officer, Safeguard Officers *Contractor, contractor workers, Manager, Foreman, Engineers | Prior to the resumption/ commencement of construction works. (1 day) | Environmental Safeguards Specialist/ Consultant | 1,800,000 |
| *Sensitization of workers on child sexual exploitation and HIV/AIDS, labour influx, Gender Based Violence, and their mitigation measures. |  | Prior to the resumption/ commencement of construction works. (1 day) | Safeguards Specialist/ Consultant | 1,200,000 |
| *Induction on occupational and public health and safety (OHS) requirements of the works and environmental management *Training on Contractor’s, manager’s, and Worker’s Code of Conduct understanding | All construction/ contractor workers | Prior to commencement of construction works. (1 day) | Lead Contractor/ Engineering Consultant/ HSE-OHS Consultant | 800,000 |
| Total |  | N4,600,000.00 |  |  |

## 7.6 Implementation Schedule

The activities related to environmental management and monitoring must be integrated into the overall construction schedule. The project implementation phase is estimated for 2 months for the construction activities. The implementation schedule is presented in Table 41.

Table 41: Implementation Schedule

| S/N | Activity Description | Responsible | Weeks |  |  |  |  |  |  |  |  | Operations Phase |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Pre-construction |  |  |  |  | Construction |  |  |  |  |
|  |  |  | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 |  |
| 1. | Clearance and Formal Disclosure of ESMP | BAUCHI PIU |  |  |  |  |  |  |  |  |  |  |
| 2. | Inclusion of E&S Requirements in bid documents | BAUCHI PIU |  |  |  |  |  |  |  |  |  |  |
| 3. | Allocating Budget for ESMP | BAUCHI PIU |  |  |  |  |  |  |  |  |  |  |
| 4. | Appointing Support Staff for ESMP | BAUCHI PIU |  |  |  |  |  |  |  |  |  |  |
| 5. | Review & Approval of Contractor’s E&S Plans | BAUCHI PIU |  |  |  |  |  |  |  |  |  |  |
| 6. | Finalization of Engineering Designs | BAUCHI PIU/ Consultant |  |  |  |  |  |  |  |  |  |  |
| 7. | Mobilization to site | Contractor |  |  |  |  |  |  |  |  |  |  |
| 8. | Site Clearing | Contractor |  |  |  |  |  |  |  |  |  |  |
| 9. | Construction Phase | Contractor |  |  |  |  |  |  |  |  |  |  |
| 10. | Implementation of Mitigation | BAUCHI PIU/ Contractor |  |  |  |  |  |  |  |  |  |  |
| 11. | Supervising ESMP Implementation | BAUCHI PIU |  |  |  |  |  |  |  |  |  |  |
| 12. | Monitoring & Reporting on ESMP Implementation | BAUCHI PIU/MDAs |  |  |  |  |  |  |  |  |  |  |
| 13. | Environmental and Social Training | E&S Consultant |  |  |  |  |  |  |  |  |  |  |
| 14. | Environmental and Social Auditing | BAUCHI PIU/Consultant |  |  |  |  |  |  |  |  |  |  |
| 13. | Demobilization Phase | BAUCHI PIU/Contractor |  |  |  |  |  |  |  |  |  |  |
| 14. | Operations Phase | BAUCHI PIU/Contractor |  |  |  |  |  |  |  |  |  |  |

## 7.7 ESMP Cost & Analysis

Detailed environmental and social mitigation measures for pre-construction, construction, and operational phases have been provided in Table 42. The environmental and social management actions is estimated at Fourteen Million, One Hundred and Forty-Six Thousand, Three Hundred and Thirty Naira Only (N14,146,330.00), and a Dollar equivalent of Thirty-Three Thousand, Two Hundred and Seven Dollars Only ($33,207.00). The cost of implementing the ESMP is presented in Table 42.

Table 42: Cost of implementing the ESMP

| S/N | ESMP Expectation Items | Responsibility | Cost Estimate |  |
| --- | --- | --- | --- | --- |
|  |  |  | Naira (N) | USD ($) |
| 1 | Mitigation | Contractor/ Supervising Consultant/BAUCHI PIU Safeguards Unit | 10,800,000.00 | 23,478.75 |
| 2 | Monitoring | BAUCHI PIU M&E Unit/ Safeguards Unit | 7,000, 000.00 | 15,217.45 |
| 3 | Capacity Building (including training on Code-of-conduct) | Lead Contractor/ Engineering Consultant/ HSE-OHS Consultant/BAUCHI PIU Safeguards Unit | 4,600,000.00 | 9,999.88 |
| 4 | GBV, STIs and HIV Mitigation | GBV Consultant/BAUCHI PIU Safeguards Officers | 500,000.00 | 1,086.94 |
| 5 | Grievance Redress Mechanism | BAUCHI PIU Safeguards Officer | 500,000.00 | 1,086.94 |
| 6 | Consultations | BAUCHI PIU Safeguards Unit | 500,000.00 | 1,086.94 |
| 7 | Disclosure | BAUCHI PIU/State/BASMEnv. /FMEnv/AfDB | 1,000,000.00 | 2,173.92 |
| #### Sub-Total |  |  | 24,900,000.00 | 54,130.43 |
| 8 | Contingency (10% of Sub-total) |  | 2,490,000.00 | 5,413.04 |
| Grand Total |  |  | 27,390,000.00 | 59,543.47 |

Conversion: 1 USD = 459.990 NGN

The cost of mitigation by the Contractor will be included in the contract as part of the implementation cost by the Contractor. The Bauchi PIU will coordinate the implementation of this ESMP in conjunction with the relevant State MDAs.

# CHAPTER EIGHT: STAKEHOLDER CONSULTATION

## 8.1 Introduction

Consultations and public participation enable the project to understand and document concerns about environmental and social impacts associated with the project. During the preparation of the ESMP, significant consultations and public participation were carried out. Stakeholder consultations and public participation was carried out:

(i) To provide an opportunity for people likely to be affected by the project to get clear, accurate, and comprehensive information about the proposed project and it’s anticipated environmental and social impacts;

(ii) To provide an opportunity for people to give their views and raise their concerns;

(iii) To provide people to be affected with the opportunity of suggesting ways of avoiding, reducing, or mitigating negative impacts;

(iv) To enable the project proponents to incorporate the needs, preferences, and values of the project as seen by the stakeholders;

(v) To provide opportunities to avoid and resolve disputes and reconcile conflicting interests; and,

(vi) To enhance transparency and accountability in decision-making.

8.2 Process and the methodology of Stakeholder consultation

During the project preparation mission, several consultations were held. Consultations were carried out with the technical officers from different ministries, civil society institutions and community members of Mashema, Dagauda and Yelwan Duguri communities in Itas-Gadau, Dambam and Alkaleri Local Government Areas respectively. Detail of the methods, Techniques, and tools used for stakeholder engagement is provided in Table 43.

Table 43: Methods, Tools and Techniques for Stakeholder Engagement in School project

| Method / Tool | Description and Use | Content | Target Groups |
| --- | --- | --- | --- |
| Surveys, Interviews and Questionnaires | The use of public opinion surveys, interviews and questionnaires to obtain stakeholder views. | Description of the proposed Project and related solutions/impact management measures. Questions targeting stakeholder perception of the Project, associated impacts and benefits, concerns and suggestions. | - Households directly benefited by the project |
| Household visits | Household-level visits conducted particularly to solicit feedback from vulnerable community members that includes the disabled, elderly and the minority ethnic communities who may be unable to attend the formal hearing events. | Description of the Project and related solutions/impact management measures. Any questions, queries or concerns, especially for stakeholders that may have a difficulty expressing their views and issues during formal community-wide meetings. | - Households directly benefited by the project |
| Focus Group Discussions and Round Table Workshops | Used to facilitate discussion on Project’s specific issues that merit collective examination with various groups of stakeholders. | Project’s specific activities and plans, design solutions and impact mitigation/management measures that require detailed discussion with affected stakeholders. | Households directly benefited by the project Representatives (Village/Ward) Local government representatives Local NGOs |

The consultations were facilitated by the Environmental/Social Safeguard officer of the IBSDEIP SPIU. Specific meeting dates and content of meetings held are presented in Table 44.

Table 44: Record of Engagement carried out at the various school project sites

| Date of the meeting | Site | Content | Attendees |
| --- | --- | --- | --- |
| 13th September, 2022 | Mashema Model School Site | Briefing on the objectives of the Bauchi State IBSDEIP Model School project particularly it Benefits, nature, size and resources required. The need for conducting the ESMP as part of the requirements for execution of projects under the AfDB. Obtaining feedback and opinions. | Community, youth and women leaders from the three communities See Appendix X for list of participants |
| 13th September, 2022 | Dagauda Model School Site |  |  |
| 14th September, 2022 | Yelwan Duguri Model School Site |  |  |

8.3 Outcome of the Stakeholder Engagement

All the project communities visited were happy with the construction/upgrade work which according to them will have positive impact on their health conditions. They applauded the project and promised to give their maximum support and cooperation.

The major issues rose by the community members and how they were addressed at the various project sites are presented in Table 45.

Table 45: Outcome of stakeholder consultations held for the school construction projects

| Issues raised during consultations | How they were addressed |
| --- | --- |
| In all the communities visited, members were eager to see the commencement and completion of the project. | All arrangements have been put in place for the commencement of the project and it will be start immediately. The project monitoring unit will ensure quality work and speedy completion of the project as scheduled. |
| The construction of fencing wall at Mashema is not good enough as domestic animals were seen crossing and entering into the school premises. | The attention of the contractor will be drawn to do the needful. |
| Involvement of member of the communities as menial workers during construction/rehabilitation stage of the project | Issues regarding labour hiring would be handled in conjunction with contractor & village heads. |
| The community hoped that with the expansion of the schools, their wards would be employed as teachers because they have unemployed university graduates | Regarding the employment of more teachers. Appropriate recommendation would be made in the ESMP document |
| In Yelwan Duguri project site, the Issue of insecurity especially kidnapping was raised. | The community members were assured by the IBSDLEIP staff that more security personnel would be provided to safeguard the lives of the workers at the construction site. |
| The community members talked to the ESMP consultants and IBSDLEIP safeguard officer on the need for soft and hard landscaping of some areas that are prone to erosion. | On the landscaping issue, the community members were informed that landscaping is part of the contract agreement and the contractor will be reminded. |

# CHAPTER NINE: GRIEVANCE REDRESS MECHANISM

## 9.1 Introduction

The Grievance Redress Mechanism (GRM) outlines a process for documenting and handling project grievances that may be raised by affected individuals or community members regarding specific project activities, environmental and social performance, the engagement process, and/or unanticipated social impacts as a result of project activities. It describes the scope and procedural steps and defines the roles and responsibilities of the parties involved. The GRM will be revised based on experiences and feedback from stakeholders.

## 9.2 Designated staff coordinating Grievance Redress

The PIU Environmental and Social Safeguard specialist will be designated as the person in charge of Grievance Redress and has the following responsibilities in respect of the GRM;

- Coordinate formation of Grievance Redress Committees (GRCs) before the commencement of construction to resolve issues.

- Act as the Focal Point at PIU on Grievance Redress issues and facilitate the grievance mechanisms.

- Create awareness of the Grievance Redress Mechanism (GRM) among all the stakeholders through public awareness campaigns.

- Assist in Redress of all Grievances by coordinating with the concerned parties.

- Maintain information of grievances and Redress.

- Monitor the activities on Redress of Grievances.

- Prepare the progress for monthly/quarterly reports.

- Provide resources to cover the operational costs of the GRM.

## 9.3 Mode of receipt and recording of Complaints

The complaints can be made in writing, verbally, over the phone, by fax, emails or any other media. As soon as the officer receives a complaints, he /she would issue an acknowledgement of the complaint, including the details of the person bringing the grievance. The officer receiving the complaints should try to obtain relevant basic information regarding the grievance and the complainant and will immediately inform the safeguard specialist the receipt of the complaint.

The PIU will maintain a Complaint/Grievance and Redress register or log book and the responsibility of keeping records collected from relevant bodies will be the responsibility of the PIU safeguard specialist.

## 9.4 Structure of Grievance Redress

The Bauchi State IBSDLEIP PIU shall receive and act upon complaints from stakeholders or Project Affected Persons (PAPs) in relation to any occurrences for which the Project is directly responsible (or believed to be responsible), and which are perceived by the aggrieved party to have involved corrupt, illegal, unjust, or unfair activities, omissions, or behaviour.

In the context of GRM complaint is a notification (in written, verbal or electronic form) regarding project activities and/or conduct of staff, consultants, partners and/or sub- contractors, directly or indirectly supporting the project or associated with its implementation, which the complainant believes is wrong, either under the law or on the grounds of unacceptable behaviour. The complainant(s) need not be personally aggrieved or impacted, and may be acting merely in accordance with a sense of civic duty in bringing an occurrence to the attention of project authorities.

In defining the levels of grievance redress, priority was given to aligning with the existing mechanism and strengthening same as required, taking into consideration the GRM developed for ISBDLEIP as a whole, which was designed based on consultation and stakeholder inclusion during the preparation of the ESMP. Defining the GRM process took into account the specific issues, cultural context, local customs, industry standards and project conditions. The functioning of the GRM system, how to register complaints (written, by phone, or in person), where to go and hours of service, all were clearly explained in local language (Hausa) during public consultations on the project.

### Expectation When Grievances Arise

When local people present a grievance, they expect to be heard and taken seriously. Therefore, the State Project Implementation Unit (SPIU) and others such as the engineers involved in one aspect of the sub-project or other must convince people that they can voice grievances and work to resolve them without retaliation. It should be understood that all or any of the followings is or are expected from the project management/channel of grievance resolution by the local people:

- acknowledgement of their problem;

- an honest response to questions/issues brought forward;

- an apology, adequate compensation (where necessary); and

- Modification of the conduct that caused the grievance and some other fair remedies.

### Management of Reported Grievances

The procedure for managing grievances should be as follows:

- The affected person files his/her grievance relating to any issue associated with the resettlement process or compensation, in writing or otherwise, to the project Resettlement and Compensation committee (phone numbers will be provided by the SPIU). When received in writing, the grievance note should be signed and dated by the aggrieved person. When received through telephone call, the receiver should document all details.

- A selected member of the Grievance Redress Committee will act as the Project Liaison Officer who will be the direct liaison with PAPs in collaboration with an independent agency/person ensure to objectivity in the grievance process.

- Where the affected person is unable to write, the local Project Liaison Officer will write the note on the aggrieved person’s behalf.

- Any informal grievances will also be documented

### Monitoring Complaints

The Project Liaison Officer will be responsible for:

- Providing the Grievance Redress Committee with a weekly report detailing the number and status of complaints;

- Any outstanding issues to be addressed;

- Monthly reports, including analysis of the type of complaints, levels of complaints, actions to reduce complaints and initiator of such action.

## 9.5 Grievance Redress Mechanism Process

The stakeholders are informed of various points of making complaints (if any) and the PIU collect the complaints from these points on a regular basis and record them. This is followed by coordinating with the concerned people to address the grievances. The PIU will manage the grievance activities at the respective stakeholder’s level to address the Grievances and would act as the focal point in this regard.

A three tier Redress structure is proposed to address all complaints in the sub-projects under IBDSLEIP

- First tier of Redress

Complaints regarding project implementation and activities arising from the project area shall be channeled to the Village head, who shall convene the GRC committee at that level to review and address the complaint.  The underlying merit is that the community has proven a notable channel for conflict resolution in the project area. The Village head shall head this committee while membership of the committee will consist of:

- The Village head -Chairman

- A representative of Council of Elders

- A representative of the Community Development Association

- A representative of Youth Organization

- Representative of the Women Group

- Environmental/Social Safeguards Officer of the SPCU

- GRM officer-Secretary

This committee will be expected to report to the SPCU. In addition, all complaint communication tools as prescribed in the GRM will be made known and accessible to the PAPs. These complaints are received (in written, verbal or electronic form) at Community Level. Complaint boxes are to be placed at one or more of the following points of receiving complaints at the community level:

- Respective LGAs;

- Community Town hall

- Designated spots along the road

- Traditional Ruler’s Palace

- Safeguards Officers at SPCU

- GRM officer

The complaints are received at various points as described above. The resolution at the first tier will be normally be done within 14 working days and notified to the concerned through a disclosure form. Should the Grievance be not solved within this period, this would be referred to the next level of Grievance Redress. However, if the PIU feels that adequate solutions are worked out but it would require a few more days for actions to be taken, he/she can decide on retaining the issue at the first level by informing the complainant accordingly. However, if the complainant requests for an immediate transfer of the issue to the next level, it would be accepted and the issue would be taken to the next tier, especially if the issue is not addressed within 21 days.

b) Second tier of Redress

The Grievance Redress Committee (GRC) would be the one which would address the grievance in the next level in case the problem is not solved at the first tier. The Project Coordinator (PC) shall head this committee while membership of the committee shall be as follows:

- Project Coordinator- Chairman

- Internal Auditor

- Monitoring and Evaluation officer

- Communications Officer.

- One representative of the non-state sector from within the State Project Monitoring Committees

- Environmental and Social Safeguard Officer

- GRM- Secretary

The safeguard specialist will coordinate the convening of the meetings of the GRC. He / She are also responsible for briefing the GRC on the grievances and deliberations of the first level of Redress, outcomes and on the views of both the parties (project proponent and complainant).

The GRC will hold the necessary meetings with the affected party/complainant and attempt to find a solution acceptable at all levels. The GRC would record the minutes of the meeting and filed by the PIU. The decisions of the GRC will be communicated to the complainant formally and if he/she accepts the resolutions, the complainant’s acceptance is obtained in writing and signing off is done between the complainant and the GRC.

If the complainant does not accept the solution offered by the GRC, then the complaint is passed on to the next level / or the complainant can reach the next level for redress. The Chairman of the GRC would be required to forward the issue to the Third Tier to facilitate in exploring a solution to the grievance. In any case, the grievance should be forwarded to the next level if no solution is reached within 14 days of the case reaching the second level. However, in cases nearing offering an amicable solution, it can be retained to an extent of 21 days.

c) Third tier of Redress

If the affected party / complainant does not agree with the resolution at the 2nd level, or there is a time delay of more than a month in solving the issue, the complainant can opt to consider taking it to the third level.

Where an agreement has not been reached, the complainant can opt to consider taking it to overall Technical Committee GRC (TC-GRC) constituted as the Third Level of Redressal to look into the problems not solved in the Second Level. Membership of the GRC at this level includes Traditional/Community Leaders and the Commissioner of Local Government of the project Community to enable the TC-GRC understand the deliberations of the two previous GRC. Additionally, the GRM Officer of the SPCU will collect all the details of the Grievance including the deliberations of First and Second level efforts and present it to the TC-GRC.

The decisions of the 3rd tier structure would be final from the project side and will be communicated to the complainant formally and if he/she accepts the resolutions, the complainant’s acceptance is obtained and signed off by the complainant and the 3rd tier structure, including the project GRC.

The Complainant may decide to take a legal or any other recourse if he /she is not satisfied with the resolutions of the deliberations of the three tiers of GRM. It should be encouraged that the 3 levels of handling the grievances should be exhausted extensively before one goes to courts as last resort.

Figure 19 shows a proposed Grievance Redress Mechanism flow process for the IBSDLEIP.

## 9.6 GRM Jurisdiction

The proposed GRM is project specific and scaled to the risks and impacts of the Project. It is meant to solve the project’s concerns by the stakeholders or any complainant. The proposed GRM is however not intended to bypass any Governments’ own existing redress process; rather is intended to address affected people’s concerns and complaints promptly, making it readily accessible to all segments of the affected people. Any established Government Redress mechanisms take priority over the proposed GRM.

## 9.7 AfDB Independent Recourse Mechanism

The Independent Recourse Mechanism (IRM) is the independent complaints mechanism of the African Development Bank Group (AfDB). The IRM addresses complaints from individuals, workers and communities who believe they have been or might be adversely affected by an AfDB-financed project.

The IRM seeks to provide fair, independent, and effective recourse for project-affected individuals, and communities, and serve as a platform where project-affected people can hold the Bank to account for its actions and seek remedy and redress for related harms.

It also aims to ensure that the Bank learns important lessons and engages in a continuous improvement process by utilizing the complaint-handling process to identify areas where the Bank may be able to strengthen its policies, procedures, and or practices in the future to avoid negative impacts, improve sustainable development outcomes, and ensure that "no one is left behind".

IRM’s goal is to enhance the accountability and sustainability of AfDB-financed projects to contribute to the social and economic progress of Africa. It aims to provide a safe and trusted space for people to bring forward their concerns about AfDB projects without fear of retribution or reprisals. IRM’s accountability report provides our stakeholders with an account of our activities and progress.

# CHAPTER TEN: CONCLUSION

## 10.1 Introduction

This project with the associated activities outlined in this ESMP for the construction/upgrade of the Model Primary Schools Dagauda, Yelwan Duguri, and Mashema towns of Bauchi State will have highly beneficial impacts by improving critical service delivery infrastructure within this community and thereby scaling up living conditions, through which social cohesion can be improved.

The civil works associated with the construction/upgrade of the model primary schools are anticipated to lead to some limited adverse environmental and social impacts which will largely be localized in spatial extent, short term, and occurring within less sensitive environmental areas. These will be managed through the application of the appropriate mitigation measures stated in the ESMP matrix table, which would be included in the contractor’s agreement, good practices, adequate supervision, and enforcement during project implementation.

The contractor and the PIU should give priority ion to mitigation of air water and soil pollution, distortion of landscape, loss of vegetation and occupational hazards such as accidents and incidents during the construction/upgrade of the model primary schools. Adverse social impacts to be addressed include the labour concerns of the local communities, loss of cultural and traditional values and the risks of gender-based violence among others.

The ESMP has provided in detail the mitigation measures for identified potential adverse impacts associated with the various phases of the project, and a monitoring program to ensure compliance. In conclusion, with an adequate application of mitigation measures the identified environmental and social impacts will be avoided, reduced, and mitigated.

# References

Adewole I. (2016) Thirty Six States and the FCT are to Share $1.5m FG Fund for Primary Health Care. Available from: https://www.informationng.com/2016/07/36-states-and-the-fct-to-share-1-5m-fg-fund-for-primary-healthcare.html

Aregbeshola, B. S. and Khan, S. M. (2017) Primary Health Care in Nigeria: 24 Years after Olikoye Ransome-Kuti’s Leadership. Fronteirs in Public Health. 5(48).

Bauchi State Agricultural Development Programme (BSADP) (2007) Bauchi state fadama III project environmental baseline survey

Dike, E. and Dan-Hassan, M. The Geology and Aquifer Properties of the Tertiary

Kern-Kerr Formation, Bauchi State. Proceeding of Nigerian Association of Hydrogeologists 3rd National Conference. Zaranda Hotel Bauchi. pp117-133, 1990.

S.E. Mansour and I.H. Hasieb, (2012). Removal of Nickel from Drinking Water by Electrocoagulation Technique Using Alternating Current. Current Research in Chemistry, 4: 41-50.

Abdulrahman, A.  Shehu, A. D. and Ibrahim, S (2016) Using vertical electrical sounding for a groundwater potential map of ATBU Yelwa Campus, Bauchi, Nigeria. JOLORN VOL. 17 No. 1.

Asodike J. (2014) Basic Issues in Primary Education Delivery in Nigeria European Scientific Journal January edition vol. 8, No.1

WHO (2018) A Vision for Primary Health Care in the 21st Century: Towards Universal Health Coverage and Sustainable Development Goals. WHO Technical Note Series on Primary Health Care. Available at:

https://www.who.int/docs/default-source/primary-health/vision.pdf

DPR (2002) Environmental Guidelines and Standards for the Petroleum Industry in Nigeria (Revised Edition). Department of Petroleum Resources of Nigeria, Ministry of Petroleum and National Resources Abuja, Nigeria, p. 171.

WHO (2022) Guidelines for drinking-water quality Fourth edition incorporating the first and second addenda

# Annex 1: Attendance Sheet

# Annex II: Sampling Locations

Soil sampling locations

| S/N | SAMPLE IDENTITY | COORDINATE |
| --- | --- | --- |
| 1 | SCH DGD 01 | N: 11o 42’ 02.9’’ E: 010o 51’ 48.0’’ |
| 2 | SCH DGD 02 | N: 11o 42’ 02.7’’ E: 010o 51’ 45.3’’ |
| 3 | SCH Y/DGR 01 | N: 09o 57’ 45.6’’ E: 010o 11’ 58.8’’ |
| 4 | SCHY/DGR 02 | N: 09o 57’ 44.8’’ E: 010o 11’ 55.4’’ |
| 5 | SCH MSM 01 | N: 11o 47’ 06’’ E: 009o56’ 23’’ |
| 6 | SCH MSM 02 | N: 11o 47’ 07’’ E: 009o56’ 32’’ |

## Ground Water sampling locations

| S/N | SAMPLE IDENTITY | COORDINATE |
| --- | --- | --- |
| 1 | SCH DGD 01 | N: 11o 42’ 00’’ E: 010o 51’ 51’’ |
| 2 | SCH DGD 02 | N: 11o 42’ 58’’ E: 010o 51’ 45’’ |
| 3 | SCH Y/DGR 01 | N: 09o 57’ 24’’ E: 010o 11’ 11’’ |
| 4 | SCH Y/DGR 02 | N: 09o 57’ 08’’ E: 010o 11’ 13’’ |
| 5 | SCH MSM 01 | N: 11o 47’ 05’’ E: 009o56’ 24’’ |
| 6 | SCH MSM 02 | N: 11o 47’ 08’’ E: 009o56’ 31’’ |

Air sampling locations

| S/N | SAMPLE IDENTITY | COORDINATE |
| --- | --- | --- |
| 1 | SCH DGD 01 | N: 11o 42’ 02’’ E: 010o 51’ 47’’ |
| 2 | SCH DGD 02 | N: 11o 42’ 58’’ E: 010o 51’ 51’’ |
| 3 | SCH Y/DGR 01 | N: 09o 57’ 50’’ E: 010o 11’ 01’’ |
| 4 | SCH Y/DGR 02 | N: 09o 57’ 44’’ E: 010o 11’ 14’’ |
| 5 | SCH MSM 01 | N: 11o 47’ 07’’ E: 009o56’ 19’’ |
| 6 | SCH MSM 02 | N: 11o 47’ 10’’ E: 009o56’ 38’’ |

# Annex III: Questionnaire used for the socio-economic survey

INCLUSIVE BASIC SERVICE DELIVERY AND LIVELIHOOD EMPOWERMENT INTEGRATED PROGRAMME (IBSDLEIP)

Questionnaire for the Preparation of Environmental and Social Management Plans (ESMP) for IBSDLEIP Projects in Bauchi State

This questionnaire is aimed at eliciting your view/opinion on the social and environmental implications of the IBSDLEIP project activities in your community. Your input would assist in the preparation of an Environmental and Social Management Plan (ESMP) that would enable the IBSDLEIP-PMU to manage the various project activities in a manner that guarantees socio-environmental sustainability of the project.

PART A: Project Information

Time Interview started ____________________________

QUESTIONNAIRE NUMBER:_____________________________

| Survey Identification: |  |
| --- | --- |
| 1. State |  |
| 2. LGA |  |
| 3. Village/Community |  |
| 4. Type of intervention |  |
| 4. Enumerator |  |
| 5. Respondents |  |
| 6. Interview date |  |
| 7. Household Telephone No. |  |
| 8. Household Identity No. |  |

Please mark (x) or write in brief detail where appropriate

PART B: Bio-data and Socioeconomics

9.	Age in years: a. 18-30 ( )  b. 31-40 ( ) c. 41-50 ( )  d. 51-60 ( ) e. Above 60

- Sex: a. Male ( )  b. Female ( )

- Religion: a. Christianity ( ) b. Islam ( ) c.  African Traditional Religion d. Atheist ()

- Marital Status: a. Single ( ) b. Married ( ) c. Divorced ( ) d. Widow ( ) e. Widower ( )

|  | 13. Ethnicity: a. Duguri ( ) b. Fulani ( ) c. Hausa ( ) d. Kanuri ( ) e. Karai-Karai ( ) f. Gerawa ( ) g. Jarawa ( ) h. Others specify ( ) |
| --- | --- |
|  | 14.Number of Children: a. 1-3 ( ) b. 4-7 ( ) c. 8-11 ( ) d. Above 11( ) |

- Educational level: a. No formal education ( ) b. Qur’anic education ( ) c. Primary school ( ) d. Secondary school ( ) e. Tertiary education ( ) f. Other(s) Specify

- What is your primary occupation?

a. Farming (   ) b. Fish capture (   ) c. Agric trading business (   ) d. Agric processing e. Formal private employment (   ) f. Domestic duties (   ) g. Public sector employment (   ) h. Retiree (   )   i. Artisan (    ) j. Handcraft (    ) k. Other(s) Specify …………………………………………….

- What is your income range per annum?

| Amount | Tick |
| --- | --- |
| N1- N100,000 |  |
| N101,000 - N200,000 |  |
| N201,000 - N300,000 |  |
| N301,000 - N400,000 |  |
| N401,000 - N500,000 |  |
| Above N500,000 |  |

- Housing

| Type(s) of Housing | Tick |
| --- | --- |
| 1. Traditional hut/grass roof |  |
| 2.Mud block/corrugated iron roof |  |
| 3.Cement Block/corrugated roof |  |
| 4.Others specify |  |

- Infrastructural Facilities

Which of the following infrastructure do you have in this community?

| S/N | Type of infrastructure | Tick |
| --- | --- | --- |
| A | Road Tarred/Feeder |  |
| B | Hospital/Health facility |  |
| C | Electricity |  |
| D | Market |  |
| E | Schools |  |
| f | Borehole |  |
| g | Others specify |  |

Please briefly describe the leadership structure in this community

- What is your perception with regard to this project?

| S/N | Perception | Tick |
| --- | --- | --- |
| A | Very useful |  |
| B | Useful |  |
| C | Not useful |  |
| D | Undecided |  |

PART C:	Water, Sanitation and Waste Management

21. What is/are the main source(s) of water in your household? (Tick as it applies).

(a)   Tap [   ]    (b) Borehole [   ]   (c) Stream [   ]   (d) Rain [   ]

(e)  Well [   ]   (f) Others (specify) _________________

22. Do you use water from the same source (s) for the various domestic purposes?

(a)  Yes [  ]    (b) No [   ]

23.	Do you experience water shortage in your household?

- Yes [   ]  (b) No  [   ]

24.	If yes, what is/are the possible reason(s) for the shortage?

| S/No. | Usage | Conflict | Increase in population | Contamination of existing water sources | Seasonal drying up of existing water sources | More competing needs |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Drinking |  |  |  |  |  |
| 2 | Cooking |  |  |  |  |  |
| 3 | Bathing |  |  |  |  |  |
| 4 | Washing dishes and clothes |  |  |  |  |  |
| 5 | Cleaning |  |  |  |  |  |

25.	How would you rate the quality of your water?

a)  Very good   [   ]   b) Good [   ]     c) Fair [   ]    d)  Poor    [   ]	e)  Very poor [   ]

25.	Does your household treat its water before use?

a)   Yes [   ]  b) No [   ]

27.	If Yes, how do you treat the water? (Tick as it applies)

a)   Boiling [   ]    b)   Filter/Sieve [   ]    c)   Use Alum/Chlorine [   ] d)   Let it settle [   ]

e)   Others (Specify)  ....................................................

28.	How do you store your water?

a)   Tank [   ]     b) Drum     c) Plastic containers [   ]   d)   Jerry Cans [   ]     e) Pots [   ] f) Don’t store [   ] f) Others (specify):……………………………………….

29.	What kind of sewage disposal system does your household have?

a)  Individual household gutters [   ] b) Central disposal [   ] c)   Individual septic

tanks [   ] d)   None [   ]

30.	What kind of Toilet/Latrine does your household use?

a)   Conventional water system [   ] b)   Pit larine [   ] c)   VIP latrine [   ] d)   Open defecation [   ]

31.	Have you emptied your latrine in the last five years?

a.) Yes	[   ]	b) No [   ]

32.  If Yes, how do you dispose the evacuated waste (Tick as applicable)

a. Buried it in another pit [   ]

b. Composted it  [   ]

c. Dumped it on open space [    ]

d. Applied it in the farm (as fertilizer) [   ]

e. Others (specify):……………………………………………………

33. Do you know of any possible source(s) of contamination to your water source in this household?     a)  Yes [  ]  b) No  [   ]  c) Not sure [   ]

34. If yes, please tick the possible source(s) of contamination:

| S/N | Water source | Dusts and solid wastes | Liquid contaminants (Effluents) | Animals | Poor hygiene | Poor sanitation |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Tap |  |  |  |  |  |
| 2 | Borehole |  |  |  |  |  |
| 3 | Well |  |  |  |  |  |
| 4 | Surface water |  |  |  |  |  |
| 5 | Rain |  |  |  |  |  |

35. 	How often does your household clear its surroundings?

a) Weekly [  ] b)  Bi-weekly [  ] c. Monthly [  ] d) Others (specify):………………………

36. 	How do you dispose your household wastes?

a. Open dumping [  ]	b. Waste collectors [  ] c. Recycling [  ] d. Composting [  ]

e. Burning [  ] f. Others:________________________________________________

37. How often do you dispose your household wastes?

a. Daily [  ]	c. Weekly [  ]	d. Fortnightly [  ]	e. Monthly [  ]	f. Others________

38. What is your understanding of sanitation and hygiene practices (Tick as applicable)

a. Washing of hands 							[  ]

b. Proper cooking and storing of food/food items.			[  ]

c. Safe disposal of faeces						[  ]

d. Cleaning of our surrounding					[  ]

e. General hygiene

[  ]

39. In your opinion when do you think is the ideal time to wash your hand (Tick as applicable)

a. After coming in contact with faeces 	[  ]

b. Before eating				[  ]

c. Before cooking				[  ]

d. Others (specify)__________________________________________________

PART D: Hygiene Practice

The following statements seek to know your hygiene practice, please indicate your agreement or otherwise by ticking (√) the appropriate box.

| S/No. | Statement | Yes | No |
| --- | --- | --- | --- |
| 40 | I don’t handle food when I am infected with disease |  |  |
| 41 | I always wash my hand before preparing food |  |  |
| 42 | I ensure the safety of my premises |  |  |
| 43 | I always cut grasses around my house |  |  |
| 44 | I properly dispose my wastes |  |  |
| 45 | I always ensure that my drainage channels are clean |  |  |
| 46 | I cover my head while cooking |  |  |
| 47 | I preserve my food properly |  |  |
| 48 | I purify my water at home |  |  |
| 49 | I spend much money on water treatment at home |  |  |

PART E:   Health Condition

50.	In your opinion, what are the most important factors responsible for good health in your household?

a)	Access to health care [   ] b)	Clean environment [   ] c) Emergency

preparedness [   ] d) Education [   ] e) Standard of living [   ]

f) Others (Specify) _________________

51.	What factor(s), put your household health at risk?   (Tick as appropriate)

a)	Pollution (air, water, land) [   ] b) Poor/Non ventilated housing [   ]

c)	Poor sanitation/poor personal hygiene [   ] d) Lack of access to health

care facility [   ] e) Indiscriminate disposal of waste [   ] f) Bushes around

the houses [   ] g) Others (specify): _________________

52.	How will you rate the overall health of the household?

a) Very good [   ] b)   Good   [   ] c)	Fair   [   ]  d) Poor [   ] e)   Very poor [   ]

53. 	Has any member of your household contracted the following diseases in the past one year?

| Disease | Yes | No | Don’t know |
| --- | --- | --- | --- |
| River blindness |  |  |  |
| Guinea worm |  |  |  |
| Malaria |  |  |  |
| Typhoid fever |  |  |  |
| Cholera |  |  |  |
| Dysentery |  |  |  |
| STIs |  |  |  |
| HIV/AIDS |  |  |  |
| Skin diseases |  |  |  |
| Worm infestations |  |  |  |

54. Has any member of your household died as a result of contracting the above mentioned diseases in the past one year?

| Disease | Yes | No | If yes State the Number |
| --- | --- | --- | --- |
| River blindness |  |  |  |
| Guinea worm |  |  |  |
| Malaria |  |  |  |
| Typhoid fever |  |  |  |
| Cholera |  |  |  |
| Dysentery |  |  |  |
| STIs |  |  |  |
| HIV/AIDS |  |  |  |
| Skin diseases |  |  |  |
| Worm infestations |  |  |  |

55. Which age group is mostly infected/affected by the above mentioned diseases?

| Age | (Tick) |
| --- | --- |
| 0-5 |  |
| 5-10 |  |
| 11-15 |  |
| 16-20 |  |
| 21-25 |  |
| 26-30 |  |
| 31-35 |  |
| Above 35 |  |

56. Which gender is mostly infected/affected by the above-mentioned diseases?

- Male     (        )       (b)   Female    (       )

57. Which of the following substance(s) is commonly abused within the community?

| Substance | (Tick) |
| --- | --- |
| Cannabis |  |
| Codein |  |
| Tramal |  |
| Zakami |  |
| Kurkura |  |
| Snuff (Angur) |  |
| Solution |  |
| Others (Specify) |  |

Section F:

58. In your own opinion, what is the benefit(s) of this project on the community: ………………………………………………………………………………………………………

………………………………………………………………………………………………………

………………………………………………………………………………………………………………………………………………………………………………………………………………

- In your own opinion, what is the negative impact of this project on the community

………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………………………………………………………………………

- Please describe the leadership structure in this community………………………………………………………………………………………………………………………………………………………………………………………..

……………………………………………………………………………………………………………………………………………..

- Name physical and cultural resources (e.g. sites, structures, natural features of historical, paleontological, religious, other cultural significance) you have in this community:................

……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………….……………………………………………………………………………………………………………………………

Thank you for you

# Annex IV: Pictures of the existing structures at the schools

BAUCHI STATE FGN/AfDB INCLUSIVE BASIC SERVICE DELIVERY & LIVELIHOOD EMPOWERMENT INTEGRATED PROGRAMME.

TERMS OF REFERENCE

ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN (ESMP) FOR THE UPGRADE/CONSTRUCTION OF 3 MODEL SCHOOLS, 3 PRIMARY HEALTH CENTRES (PHCs), 2 TECHNICAL AND VOCATIONAL EDUCATION TRAINING CENTERS (TVET), 3 COMMUNITY TOWN HALL AND WASH FACILITIES IN THE STATE.

- Overview

The Inclusive Basic Service Delivery and Livelihood Empowerment Integration Program (IBSDLEIP) is part of Federal Government efforts toward North East States Emergency Transition, Recovery and Peace building, elaborated by the five-year programmatic “Buhari Plan” of 2016. The programme aligns with interventions by Development Partners (DPs) within the Recovery and Peace Building framework which seeks to support the implementation of the “Buhari Plan”. The overall budgetary requirement for the “Buhari Plan” is currently estimated at 2.13 trillion Naira.

The Programme will contribute to 4.7 % of existing funding gaps in the development strategies priority needs which constitutes 71% of budget needs of the Buhari Plan to help address the inherent socio-economic drivers of the insurgency. The Program emphasizes selectivity, integration and prioritizes support to;

- infrastructure with emphasis on restoration, reconstruction and improvements for Water and sanitation; Primary Health Clinics, basic schools and markets;

- food security and nutrition;

- Water, sanitation and hygiene, primary health care and basic education services and systems strengthening;

- Entrepreneurship, job creation and livelihoods for youth, women and the vulnerable; and

- Social cohesion and psychosocial support as cross cutting.

The Program will help address the needs of an estimated 14 million affected people, including over 2.3 million Internally Displaced Persons, of whom nearly 80 % are women, children, and youth and with special attention to rural households in Local Government Areas affected by the insurgency. The implementation of the Program will span a five -year period, beginning January 2017 to December 2021 and will be financed through an AfDB loan of UA 107.65 million, ADF loan of UA 71.77 million and RWSSI-TF Grant of UA 3.98 million, with an estimated counterpart funding of up to 5.8% (of the Bank’s total financing) by the Federal Government of Nigeria (FGN) and State Governments in the context of reduced revenues spawned by the oil crisis.

1.1 Programme Description

The Program is anchored on two major reinforcing components. The respective sub-components are elaborated below.

Component 1: Service Delivery

This component will promote restoration, access and utilization of basic social services in health, education and water and sanitation- with targeted interventions in infrastructure provision, skills acquisition and upgrading, rural water and sanitation reform and community-based nutrition support programmes. The key principle to be applied in the reconstruction and rebuilding of the North East is “building back better” i.e., ensuring better construction standards and contract terms to ensure durable infrastructure, systems development and human resources for sustainable services. The main outputs to be delivered include (i) improved Gender-sensitive infrastructure/facilities for primary health care, basic education and Water and sanitation; (ii) Enhanced skills acquisition/upgrading for service workers in water, sanitation, health and education systems; (iii) strengthened awareness on hygiene, sanitation  water conservation and environment and Open Defecation Free Environment; (iv) Enhanced Monitoring and Evaluation and demand side accountability in service delivery in health, education and water and sanitation through social accountability measures and (v) enhanced nutrition for infants and pregnant women.

Component II: Economic Recovery

This component will promote job creation and entrepreneurship with focus on youth and women. It will also support the reconstruction of Major markets to recover commerce. Additionally, tailored training to upgrade the skills of artisans and equip them to take better, the economic opportunities arising from public work programmes resulting from reconstruction and rehabilitation of infrastructure in component 1 and other economic integration activities will be undertaken. The component will also support vulnerable households (IDPs) to enhance their economic reintegration and the building of livelihoods with focus on agribusiness. To ensure better targeting of interventions for the vulnerable, the Bank will support the development of state unified social registry which in turns contributes to the development of the national registry compilation for the safety nets programme, co-financed by the World Bank32. Given the socio-cultural context, promoting women’s entrepreneurship and job for female, accessing skills and training programs and facilitating women access to market, require specific gender-focused interventions.  Expected results for this component will therefore include (i) youth/women MSMEs and Entrepreneurship promoted; (iii) unskilled youth (50% female) trained in viable economic ventures and life skills; (iii) Poor household food security and agricultural livelihood opportunities enhanced Intervention Organization Funding framework.

Component III: Institutional Strengthening and Project Management

Institutional strengthening interventions include technical assistance to the Women Empowerment  Fund to facilitate loan disbursement to women SMMEs, enhanced capacities of ministry of Labour  and Employment for enforcement and monitoring of the Private Agency Employment Regulation; enhanced capacity of the Universal Basic Education Commission (UBEC) to implement the National Education Management Information System to support and National Primary Health Care  evidenced based policy and strategy development in the sub sectors of basic education and Primary Health. In addition, the office of the Vice President social Investment Unit will be support to put in place an MIS to facilitate coordination and monitoring of cluster programmes. The programme will also facilitate the development of programme implementation manuals and monitoring and evaluation framework as well as an impact evaluation. The Project Coordination and Implementation Units capacities will also be built to enhance implementation efficiency.

- Physical Project Description

The details description of the physical activities and spatial boundary coverage of such activities in each sub project are as follows;

- The Construction/upgrade activities of 3 PHCs at Duguri, Dagauda and Mashema involves; Clinic premises fencing, Renovation of some existing structures, and provision of Hospital Equipment and the construction of staff quarters with furnishings.

- The Construction/upgrade activities of 3 Model Primary Schools at Yelwan duguri, Dagauda and Mashema involves; Provision of school perimeter fencing, Renovation of some existing, Structures, demolition and alteration and Construction of class room blocks, offices, stores libraries, laboratories, school garden, recreational facilities, construction of staff quarters including furnishings.

- The Construction activities of 3 Community Town Hall at Yelwan duguri, Dagauda and Mashema involves; Provision of main town Hall, Fencing, drainages and furnishings.

- The Construction/upgrade activities of 2 TVET centres at Bauchi and Azare involves; Provision of school premises fencing, Renovation of some existing Structures, demolition and alteration and Construction of new blocks with workshops, Construction of staff quarters including furnishings with ICT equipment.

- The Constructions and Rehabilitations activities of WASH Facilities at Yelwan duguri, Duguri, Dagauda and Mashema and some parts of the State involves; geophysical survey, borehole drilling instillations with Reticulation and construction of toilets buildings with its Hand washing facilities.

- Objectives of the Consultancy Services or the ESIA and ESMP

The objective of the consultancy services is to prepare an Environmental and Social Management Plan (ESMP) for the proposed Upgrade/Construction of 3 Model Schools, 3 PHCs, 2 TVET Centers, 3 Community Town Hall and WASH facilities in some parts of the State.  The Environmental and Social Management Plan (ESMP) shall consequently be teased out from: (i) the baseline information gathered from the specific activities locations, (ii) the interface between the various activities such as described in section 2.0 above and the various environmental and socioeconomic activities such as the climate, quality of air, ambient noise, surface water quality, groundwater quality, soil quality, fauna and flora, demography, social services, market activities, communities’ perception, health conditions, domestic wastes types and disposal, etc. The ESMP must be specific to this project and not generic. It should also be implementable within the project life span.

The consultant will work in close collaboration with the Project Implementation Unit’s (PIU), and with other actors as directed by the PIU. The Consultant is expected to make reference to the technical designs/drawing of the proposed works. The documents should be obtained from the (PIU). The consultant will take into account the proposed civil engineering designs and other activities that would be carried out within the project location.

4.0 Scope of the ESMP and the Bank’s Guiding Principle

The scope of the consultancy services includes the preparation of the ESMP in accordance with The African Development Bank policies on the Environmental and Social Assessment (OS1), Involuntary resettlement, land acquisition, population displacement, and compensation (OS2), Biodiversity, renewable resources and ecosystems services (OS3), Pollution Prevention and Control, Hazardous Materials and Resources Efficiency (OS4), Labour Conditions, Health and Safety (OS5),

The Federal Ministry of Environment legislations on Environmental Impact Assessment (EIA), will be the guiding principles for developing and implementing the ESMP.

The project activities as described in section 2.0 above will interface with the biophysical, climate, socio economic and human health components of the environment, at such, the ESMP must consider these interactions and identify the impacts as well as proffer mitigation measures with monitoring indicators.

The biophysical, climate, socio economic and human health components of the environment that will potentially be impacted during the construction/rehabilitation of 3 Model Schools, 3 PHCs, 2 TVET Centers,3 Community Town Hall and WASH facilities activities will include but not limited to: ambient air and noise, land take, soil quality, livelihood means, employment, road transportation, groundwater, surface water, vegetative plant cover, migrant workers and job seekers especially youths, ethno religious set up, health and safety conditions of project implementation workers and locals around project area, waste management, etc.

The impacts of these activities shall be fully identified, appropriate mitigation/amelioration measures fully proffered and costed.

4.1: Scope of data for the Environmental and Social Management Plans

The Environmental and Social Management Plans (ESMP) report to be prepared by the consultant shall be in accordance with the format stipulated in the Bank’s ISS and ESAP document thus:

The Environmental and Social components to be studied include but not limited to the following:

- Weather and Climatic Conditions and Green House Gases

- Ambient Air Quality and Noise

- Soil Conditions

- Surface Water (where available):-, pH, Cond. TDS, Turbidity. DO, BOD5. COD, O/G, Chloride, Nitrate, Salinity, Sulphate, Carbonate, Heavy Metals (Mn, Fe, Cu, Zn, V, Ni, Cd, Pb, Cr), Microbiology (total coliforms, fecal coliforms, heterotrophic bacteria and fungi), Planktons, Fisheries, Sediment (Mn, Fe, Cu, Zn, Pb, Ni, Cd, Cr, Co, V, Ca, Mg, K, Na, Ba, Plankton, benthic macro fauna).

- Groundwater from existing boreholes and wells (same physicochemical and microbiological parameters as for surface water)

- Social Characteristics (Ethno – demographic characteristics, Religion, believes and Taboos, Population, livelihood and socioeconomic activities, Infrastructure, governance, perception towards proposed project.

- Health (morbidity/ mortality across the various age strata and gender, health status available health institutions, and facilities, health risks (HIV/AIDS, STIs, etc.) Substances abuse, sanitation ad hygiene Waste type, management and disposal.

The consultant shall generate data (from laboratory, field observations, and statistical analysis) on the above Environmental and Social components that constitute the Baseline Data. The consultant shall then carry out an assessment of the potential direct, indirect, and cumulative impacts likely to occur as a consequence of project activities. The consultant shall then proffer mitigation and amelioration measures.

4.2 Assessment of Potential Impacts and Mitigation Measures

The identification and evaluation of associated and potential impacts of   Upgrade/Construction of 3 Model Schools, 3 PHCs, 2 TVET Centers, Community Town Hall and WASH facilities and associated activities shall be conducted with accordance with standard methodology thus:

- Identification of Impacts sources, indicators and prediction of magnitude

- Evaluation of the importance of environmental component interfacing with the construction activity (e.g. importance of the site area to the public)

- Evaluation of the impacts from the activities (using models such as the Risk Assessment Matrix, Strength Assessment Matrix

- Description of the impacts at the various project phases

- Classification of Impacts (Incremental, Cumulative, Residual, Adverse, Beneficial, short term, long term, Reversible, Irreversible, direct and indirect

- Hazards and Risks

4.3 Consultations and Disclosures

The consultant will carry out public consultations for the project, to collate the concerns, expectations, and opinions of affected, concerned and interested stakeholders.

The consultation with the various stakeholders to the project shall include the Federal Ministry of Environment, the government of Bauchi State, and the project affected LGAs of the areas of the state. The Project Affected Persons (PAPs), Community Based Organizations, Non-Governmental Organizations, etc.

5.0 Environmental and Social Management Plan (ESMP)

The consultant shall prepare a comprehensive Environmental and Social Management Plan that has been teased out of the baseline data and project activities. The ESMP shall describe the various methods and procedures that shall be employed in enhancing the positive and beneficial impacts and mitigating the adverse ones.

(1) ESMP Objectives and Scope

(2) Institutional Arrangement for ESMP Implementation

(3) Disclosure of E&S Safeguards Instruments

(4) Training and Awareness Programs

(5) Chemical Management

(6) Waste Management

(7) Monitoring and Reporting (includes description of monitoring programs and reporting requirements, and the presentation of (1) ESMP table, and (2) E&S monitoring table.

(8) Cost Estimates for ESMP Implementation

The ESMP also indicates the action party to ensure the implementation of these measures, the specific period and duration during the various phases and the cost implication.

The context section of the ESMP shall describe and analyse the physical, biological and human conditions prevailing in Bauchi State, where the project facility is to be located. The context section shall also outline existing interrelations between physical, ecological and social processes. These interrelations among components shall be measures to be taken into account in the impact assessment and the development of mitigation/enhancement measures.

Measures for enhancing overwhelming benefits of the health facilities in the respective states shall also be outlined.

5.1 Responsibilities and Institutional Arrangements

The ESMP shall identify the responsibilities of the Bank, the Borrower, the implementing agencies and other stakeholders especially the country environmental and social safeguard agencies in applying the ESMP, particularly the monitoring programme. The ESMP shall also propose support to the organization that may have insufficient capacities to fulfil their obligations. This support could be provided through various means including technical assistance, training and/or procurement.

5.2 Implementation Results Schedule and Reporting

The ESMP shall include a results matrix, an implementation schedule taking into account all activities related to the proposed measures (enhancement and mitigation, the monitoring programme, consultations, complementary initiatives and institutional arrangements. The implementation schedule shall be developed by phases and in co-ordination with the overall project implementation plan.

Reporting on the progress on the implementation of the ESMP shall be incorporated into the Implementation Progress and Results Report (IPPR). The section of the IPPR that reports the ESMP implementation shall outline the result achieved and any remaining E&S outstanding issues.

5.3 Conclusion

The conclusion shall summarise the main expected environmental and social impacts and mitigation and enhancement measures that will ensure that the project meets the Bank’s Safeguards requirements. It shall also specify the environmental and social loan conditions or covenants that are part of the project loan agreements.

6.0. Project Affected Persons (PAPs)

Where applicable, the consultant shall identify the presence of Project Affected Persons in the locations of the facility.

7.0 The ESMP Consultant Qualifications

The Consultant and key members of his team should at least have the following requirements:

At least a Master’s degree in Environmental Studies, Natural Resource Management, Environmental Policy or a related discipline;

A minimum of six (6) years of relevant professional experience in areas related to environmental and natural resource management, environmental assessment, environmental monitoring and environmental stewardship;

A good knowledge and experience in developing and managing the implementation of Environmental and Social Impact Assessments (ESIAs), Environmental and Social Management Plans (ESMP), the social aspects of development projects (health and safety aspects, involuntary resettlement and gender issues, etc.), monitoring, evaluation and conformity assessment;

A proven knowledge and practice of ISS, including the safeguards policies, procedures and practices of development agencies of key bilateral and multilateral partners in regional member countries.

A good knowledge and experience of multi-criteria assessments, stakeholder engagement and consultation, community participation; analytical skills to assess institutional capacity and to design/ review practical arrangements for implementing complex projects, particularly in Africa;

A results-oriented, able to work in a team, a meticulous analyst with a sense of detail, a persuasive communicator and an excellent copywriter;

Listening to clients - providing effective services and solutions to staff beyond presenting past challenges and able to gain respect through the depth of demonstrated expertise, effectively managing various clients and country situations;

Innovation and Change - Constantly seek more efficient and practical methods for the delivery of services and products as well as departmental process management and propose new ways to improve the quality and relevance of products and services;

Demonstrated ability to work effectively in a multicultural environment and to develop effective working relationships with clients and colleagues;

Have excellent technical and analytical skills, with a proven track record in operational and political work on environmental and social issues;

Have a good knowledge of the assessment, preparation and/or management of the implementation of the Bank's environmental and social safeguards for the development of major infrastructures in Africa;

Have a good knowledge of the environmental and social issues facing Regional Member Countries (RMCs);

Have solid practical experience in the evaluation, integration and monitoring of social development concerns at the level of Bank operations.

Have ability to work accurately with minimal supervision for achieving results within set time frame.

Ethical requirements

Before undertaking any activity, the Consultants’ team will make sure that it understands all ethical considerations related to Gender-based violence (GBV) in particular Sexual Exploitation and Abuse (SEA). The consultant should not collect any primary data and should NOT conduct interviews or research using the SEA survivors and will only make use of secondary sources and data. This is with the objective to minimize harm to women and children.

8.0 Deliverables

A comprehensive and fully referenced Report including detailed recommended actions for implementation must be submitted at the end of the assignment. The Report shall contain an in-depth analysis of the issues described in the objectives and should propose clear, implementable measures towards achieving the set goals of the ESMP.

Quality Assurance and Quality Control

The maps, figures, and plates provided in the report should be clearly legible, specific to the study area and providing adequate information required. The geographic coordinates of the various sampling locations shall also be provided for future reference purposes.

Chromatogram plot outs, Chain of Custody, and Laboratory analysis certifications shall be included as annexes to the ESMP.

Report Structure

The table below is some of the contents in the structure of the ESMP report:

| S/N | SECTION | SUB-SECTION |
| --- | --- | --- |
| 1. | Premilaries | - Cover page - Table of contents - List of Abbreviations and Acronyms - List of Tables - List plates - List of Figures - List of Annexes |
| 2. | Executive Summary | - Summary of each chapter of the report |
| 3. | Chapter one Introduction | 1.1 Introduction 1.2 Project Background 1.3 Objectives of the ESMP 1.4 Scope of ESMP and Applicability - 1.5 Policy, Legal, and Regulatory Frameworks - 1.6 African Development Banks Environmental and Social Safeguards Policies |
| 4. | Chapter Two Project Justification | - 2.1 Introduction - 2.2 Project Justification - 2.3 Project Sustainability |
| 5 | Chapter Three Project Description | - 3.1 Introduction - 3.2 Project Location (including legible maps showing specific locations of the proposed facilities) - 3.3 Project Facilities (i.e., Existing and Proposed Facilities including site layouts, drawings/diagrams) - 3.4 Description of the Construction Activities - 3.5 Description of Operational Activities - 3.6 Description of Decommissioning Activities - 3.7 Sourcing of materials (i.e., a description of sources of raw materials and water for use in the project). - 3.8 Manpower - 3.9 Waste (i.e., provide an inventory of the types and volumes of waste expected from the project) - 3.9 Project Schedule (i.e., a schedule of activities and timelines from pre-construction > construction > commissioning/operational phase. |
| 6 | Chapter Four Description of the Baseline Environment | ## 4.1 Introduction ## 4.2 Study Approach and Methodology ## 4.3 Spatial Boundary for the Study ## 4.4 Environmental Components of the Study ## 4.5 Description of Sampling Activities (i.e., locations/stations and their coordinates, and sample numbers for each environmental component of interest. A sampling map should be included, where possible, as well as few pictures of the field activities) ## 4.6 Quality Assurance/Quality Control ## 4.7 Biophysical Environment ## 4.8 Socioeconomic Environment |
| 7. | Chapter Five Potential Impacts | 5.1 Introduction 5.2 Impact Assessment Methodology 5.3 Potential Impacts (present the impact assessment table structured to capture the individual phases (pre-construction, construction, operational and decommissioning) of the project and impacts during each phase. Also, the impact evaluation and significance rating.) 5.33.1 Positive Environmental and Social Impacts (briefly describe based on the impact assessment table) 5.3.2 Negative Environmental and Social Impacts (briefly describe the significant i.e., moderate – high adverse impacts) 5.3.3 Cumulative impacts (describe if any) |
| 8 | Chapter Six Mitigation and Enhancement Measures | 6.1 Introduction 6.2 Mitigation Approach 6.3 Mitigation and Enhancement Measures |
| 9. | Chapter Seven Environmental and Social Management Plan | 7.1 Introduction 7.2 ESMP Objectives and Scope 7.3 Institutional Arrangement (i.e., for ESMP Implementation) 7.4 Disclosure of E&S Safeguards Instruments 7.5 E&S Compliance Audit 7.6 Training, Capacity Building and Awareness Programs 7.7 Waste Management 7.8 Monitoring and Reporting (includes description of monitoring programs and reporting requirements, and the presentation of (1) ESMP table, and (2) E&S monitoring table. 7.9 Cost Estimates for ESMP Implementation |
| 10. | Chapter Eight Stakeholder Consultations | 8.1 Introduction 8.2 Consultations with relevant stakeholders |
| 11. | Chapter Nine Grievance Redress Mechanism | ## 9.1 Introduction ## 9.2 Grievance Redress Process 9.3 Designated staff coordinating Grievance Redress 9.4 Mode of receipt and recording of Complaints ## 9.5 Structure of Grievance Redress ## 9.6 GRM Jurisdiction ## 9.7 AfDB GRM |
| 12 | Chapter Ten Conclusion | 10.1 Conclusion |
| 13 | References |  |
| 14 | Annexes |  |